## Data
ChangeID | Summary | Priority | StatusReason | Impact | ChangePlanning | Submitter | Coordinator | SubmitDateTime | SchStartDateTime | SchEndDateTime | ActualStartDateTime | ActualEndDateTime | CompletedDateTime | ClosedDateTime | CompletedYear | CompletedMonth | ChangeSuccess | ProdCat2 | ProdCat3 | OpCat1 | OpCat2 | Customer | CustomerOpco | CustomerGroup | CustomerDept | ApprovalDateTime | SchForAppDateTime | ImpInProgDateTime | LastModifiedDate | CompletedYearQtr | ClosedMonth | ClosedYearQtr
CRQ000000278909 | AL, Birmingham, APC HQ and Leeds Nokia/Turf Club OLT circuit cutover | Low | Successful | Minor | Planned | GPB | TT | 44966.4459 | 44980.75 | 44981 | 44980.7514 | 44980.8333 | 44981.4006 | 44981.4008 | 2023 | 2023-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44972.451 | 44971.5209 | 44980.737 | 44981.4008 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000278912 | GA, Atlanta, Distribution ROW, Repair damaged section of cable. | Medium | Successful | Moderate | Planned | JLM | TT | 44966.5461 | 44982.3333 | 44982.75 | 44982.3333 | 44982.5875 | 44984.4037 | 44984.4079 | 2023 | 2023-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44967.6962 | 44967.4648 | 44982.3204 | 45519.4679 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000278914 | GA, YPSILANTI LTE G8144, REPLACE LMR-400 COAXIAL IF FEEDERS ON MINILINK | Low | Successful | Minor | Planned | WKA | TT | 44966.5617 | 44972.2917 | 44973.7083 | 44972.2917 | 44972.7083 | 44973.4993 | 44973.4995 | 2023 | 2023-02 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44970.6179 | 44970.6004 | 44972.2788 | 45519.4801 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000278918 | AL, Bessemer, Reconfigure fiber between Bessemer TS and Leaf Lake | Medium | Successful | Moderate | Planned | RRR | TT | 44966.6195 | 44977.7917 | 44978 | 44977.7965 | 44977.9979 | 44978.3859 | 44978.3972 | 2023 | 2023-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44967.6247 | 44967.4626 | 44977.7787 | 45519.4679 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000279007 | AL, BIRMINGHAM, APC CORP HQ, TURF CLUB DS CABINET, RECONFIG BACKHAUL TO NOKIA SAR | Low | Successful | Minor | Planned | ZPE | TT | 44966.4702 | 44980.75 | 44981 | 44980.75 | 44981 | 44981.4024 | 44981.4026 | 2023 | 2023-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ZP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44972.4507 | 44971.5229 | 44980.737 | 44981.4026 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000279413 | GA, Savannah ICON Ring, Create SWAN and SoNet port settings for DHA/LFL | Medium | Successful | Moderate | Planned | RPY | TT | 44967.5948 | 44986.375 | 44986.75 | 44986.3833 | 44986.6028 | 44986.607 | 44986.6084 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44971.4151 | 44970.621 | 44986.3622 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000279600 | GA, Lakeland ENODEB, Emergency Hybrid Replacement | Low | Successful | Minor | Planned | LPE | TT | 44969.5317 | 44977.4583 | 44977.5833 | 44977.4583 | 44977.5833 | 44977.592 | 44977.6022 | 2023 | 2023-02 | Successful | Facilities Component | Cables, jumpers, and connectors | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 44970.6179 | 44970.5983 | 44977.4455 | 44977.6022 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000279810 | AL, Northport, Bankhead DAM, NGTAN circuit cutover. | Low | Successful | Minor | Planned | GPB | TT | 44970.4714 | 44979.4167 | 44979.625 | 44979.4167 | 44979.5201 | 44979.7046 | 44979.7052 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44971.4121 | 44970.6193 | 44979.4039 | 44979.7052 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280127 | AL, Ensley LTE site AT&T Circuit migration | Low | Successful | Minor | Planned | DRI | TT | 44971.7028 | 44979.375 | 44979.5417 | 44979.4167 | 44979.4313 | 44979.7016 | 44979.7041 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44973.6158 | 44973.6089 | 44979.3622 | 44979.7041 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280220 | AL, Thomasville LTE, guy wire tension and tower plumb checks | Low | Successful | Minor | Planned | CDL | TT | 44971.6112 | 44986.4583 | 44988.8333 | 44986.4583 | 44988.8333 | 44991.4022 | 44991.4024 | 2023 | 2023-03 | Successful | Transport Device | Tower Structure | Repair | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 44978.3633 | 44977.5783 | 44986.4456 | 44991.4024 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000280227 | MS, NASA Area, Migrate NASA/Logtown West Subtations To NGTAN | Medium | Successful | Moderate | Planned | DRB | TT | 44971.6933 | 44985.4167 | 44985.75 | 44985.4167 | 44985.7458 | 44986.3977 | 44986.4054 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44973.5832 | 44973.534 | 44985.4037 | 44986.4054 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000280230 | AL, Liberty Park LTE AT&T Circuit migration | Low | Successful | Minor | Planned | DRI | TT | 44971.6994 | 44980.375 | 44980.5417 | 44980.375 | 44980.5417 | 44980.562 | 44980.5635 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44973.6158 | 44973.6104 | 44980.3621 | 44980.5635 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280321 | AL, Cahaba Heights LTE site Circuit migration | Low | Successful | Minor | Planned | DRI | TT | 44971.7055 | 44979.5417 | 44979.7083 | 44979.5653 | 44979.5868 | 44980.431 | 44980.4311 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44973.6158 | 44973.6096 | 44979.5285 | 44980.4311 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280505 | AL, Trussville, Splicing dark fiber for CSpire Handoff | Low | Successful | Minor | Planned | RCA | TT | 44972.4021 | 44979.3333 | 44981.7917 | 44979.3333 | 44981.7917 | 44984.4027 | 44984.4028 | 2023 | 2023-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 44973.6158 | 44973.6077 | 44979.3204 | 45519.4588 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280511 | AL, Jasper, Splicing dark fiber for CSpire handoff | Low | Successful | Minor | Planned | RCA | TT | 44972.5303 | 44984.3333 | 44988.7917 | 44984.3333 | 44985.4167 | 44985.4302 | 44985.4304 | 2023 | 2023-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 44973.5345 | 44973.5311 | 44984.3203 | 45519.4588 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000280521 | AL, Birmingham, APC HQ Nokia SAR 7750 Software upgrade. | Low | Successful | Minor | Planned | GPB | TT | 44972.7134 | 44984.75 | 44984.875 | 44984.75 | 44984.7896 | 44985.3958 | 44985.396 | 2023 | 2023-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44973.6165 | 44973.5322 | 44984.7369 | 44985.396 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000281101 | Advisory/Oper Event: AL - WILMER - FIBER RELOCATION - NCC-13949 | Low | Successful | Std/PreApp | Planned | HHA | HH | 44974.3474 | 44980.0417 | 44980.25 | 44980 | 44980.3361 | 44980.344 | 44980.3442 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44974.3532 | 44974.3532 | 44980.0287 | 44980.3442 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000281215 | GA, VIENNA LTE G8325, DEKEY SO LINC LTE AND MINILINK MICROWAVE | Low | Successful | Minor | Planned | WKA | TT | 44974.6352 | 44980.75 | 44980.8333 | 44980.75 | 44980.8333 | 44981.4013 | 44981.4015 | 2023 | 2023-02 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44978.3608 | 44977.56 | 44980.737 | 45519.4801 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000281400 | FL, Paxton, Paxton ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 44975.403 | 45000.3333 | 45000.7083 | 45000.3333 | 45000.7014 | 45000.7083 | 45000.7084 | 2023 | 2023-03 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 44978.3645 | 44977.5633 | 45000.3211 | 45000.7084 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281509 | GA, Atlanta & Savannah ICON Ring, Port turn up for SWAN DHA & LFL | Medium | Successful | Moderate | Planned | RPY | TT | 44977.5336 | 45022.375 | 45022.7083 | 45022.375 | 45022.5 | 45022.548 | 45022.5483 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.6503 | 44978.5616 | 45022.3622 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000281607 | GA, BRUSNWICK, PLANT MCMANUS, TROUBLESHOOT SAR TRANSPORT LINK | Medium | Successful | Moderate | Planned | WKA | TT | 44977.4794 | 44985.7083 | 44985.875 | 44985.7153 | 44985.7958 | 44986.4043 | 44986.4055 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44978.4657 | 44977.813 | 44985.6953 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281615 | GA, Atlanta ICON Ring, Port turn for SWAN DHA & LFL | Medium | Successful | Moderate | Planned | RPY | TT | 44977.531 | 45008.375 | 45008.7083 | 45008.375 | 45008.7049 | 45008.7503 | 45008.7549 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.6705 | 44978.561 | 45008.3628 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281616 | GA, Atlanta ICON Ring, Port turn up for SWAN DHA & LFL | Medium | Successful | Moderate | Planned | RPY | TT | 44977.5359 | 45029.375 | 45029.7083 | 45029.375 | 45029.7083 | 45030.4627 | 45030.4677 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.658 | 44979.5603 | 45029.3622 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000281715 | GA, Atlanta and Savannah ICON Ring, Move SWAN to DHA AND LFL path | Medium | Successful | Moderate | Planned | RPY | TT | 44977.5234 | 45001.375 | 45001.7083 | 45001.375 | 45001.7083 | 45002.5065 | 45002.5165 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.649 | 44978.56 | 45001.3623 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281716 | GA, Savannah ICON Ring, Turn ports up for SWAN to DHA & LFL | Medium | Successful | Moderate | Planned | RPY | TT | 44977.5287 | 45007.375 | 45007.7083 | 45007.375 | 45007.7083 | 45008.7492 | 45008.7548 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.6469 | 44978.5723 | 45007.3622 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281917 | AL, GA, MS, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 44978.5248 | 44987 | 44987.0833 | 44987 | 44987.1194 | 44987.4162 | 44987.4199 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44979.6571 | 44979.5588 | 44986.987 | 44987.4199 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000281925 | MS, GULFPORT, MPC OP CTR UPS -1 DECOMM | Medium | Successful | Moderate | Planned | MVW | TT | 44978.5845 | 44989.3333 | 44989.75 | 44989.3333 | 44989.5042 | 44991.3981 | 44991.4016 | 2023 | 2023-03 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Remove/Retire | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 44980.499 | 44980.4836 | 44989.3205 | 45498.7092 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282001 | AL, Birmingham, APC HQ NGTAN Circuit Cut | Medium | Successful | Moderate | Planned | GPB | TT | 44978.3917 | 44985.4167 | 44985.75 | 44985.4167 | 44985.75 | 44986.4071 | 44986.4084 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44978.4551 | 44978.4054 | 44985.4037 | 44986.4084 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282207 | GA, Cornelia, Rabun Gap, Alex, Long & Currahee Mtn, Winder, NOKIA circuit migration. | Medium | Successful | Moderate | Planned | TSE | TT | 44979.4451 | 44992.3333 | 44993.9583 | 44992.3333 | 44993.7431 | 44994.3863 | 44994.4095 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44980.6462 | 44979.6984 | 44992.3205 | 45341.1766 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282216 | AL, Barry SP Ring, Nodes need to be set to Single tie nodes | Low | Successful | Minor | Planned | RPY | TT | 44979.635 | 44998.4375 | 44998.7083 | 44998.4771 | 44998.65 | 44998.6894 | 44998.6895 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44980.6385 | 44980.4851 | 44998.4179 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282222 | AL, Roanoke, East Roanoke Switching Substation, Migrate Leased Circuit | Low | Successful | Minor | Planned | JBS | TT | 44979.6812 | 44993.375 | 44993.8333 | 44993.4118 | 44993.5153 | 44994.4954 | 44994.4956 | 2023 | 2023-03 | Successful | Transport Device | CSU / DSU | Migrate | Transport | JBS | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 44979.7689 | 44979.7136 | 44993.3621 | 45519.4508 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282422 | AL, Anniston, Transport Upgrade Nokia SAR 7705-A8 | Low | Successful | Minor | Planned | GPB | TT | 44980.6667 | 44994.4167 | 44994.5417 | 44994.4958 | 44994.5292 | 44994.574 | 44994.5748 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44981.5563 | 44981.4378 | 44994.4038 | 44994.5748 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282505 | GA, Roswell EBTS building, Replace coax and possibly defective RAU | Low | Successful | Minor | Planned | RGK | TT | 44980.4917 | 44984.375 | 44984.7083 | 44984.3979 | 44984.5153 | 44984.7125 | 44984.7135 | 2023 | 2023-02 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | RGK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44980.5781 | 44980.5615 | 44984.362 | 45519.4801 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000282510 | AL, Birmingham ICON ring, DS1 Sync and FX circuit removal due to not needed (BACKUP DATE) | Medium | Successful | Moderate | Planned | RPY | TT | 44980.5434 | 45005.4167 | 45005.7083 | 45005.4382 | 45005.6854 | 45005.7016 | 45005.7064 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44981.5986 | 44981.442 | 45005.4038 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282518 | AL, Montgomery, J St and SDC, Nokia SAR 7750 and 7705-A8 Software Upgrade | Low | Successful | Minor | Planned | GPB | TT | 44980.649 | 44987.4167 | 44987.7083 | 44987.4167 | 44987.5938 | 44988.4305 | 44988.4306 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44981.5577 | 44981.4302 | 44987.4037 | 44988.4306 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282519 | AL, Birmingham, Leeds and Colonnade, Nokia SAR 7705-A8 Software Upgrade | Medium | Successful | Moderate | Planned | GPB | TT | 44980.6613 | 44992.4167 | 44992.7083 | 44992.4174 | 44992.6375 | 44994.4082 | 44994.4096 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44981.6132 | 44981.4324 | 44992.4039 | 44994.4096 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282606 | Advisory/Oper Event: GA - WAYCROSS - FIBER REPAIR - NCC-14059 | Low | Successful | Std/PreApp | Planned | HHA | HH | 44980.4834 | 44986 | 44986.25 | 44986 | 44986.2917 | 44986.3544 | 44986.3545 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44980.4887 | 44980.4887 | 44985.9871 | 44986.3545 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282608 | Advisory/Oper Event: GA - TIFTON - SOFTWARE UPGRADE - NCC-14110 | Low | Successful | Std/PreApp | Planned | HHA | HH | 44980.4979 | 44986 | 44986.25 | 44986 | 44986.1125 | 44986.3554 | 44986.3555 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44980.5043 | 44980.5043 | 44985.9871 | 44986.3555 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282612 | AL, Birmingham ICON Ring, NPAD transmitted more than once. Circuit needs to be rebuilt | Medium | Successful | Moderate | Planned | RPY | TT | 44980.5824 | 45012.4167 | 45012.7083 | 45012.4618 | 45012.7604 | 45013.4132 | 45013.4147 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44981.5931 | 44981.4437 | 45012.4039 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282704 | GA, REIDSVILLE EBTS, REPLACE NPU MODULE ON ERICSSON MINILINK | Low | Successful | Minor | Planned | WKA | TT | 44981.4084 | 44988.375 | 44988.4583 | 44988.375 | 44988.4472 | 44991.3995 | 44991.3996 | 2023 | 2023-03 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44981.4803 | 44981.4721 | 44988.3628 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000282717 | Advisory/Oper Event: GA - NORCROSS - FIBER MAINTENANCE NCC-14121/14123 | Low | Successful | Std/PreApp | Planned | HHA | HH | 44981.6343 | 44985 | 44985.25 | 44984.9771 | 44985.2396 | 44985.3098 | 44985.31 | 2023 | 2023-02 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44981.6417 | 44981.6411 | 44984.9869 | 44985.31 | 2023-Q1 | 2023-02 | 2023-Q1
CRQ000000282903 | GA, Fowlstown LTE, Router replacement | Low | Successful | Minor | Planned | DRI | TT | 44981.5121 | 44991.375 | 44991.5417 | 44991.375 | 44991.5417 | 44991.7446 | 44991.7459 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44985.7332 | 44985.5658 | 44991.3622 | 44991.7459 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000283612 | AL, Mobile Div Office, Nokia 7705-A8 Software Upgrade | Medium | Successful | Moderate | Planned | GPB | TT | 44984.6211 | 45001.4167 | 45001.5417 | 45001.4215 | 45001.45 | 45001.6361 | 45001.6411 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44988.592 | 44985.6108 | 45001.404 | 45001.641 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000283615 | GA, Menlo LTE, Replace coax and connectors on Microwave radio | Low | Successful | Minor | Planned | RGK | TT | 44984.651 | 44991.375 | 44991.7083 | 44991.375 | 44991.7083 | 44992.3897 | 44992.3898 | 2023 | 2023-03 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | RGK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44985.7318 | 44985.5642 | 44991.3622 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000283703 | GA, Atlanta ICON Ring, Port turn up between ATL Water Storage & NW 115 | Medium | Successful | Moderate | Planned | RPY | TT | 44985.3533 | 44998.375 | 44998.5417 | 44998.3778 | 44998.5611 | 44998.6165 | 44998.6175 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44988.5927 | 44985.6092 | 44998.3622 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000283710 | AL, Thomasville LTE A9443, install CBRS on the tower | Low | Successful | Minor | Planned | CDL | TT | 44985.4119 | 44998.375 | 45002.8333 | 44998.375 | 45002.8333 | 45005.4083 | 45005.4086 | 2023 | 2023-03 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 44985.7409 | 44985.5679 | 44998.3622 | 45005.4086 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000283808 | AL, Thomasville LTE A9443, install CBRS on the tower (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 44985.412 | 45012.375 | 45014.8333 | 45012.375 | 45013.6667 | 45013.6724 | 45013.6726 | 2023 | 2023-03 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45002.546 | 45002.5183 | 45012.3622 | 45013.6726 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284002 | AL, Anniston area, NGTAN Circuit Cut. | Low | Successful | Minor | Planned | GPB | TT | 44986.4454 | 44993.625 | 44993.7917 | 44993.6285 | 44993.8604 | 44994.3883 | 44994.3884 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44988.5962 | 44986.6007 | 44993.6119 | 44994.3884 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284111 | GA, Union City, Transmission ROW, Roll to new section of cable | Medium | Successful | Moderate | Planned | JLM | TT | 44986.4714 | 45003.3333 | 45003.75 | 45003.3361 | 45003.7146 | 45005.41 | 45005.4114 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44988.5962 | 44986.6027 | 45003.3211 | 45519.4679 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284112 | GA, Macon, Key St. DCC, Permanent Repair of damaged cable feeding the DCC | Medium | Successful | Moderate | Planned | JLM | TT | 44986.4933 | 45004.3333 | 45004.75 | 45004.3333 | 45004.609 | 45005.4122 | 45005.414 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44988.6011 | 44986.6052 | 45004.3204 | 45519.4679 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284116 | GA, Atlanta ICON Ring, Ports to be turned up at Clarkston and Scottdale | Medium | Successful | Moderate | Planned | RPY | TT | 44986.5903 | 45040.375 | 45040.7083 | 45040.375 | 45040.5833 | 45040.6113 | 45041.4078 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44988.6004 | 44987.701 | 45040.3621 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000284121 | MS, GULFPORT, MPC OPS CNTR, Upgrade MPC OPS Center SAR-a8 Software | Low | Successful | Minor | Planned | DRB | TT | 44986.7213 | 44993.6667 | 44993.7917 | 44993.6868 | 44993.734 | 44994.3844 | 44994.3845 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44987.7284 | 44987.4727 | 44993.6536 | 44994.3845 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284210 | GA, Atlanta ICON Ring, move fibers from Old Clarkston to new Clarkston | Medium | Successful | Moderate | Planned | RPY | TT | 44986.567 | 45006.375 | 45006.7083 | 45006.375 | 45006.6278 | 45006.6713 | 45006.6754 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44988.599 | 44987.5078 | 45006.362 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284212 | GA, Atlanta ICON Ring, Clarkston ICON node to be inserted | Medium | Successful | Moderate | Unplanned | RPY | TT | 44986.576 | 45021.375 | 45021.7083 | 45021.4083 | 45021.6062 | 45021.6744 | 45021.6758 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45020.5736 | 45020.5008 | 45021.3594 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000284214 | GA, Atlanta ICON Ring, Ports to be turned up at Clarkston, Ponce, and Norcross 002 | Medium | Successful | Moderate | Planned | RPY | TT | 44986.585 | 45026.375 | 45026.7083 | 45026.375 | 45026.5819 | 45026.6202 | 45026.6243 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44988.5997 | 44987.5111 | 45026.362 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000284217 | GA, Atlanta ICON Ring, connect fibers between Norcross002 and Ponce de Leon (BACKUP DATE) | Medium | Successful | Moderate | Planned | RPY | TT | 44986.5961 | 45000.375 | 45000.7083 | 45000.3799 | 45000.684 | 45000.6992 | 45000.7046 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 44988.5976 | 44987.5069 | 45000.3628 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284407 | GA, Virginia Ave, Nokia 7750a8 firmware OS upgrade. | Medium | Successful | Moderate | Planned | TSE | TT | 44987.5085 | 45005.4583 | 45005.7083 | 45005.4583 | 45005.6347 | 45005.732 | 45005.7334 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44995.5707 | 44991.4098 | 45005.4455 | 45341.1766 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284415 | AL, GOODWATER, HOLLINS TRANSPORT, DC/BATTERY RACK INSTALLATION | Low | Successful | Minor | Planned | MVW | TT | 44987.6788 | 45005.375 | 45009.6667 | 45005.375 | 45009.6667 | 45012.3967 | 45012.3968 | 2023 | 2023-03 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 44987.7291 | 44987.7061 | 45005.3621 | 45498.7092 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284503 | GA, Columbus, Nokia 7750a8 firmware OS upgrade. | Medium | Successful | Moderate | Planned | TSE | TT | 44987.4791 | 45005.4167 | 45005.7083 | 45005.4167 | 45005.4688 | 45005.5825 | 45005.5846 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44988.5955 | 44987.5048 | 45005.4038 | 45341.1766 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000284514 | AL, DELTA, CHEAHA MTN TRANSPORT, DC/BATTERY INSTALLATION | Low | Successful | Minor | Planned | MVW | TT | 44987.6831 | 45012.375 | 45016.6667 | 45012.375 | 45016.6667 | 45018.9605 | 45018.9632 | 2023 | 2023-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 44987.7291 | 44987.7072 | 45012.3622 | 45498.7092 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000284705 | GA, Commerce to Carnesville, Waveguide pressure alarm on primary path | Medium | Successful | Moderate | Unplanned | CJA | TT | 44988.4055 | 44995.7083 | 44995.875 | 44995.7083 | 44995.7611 | 44998.3941 | 44998.3955 | 2023 | 2023-03 | Successful | Transport Device | Antenna System | Repair | Transport | CJA | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44994.5063 | 44994.4898 | 44995.696 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285314 | GA, REIDSVILLE EBTS, REPLACE NPU MODULE ON ERICSSON MINILINK | Low | Unsuccessful | Minor | Planned | WKA | TT | 44991.59 | 44999.3333 | 44999.7083 | 44999.3333 | 44999.5833 | 44999.5922 | 44999.5923 | 2023 | 2023-03 | Unsuccessful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44992.4396 | 44991.755 | 44999.3205 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285316 | MS, Coastal Area, Migrate Gulfport Area and Delisle Dupont Substations to NGTAN | Medium | Successful | Moderate | Planned | DRB | TT | 44991.621 | 45006.4167 | 45006.75 | 45006.4167 | 45006.6257 | 45006.6701 | 45006.6755 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44998.7093 | 44994.4521 | 45006.4037 | 45006.6755 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285523 | AL, Bessemer TS, Final Phase of Fiber Reconfigure for New Bessemer TS | Medium | Successful | Moderate | Planned | RRR | TT | 44992.6491 | 45008.7917 | 45009.125 | 45008.7917 | 45009.2042 | 45009.3681 | 45009.3693 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44995.572 | 44994.63 | 45008.778 | 45519.4679 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285529 | GA, Atlanta, 241 Ralph McGill, LTE Core EPG 2 software Upgrade. | Medium | Successful | Moderate | Unplanned | MHI | TT | 44992.7771 | 45028.9583 | 45029.2083 | 45028.9583 | 45029.2083 | 45029.5318 | 45029.5341 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MH | COM |  | CORE NETWORK ENGINEERING | 45028.6002 | 45028.5966 | 45028.9454 | 45029.5341 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000285608 | AL, South Bessemer TS, Drop Long-Haul dark fibers into 115 and 230 switch houses | Medium | Successful | Moderate | Planned | RRR | TT | 44992.4626 | 45001.7917 | 45002 | 45001.8028 | 45001.9444 | 45002.5071 | 45002.5166 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 44995.5734 | 44994.6118 | 45001.7794 | 45519.4679 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285702 | GA, Macon DCC, monthly generator PM | Low | Successful | Minor | Planned | JCT | TT | 44992.3981 | 44997.3333 | 44997.5 | 44997.3333 | 44998 | 44998.3946 | 44998.3948 | 2023 | 2023-03 | Successful | Facilities Component | Generator | Repair | Transport | JCT | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44992.432 | 44992.4047 | 44997.3205 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285710 | AL, Hueytown EBTS, replace breaker | Low | Successful | Minor | Planned | WJO | TT | 44992.483 | 44999.7708 | 44999.8229 | 44999.7708 | 44999.8229 | 45000.4177 | 45000.4178 | 2023 | 2023-03 | Successful | Facilities Component | DC Backup System | Repair | Transport | WJ | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 44994.468 | 44994.4493 | 44999.7516 | 45519.4508 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285725 | GA, Atlanta, 241 Ralph McGill, LTE Core EPG 1 software Upgrade. | Medium | Unsuccessful | Moderate | Planned | MHI | TT | 44992.7598 | 44998.9583 | 44999.2083 | 44998.9583 | 44999.2083 | 44999.4367 | 44999.4374 | 2023 | 2023-03 | Unsuccessful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MH | COM |  | CORE NETWORK ENGINEERING | 44994.4704 | 44994.4315 | 44998.9453 | 44999.4374 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285727 | AL, Birmingham, APC CORP HQ building, LTE Core EPG 2 software upgrade. | Medium | Successful | Moderate | Planned | MHI | TT | 44992.8005 | 45005.9583 | 45006.2083 | 45005.9583 | 45006.2083 | 45006.407 | 45006.4102 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MH | COM |  | CORE NETWORK ENGINEERING | 44994.4872 | 44994.4347 | 45005.9453 | 45006.4102 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285728 | AL, Birmingham, APC CORP HQ building, LTE Core EPG 1 software upgrade. | Medium | Successful | Moderate | Planned | MHI | TT | 44992.8161 | 45034.9583 | 45035.2083 | 45034.9583 | 45035.2083 | 45035.4046 | 45035.4209 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MH | COM |  | CORE NETWORK ENGINEERING | 45021.6767 | 45021.6724 | 45034.9454 | 45035.4209 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000285839 | GA, AUGUSTA, TRANSPORT BLDG, REPLACE ATS | Low | Successful | Minor | Planned | MVW | TT | 44993.7175 | 45007.3333 | 45007.7083 | 45007.3681 | 45007.7097 | 45008.4343 | 45008.4345 | 2023 | 2023-03 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 44994.6875 | 44994.4943 | 45007.3205 | 45498.7092 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285840 | AL, East Alabama, Clean and/or Migrate Fibers Between North Auburn and Columbus DWDM | Low | Successful | Minor | Planned | DRB | TT | 44993.7512 | 45000.7917 | 45000.9583 | 45000.7917 | 45000.9583 | 45001.6645 | 45001.6646 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 44998.7081 | 44994.4389 | 45000.7787 | 45001.6646 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285842 | GA & AL, Phenix City, Fort Benning #2, NOKIA circuit migration, SWAN Hub consolidation | Medium | Successful | Moderate | Planned | TSE | TT | 44993.8054 | 45008.3333 | 45008.75 | 45008.3639 | 45008.7625 | 45008.764 | 45008.7665 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 44998.7081 | 44998.6031 | 45008.3211 | 45341.1766 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000285917 | GA, Flowery Branch LTE, Replace coax and coax connectors on MiniLink licensed microwave | Low | Successful | Minor | Planned | JTC | TT | 44993.6875 | 45015.375 | 45015.7083 | 45015.375 | 45015.7083 | 45018.9535 | 45018.9552 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 44994.6201 | 44994.6065 | 45015.3621 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000286003 | AL, Pelham, CSpire dark fiber handoff | Low | Successful | Minor | Planned | RCA | TT | 44993.3848 | 45005.2917 | 45009.75 | 45005.2917 | 45009.25 | 45012.3959 | 45012.3961 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 44995.5387 | 44994.4296 | 45005.2787 | 45519.4588 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000286015 | GA, Talmo LTE, Replace coax and coax connectors for MiniLink licensed microwave | Low | Successful | Minor | Planned | JTC | TT | 44993.6931 | 45016.375 | 45016.7083 | 45016.375 | 45016.7083 | 45018.9625 | 45018.9633 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45000.6105 | 44999.4115 | 45016.3623 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000286108 | AL, BIRMINGHAM, INSTALLING NEW DC POWER CONNECTION | Low | Successful | Minor | Planned | SDG | TT | 44994.4841 | 45006.375 | 45007.25 | 45006.375 | 45007.25 | 45007.4374 | 45007.4375 | 2023 | 2023-03 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | SCS | OPERATIONS | STI | 44995.4751 | 44995.4591 | 45006.362 | 45007.4375 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000286126 | MS, GULFPORT, MPC OP CTR UPS-1 COMMISSIONING IN-SERVICE | Medium | Successful | Moderate | Planned | MVW | TT | 44994.764 | 45024.3333 | 45024.7083 | 45024.334 | 45024.5007 | 45026.3974 | 45026.3988 | 2023 | 2023-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45019.5443 | 45018.9291 | 45024.3203 | 45498.7092 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000286127 | AL, SEARLES, LTE TOWER, REPLACE DAMAGED TOWER LIGHT CABLING | Low | Successful | Minor | Planned | MVW | TT | 44994.7676 | 45002.2917 | 45002.75 | 45002.2917 | 45002.75 | 45005.4091 | 45005.4093 | 2023 | 2023-03 | Successful | Facilities Component | Cables, jumpers, and connectors | Repair | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 44995.4742 | 44995.4615 | 45002.2794 | 45498.7092 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287221 | AL, Montgomery, SDC NGTAN Circuit move | Low | Unsuccessful | Minor | Planned | GPB | TT | 44998.6724 | 45007.4167 | 45007.6667 | 45007.4167 | 45007.6667 | 45008.4259 | 45008.4261 | 2023 | 2023-03 | Unsuccessful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45005.4756 | 44999.4136 | 45007.404 | 45008.4261 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287417 | AL, GA, MS, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 44999.6951 | 45007 | 45007.125 | 45007.0007 | 45007.0424 | 45007.4361 | 45007.4388 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45001.5221 | 45000.6929 | 45006.9871 | 45007.4388 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287519 | GA, Atlanta ICON Ring, 3 circuit to be removed per P&C requests | Medium | Successful | Moderate | Planned | RPY | TT | 44999.5909 | 45013.4375 | 45013.6875 | 45013.4792 | 45013.5458 | 45013.6379 | 45013.6403 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45009.3662 | 45000.6772 | 45013.4178 | 45340.9658 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287521 | GA, REIDSVILLE EBTS, REPLACE NPU MODULE ON ERICSSON MINILINK | Low | Successful | Minor | Planned | WKA | TT | 44999.5933 | 45007.3333 | 45007.7083 | 45007.5264 | 45007.7083 | 45008.4332 | 45008.4335 | 2023 | 2023-03 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45001.5086 | 45000.6678 | 45007.3205 | 45519.4801 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287522 | GA, REIDSVILLE EBTS, REPLACE NPU MODULE ON ERICSSON MINILINK (BACKUP DATE) | Low | Successful | Minor | Planned | WKA | TT | 44999.5935 | 45019.3333 | 45019.7083 | 45019.3764 | 45019.4514 | 45019.8441 | 45019.8445 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45012.5987 | 45012.5558 | 45019.3203 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000287627 | AL, Hoover, Patton Chapel EBTS, Hybrid replacement due to damaged hybrid. | Low | Successful | Minor | Planned | RBK | TT | 45000.0194 | 45008.3333 | 45008.7083 | 45008.3333 | 45008.7083 | 45009.3667 | 45009.367 | 2023 | 2023-03 | Successful | Facilities Component | Cables, jumpers, and connectors | Install | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45001.9132 | 45001.6677 | 45008.3211 | 45009.367 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287712 | AL, Wetumpka LTE site, Software upgrade and reboot | Low | Successful | Minor | Planned | DRI | TT | 45000.6089 | 45007.125 | 45007.1667 | 45007.125 | 45007.1583 | 45007.4355 | 45007.4356 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45001.5094 | 45000.7769 | 45007.1122 | 45007.4356 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000287802 | AL, Calera, GSC Complex Bldg. 10 Nokia NGTAN Circuit Cut | Medium | Successful | Moderate | Planned | GPB | TT | 45000.3889 | 45014.4167 | 45014.625 | 45014.4167 | 45014.4583 | 45018.9466 | 45019.8406 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45007.3637 | 45000.6761 | 45014.4039 | 45019.8406 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000287803 | AL, Eclectic, splicing dark fiber for Point Broadband handoff | Low | Successful | Minor | Planned | RCA | TT | 45000.3984 | 45012.2917 | 45023.75 | 45012.2917 | 45023.75 | 45026.3994 | 45026.3995 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45002.3764 | 45000.6733 | 45012.2787 | 45519.4588 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000287929 | GA, Atlanta, Northwest Sub, Re-route fiber cable to new section of transmission line | Medium | Successful | Moderate | Unplanned | JLM | TT | 45000.7939 | 45012.3333 | 45012.75 | 45012.3812 | 45012.6833 | 45013.4116 | 45013.4148 | 2023 | 2023-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45009.4427 | 45009.4366 | 45012.3205 | 45519.4679 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000288007 | GA, ATL and SAV ICON Ring, Move SWAN to DHA AND LFL path | Medium | Successful | Moderate | Planned | RPY | TT | 45001.6068 | 45043.375 | 45043.5417 | 45043.375 | 45043.5569 | 45043.5893 | 45043.5905 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45007.3626 | 45002.5297 | 45043.3621 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288016 | GA, Tallulah, Currahee Mtn, Athens & Augusta NOKIA circuit migration. (BACKUP DATE) | Medium | Successful | Moderate | Planned | TSE | TT | 45001.7778 | 45028.3333 | 45028.9583 | 45028.3333 | 45028.6076 | 45028.6604 | 45028.6609 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45007.3718 | 45002.6062 | 45028.3203 | 45341.1766 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288307 | AL, GA, MS, LTE router software updates & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45002.6862 | 45014 | 45014.0833 | 45014 | 45014.0639 | 45014.5244 | 45019.8405 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45006.3809 | 45005.6488 | 45013.9871 | 45019.8405 | 2023-Q1 | 2023-04 | 2023-Q2
CRQ000000288506 | GA, Atlanta ICON Ring, FIber t'shooting between Willingham Dr & Hartsfield Node 1 | Medium | Successful | Moderate | Planned | RPY | TT | 45002.4331 | 45013.3333 | 45013.75 | 45013.3333 | 45013.7188 | 45013.8854 | 45019.8404 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45007.592 | 45007.5745 | 45013.3205 | 45340.9658 | 2023-Q1 | 2023-04 | 2023-Q2
CRQ000000288648 | GA, IRWINTON, McINTYRE EBTS, REPLACE ANTENNA ASSEMBLY ON GORDON MINI-LINK MW | Low | Successful | Minor | Planned | WKA | TT | 45005.5378 | 45012.3333 | 45013.7083 | 45012.3333 | 45013.7083 | 45018.941 | 45018.9426 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45005.7423 | 45005.5802 | 45012.3205 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288654 | GA, Gees Mill Rd, LTE Upgrade existing MiniLink TN MW radio to Ericsson 6691 MW radio | Low | Successful | Minor | Planned | JTC | TT | 45005.6238 | 45021.3333 | 45021.7083 | 45021.3347 | 45021.7097 | 45021.7349 | 45021.7351 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45013.6516 | 45013.6496 | 45021.3177 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288809 | GA, Covington #2, LTE Upgrade existing MiniLink MW radio to Ericsson 6691 MW radio | Low | Successful | Minor | Planned | JTC | TT | 45005.5109 | 45020.3333 | 45020.7083 | 45020.3333 | 45020.7083 | 45021.4554 | 45021.4556 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45013.6516 | 45013.6433 | 45020.3205 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288817 | GA, Gees Mill Rd, LTE Upgrade existing MiniLink TN MW radio to Ericsson 6691 MW radio (BACKUP DATE) | Low | Successful | Minor | Planned | JTC | TT | 45005.6239 | 45029.3333 | 45029.7083 | 45029.3444 | 45029.6667 | 45030.461 | 45030.4611 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45023.4495 | 45023.4304 | 45029.3205 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288818 | GA, Conyers LTE, Upgrade existing MiniLink TN MW radio to Ericsson 6691 MW radio | Low | Successful | Minor | Planned | JTC | TT | 45005.6354 | 45022.3333 | 45022.7083 | 45022.3493 | 45022.5681 | 45022.5995 | 45022.5998 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45013.6572 | 45013.6536 | 45022.3205 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000288819 | GA, Conyers LTE, Upgrade existing MiniLink TN MW radio to Ericsson 6691 MW radio (BACKUP DATE) | Low | Successful | Minor | Planned | JTC | TT | 45005.6355 | 45029.3333 | 45029.7083 | 45029.3493 | 45029.641 | 45030.4604 | 45030.4605 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45023.4498 | 45023.4324 | 45029.3205 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289014 | GA, McIntyre, Senoia & NE Ivey LTE router software update & reboot | Low | Successful | Minor | Planned | DRI | TT | 45006.6401 | 45014 | 45014.0833 | 45014 | 45014.0639 | 45014.5253 | 45018.9433 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45007.5198 | 45006.6874 | 45013.9871 | 45018.9433 | 2023-Q1 | 2023-04 | 2023-Q2
CRQ000000289017 | GA, Surrency, Tarrytown, Gordon & Flovilla, adding 60 & 30 amps to racks | Low | Successful | Minor | Planned | SDG | TT | 45006.6488 | 45015.875 | 45016.25 | 45015.875 | 45016.25 | 45018.9595 | 45018.963 | 2023 | 2023-04 | Successful | Facilities Component | Cabinet / Rack | Install | Transport | SDG | SCS | OPERATIONS | STI | 45014.5949 | 45014.5046 | 45015.8622 | 45018.963 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289018 | GA, Surrency, Tarrytown, Gordon & Flovilla, adding 60 & 30 amps to racks (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45006.6489 | 45022.875 | 45023.25 | 45022.875 | 45023.25 | 45023.4351 | 45023.4352 | 2023 | 2023-04 | Successful | Facilities Component | Cabinet / Rack | Install | Transport | SDG | SCS | OPERATIONS | STI | 45014.613 | 45014.5076 | 45022.8622 | 45023.4352 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289101 | AL, Trussville, Splicing dark fiber for CSpire | Low | Successful | Minor | Planned | JFE | TT | 45006.4613 | 45013.3333 | 45014.7917 | 45013.3333 | 45014.7917 | 45018.95 | 45018.951 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JFE | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45007.6976 | 45006.5429 | 45013.3205 | 45519.4588 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289102 | AL, Jasper, Transport Hut, Splicing fibers for CSpire | Low | Successful | Minor | Planned | JFE | TT | 45006.4714 | 45015.3333 | 45015.7917 | 45015.3333 | 45015.7917 | 45018.9549 | 45018.9627 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JFE | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45007.6976 | 45006.5437 | 45015.3204 | 45519.4588 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289307 | Advisory/Oper Event: GA - APPLING - WEST AUGUSTA - FIBER RELOCATION - NCC-14219 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45007.4426 | 45009 | 45009.2083 | 45009.0056 | 45009.2486 | 45009.3454 | 45009.3455 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45007.4467 | 45007.4467 | 45008.9864 | 45009.3455 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000289518 | GA, MACON AREA, Scope/Clean Fibers between MACN WDM002 and JCSN WDM001 | Medium | Successful | Moderate | Planned | DRB | TT | 45008.7419 | 45015.75 | 45015.9167 | 45015.75 | 45015.9167 | 45016.6816 | 45019.8419 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.4271 | 45013.6611 | 45015.7371 | 45019.8419 | 2023-Q1 | 2023-04 | 2023-Q2
CRQ000000289520 | MS, Laurel Area, Migrate Ellisville/Hattiesburg/Laurel Substations to NGTAN | Medium | Successful | Moderate | Planned | DRB | TT | 45008.7611 | 45021.4167 | 45021.75 | 45021.4167 | 45021.6979 | 45022.4906 | 45022.4913 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.4198 | 45013.6676 | 45021.4011 | 45022.4913 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289611 | AL, Birmingham APC HQ, Installing a new DC power connection. | Low | Successful | Minor | Planned | SDG | TT | 45008.4405 | 45013.8542 | 45014.25 | 45013.8542 | 45014.1042 | 45018.9448 | 45018.9453 | 2023 | 2023-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45009.4975 | 45009.372 | 45013.8343 | 45018.9453 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289626 | MS, Meridian Area, Relocate Meridian SC-MRDN NE Sub Fiber Cable | Low | Successful | Minor | Planned | DRB | TT | 45008.6957 | 45027.3333 | 45027.8333 | 45027.3451 | 45027.6361 | 45027.7291 | 45027.7293 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.4039 | 45014.6719 | 45027.3204 | 45027.7293 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289629 | MS, Long Beach, Splice Long Beach Tower drop cable into 144-Fiber Underground Route | Low | Successful | Minor | Planned | DRB | TT | 45008.7225 | 45020.3333 | 45020.8333 | 45020.3354 | 45020.7667 | 45021.461 | 45021.4612 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.4107 | 45013.6641 | 45020.3205 | 45021.4612 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000289631 | MS, Meridian, Replace SFPs between MRDN SC SAR001 1/4/8 and SAR002 1/3/8 | Low | Successful | Minor | Unplanned | DRB | TT | 45008.7295 | 45015.375 | 45015.75 | 45015.375 | 45015.75 | 45016.7192 | 45016.7199 | 2023 | 2023-03 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.4116 | 45012.5607 | 45015.4177 | 45016.7199 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000290607 | AL, GA, MS, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45012.6871 | 45021 | 45021.0833 | 45021 | 45021.0431 | 45021.5053 | 45021.5299 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45013.7086 | 45013.6702 | 45020.9842 | 45021.5299 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000290611 | AL, various site, LTE router software upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45012.7773 | 45021.0833 | 45021.125 | 45021.0833 | 45021.1181 | 45021.457 | 45021.4605 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45013.7086 | 45013.6714 | 45021.0676 | 45021.4605 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000291011 | Advisory/Oper Event: AL - TUSCALOOSA - EMERGENCY MAINTENANCE - NCC-14335 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45013.464 | 45013.9583 | 45014.2083 | 45013.9583 | 45014.0146 | 45014.3571 | 45014.3573 | 2023 | 2023-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45013.5266 | 45013.5265 | 45013.9454 | 45014.3573 | 2023-Q1 | 2023-03 | 2023-Q1
CRQ000000291118 | Advisory/Oper Event: GA, Multi Sites - Fiber Audit - NCC-14218 - PRIMARY | Low | Successful | Std/PreApp | Planned | HHA | HH | 45014.5866 | 45019.9583 | 45020.2083 | 45019.9583 | 45020.2799 | 45020.3123 | 45020.3125 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45014.5935 | 45014.593 | 45019.9454 | 45020.3125 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000291213 | Advisory/Oper Event: GA, Multi Sites - Fiber Audit - NCC-14218 - SECONDARY | Low | Successful | Std/PreApp | Planned | HHA | HH | 45014.5898 | 45020.9583 | 45021.2083 | 45020.9583 | 45021.2083 | 45021.4627 | 45021.4628 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45014.5935 | 45014.5928 | 45020.9425 | 45021.4628 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000291603 | Advisory/Oper Event: AL - GULF SHORES - FIBER RELOCATION - NCC-14233 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45015.4293 | 45019.9583 | 45020.25 | 45019.9583 | 45020.25 | 45020.4045 | 45020.4047 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.443 | 45015.4429 | 45019.9454 | 45020.4047 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000291605 | Advisory/Oper Event: AL - GULF SHORES - FIBER RELOCATION - NCC-14233 (Secondary) | Low | Successful | Minor | Planned | HHA | HH | 45015.4306 | 45020.9583 | 45021.25 | 45020.9583 | 45021.25 | 45021.4621 | 45021.4623 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.5997 | 45015.4428 | 45020.9425 | 45021.4623 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000291606 | Advisory/Oper Event: AL - GULF SHORES - FIBER RELOCATION - NCC-14233 (Tertiary) | Low | Successful | Minor | Planned | HHA | HH | 45015.4318 | 45021.9583 | 45022.25 | 45021.9583 | 45022.3229 | 45022.3758 | 45022.3759 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45015.5997 | 45015.4422 | 45021.9453 | 45022.3759 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000292706 | GA, Athens transport hub, test the generator with load | Low | Successful | Minor | Planned | PCM | TT | 45019.5038 | 45034.375 | 45034.5833 | 45034.3799 | 45034.4625 | 45034.5965 | 45034.5966 | 2023 | 2023-04 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | PCM | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45021.8317 | 45021.5322 | 45034.3628 | 45519.4801 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000292719 | GA, Waynesboro, Vogtle 500kv Sub, NOKIA circuit migrate & SWAN Hub consolidate. | Medium | Successful | Moderate | Planned | TSE | TT | 45019.7007 | 45036.3333 | 45036.8333 | 45036.3479 | 45036.5826 | 45036.5954 | 45036.5968 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45023.5437 | 45021.5837 | 45036.3205 | 45341.1766 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000292721 | AL, East Alabama, Migrate Fibers Between North Auburn and Goat Rock | Low | Successful | Minor | Planned | DRB | TT | 45019.745 | 45034.75 | 45034.9167 | 45034.75 | 45034.8181 | 45034.9571 | 45034.9577 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.6102 | 45028.657 | 45034.737 | 45034.9576 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000292904 | Advisory/Oper Event: AL - FLOMATON - EMERGENCY MAINTENANCE NCC-14362 (PRIMARY) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45020.377 | 45027.0417 | 45027.25 | 45027.0257 | 45027.2951 | 45027.3307 | 45027.3308 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45020.3877 | 45020.3877 | 45027.0287 | 45027.3308 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293001 | Advisory/Oper Event: AL - FLOMATON - EMERGENCY MAINTENANCE NCC-14362 (SECONDARY) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45020.3794 | 45028.0417 | 45028.25 | 45028.0417 | 45028.25 | 45028.4003 | 45028.4005 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45020.3873 | 45020.3873 | 45028.028 | 45028.4005 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293002 | Event: AL - FLOMATON - EMERGENCY MAINTENANCE NCC-14362 (TERTIARY) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45020.3821 | 45029.0417 | 45029.25 | 45029.0417 | 45029.1083 | 45029.3138 | 45029.314 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45020.387 | 45020.387 | 45029.0288 | 45029.314 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293008 | AL, Parrish, Cut New Fayette OPGW route into Goodsprings TS at Str 10 | Low | Successful | Minor | Planned | RRR | TT | 45020.4249 | 45028.7917 | 45028.9583 | 45028.8007 | 45028.916 | 45029.5369 | 45029.537 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45023.5381 | 45021.5337 | 45028.7787 | 45519.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293014 | GA, AUGUSTA, TRANSPORT BLDG, REPLACE ATS | Low | Successful | Minor | Planned | MVW | TT | 45020.4708 | 45029.3333 | 45029.7083 | 45029.3583 | 45029.5076 | 45030.4617 | 45030.4618 | 2023 | 2023-04 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45021.8305 | 45021.5286 | 45029.3205 | 45498.7092 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293016 | AL, Gadsden, drop fibers out of Gadsden to Weiss route to new OPGW built to Keener DS | Low | Successful | Minor | Planned | RRR | TT | 45020.5153 | 45029.7917 | 45029.9583 | 45029.7917 | 45029.9583 | 45030.4652 | 45030.4653 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45023.537 | 45021.5135 | 45029.7787 | 45519.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293017 | AL, Gadsden, drop fibers out of Gadsden to Weiss route to new OPGW built to Keener DS (BACKUP DATE) | Low | Successful | Minor | Planned | RRR | TT | 45020.5154 | 45033.7917 | 45033.9583 | 45033.7917 | 45033.9583 | 45034.4006 | 45034.4008 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45023.537 | 45021.5142 | 45033.7793 | 45519.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293028 | AL & GA, LTE Cell site router software upgrades & reboots | Medium | Unsuccessful | Moderate | Planned | DRI | TT | 45020.7833 | 45028 | 45028.0833 | 45028 | 45028.0104 | 45028.3947 | 45028.3958 | 2023 | 2023-04 | Unsuccessful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45022.3685 | 45021.5783 | 45027.9863 | 45028.3958 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293029 | AL, Irondale, AT&T Circuit Migration | Low | Successful | Minor | Planned | DRI | TT | 45020.7972 | 45030.375 | 45030.5417 | 45030.375 | 45030.4938 | 45030.5993 | 45030.5995 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45021.8331 | 45021.5793 | 45030.3622 | 45030.5995 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293108 | AL, BIRMINGHAM, OAK MTN TRANSPORT BLDG, REPLACE DC RECTIFIER/BATTERIES | Low | Successful | Minor | Planned | MVW | TT | 45020.4881 | 45033.375 | 45037.625 | 45033.375 | 45037.625 | 45041.4013 | 45041.4015 | 2023 | 2023-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45021.8339 | 45021.5311 | 45033.362 | 45498.7092 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293312 | AL, Jasper, Splicing dark fiber for CSpire handoff | Low | Successful | Minor | Planned | RCA | TT | 45021.5894 | 45028.3333 | 45028.7917 | 45028.3333 | 45028.7917 | 45029.5323 | 45029.5342 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45023.5366 | 45022.5518 | 45028.3203 | 45519.4588 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293320 | GA, Atlanta, Northwest Substation, Roll ICON fibers to alternate cable | Medium | Successful | Moderate | Planned | JLM | TT | 45021.7975 | 45034.3333 | 45034.75 | 45034.3431 | 45034.3576 | 45034.4969 | 45034.5012 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45023.4547 | 45023.4372 | 45034.3211 | 45519.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293322 | GA, Atlanta, Northwest Sub, Move OPGW cable for substation rebuild | Medium | Successful | Moderate | Planned | JLM | TT | 45021.923 | 45045.3333 | 45045.75 | 45045.3333 | 45045.8417 | 45046.9294 | 45046.9332 | 2023 | 2023-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45023.4554 | 45023.4407 | 45045.3205 | 45519.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293525 | GA, Chamblee LTE site, AT&T circuit migration | Low | Successful | Minor | Planned | DRI | TT | 45022.5403 | 45037.5417 | 45037.7083 | 45037.5417 | 45037.7083 | 45041.4041 | 45041.4044 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45033.4083 | 45030.6005 | 45037.5285 | 45041.4044 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293700 | Advisory/Oper Event: AL - GULF SHORES - FIBER RELOCATION - NCC-14233 (Backup) | Low | Successful | Minor | Planned | HHA | HH | 45022.3685 | 45022.9583 | 45023.25 | 45022.9583 | 45023.25 | 45023.4356 | 45023.4357 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45022.4894 | 45022.375 | 45022.9456 | 45023.4357 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000293810 | AL, Uniontown EBTS A9229, foundation and tower modifications | Low | Successful | Minor | Planned | CDL | TT | 45023.532 | 45033.375 | 45058.5257 | 45033.375 | 45058.5257 | 45061.4026 | 45061.4027 | 2023 | 2023-05 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45027.4931 | 45027.4848 | 45033.362 | 45061.4027 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000293909 | AL, Ozark Local Office, replace Adtran Tracer MW Radio due to bad fans | Low | Successful | Minor | Planned | JEN | TT | 45023.5488 | 45029.7708 | 45029.875 | 45029.7708 | 45029.7833 | 45030.4639 | 45030.4642 | 2023 | 2023-04 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Repair | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45026.7009 | 45026.6938 | 45029.7509 | 45519.4508 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294208 | AL, GA, MS, FL, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45026.5805 | 45042.0833 | 45042.125 | 45042.0833 | 45042.125 | 45042.3825 | 45042.3838 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45033.4126 | 45030.6157 | 45042.0705 | 45042.3838 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294209 | AL, GA, MS, FL, LTE Cell site router software upgrades & reboots (BACKUP DATE) | Medium | Successful | Moderate | Planned | DRI | TT | 45026.5806 | 45049.0833 | 45049.125 | 45049.0833 | 45049.125 | 45049.3951 | 45049.3957 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45033.4141 | 45030.6169 | 45049.0705 | 45049.3957 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000294412 | GA, N. GA ICON Ring, set up new DHA & LFL SWAN circuit | Medium | Successful | Moderate | Planned | RPY | TT | 45026.4842 | 45047.375 | 45047.75 | 45047.416 | 45047.4389 | 45047.7148 | 45047.7165 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45033.8973 | 45030.6238 | 45047.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000294415 | MS, Gulfport/Region 4, Remove Hattiesburg OC12 DWDM X-Connects | Medium | Successful | Moderate | Planned | DRB | TT | 45026.4922 | 45033.5417 | 45033.75 | 45033.5417 | 45033.75 | 45034.3987 | 45034.4 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.4056 | 45027.5163 | 45033.5292 | 45034.4 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294424 | AL, Various Turn down Adtran OPTI6100 Ring 3 West | Medium | Successful | Moderate | Planned | GPB | TT | 45026.6444 | 45036.4167 | 45036.6667 | 45036.4167 | 45036.5917 | 45037.4606 | 45037.4625 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.8966 | 45027.5119 | 45036.4039 | 45037.4625 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294501 | Advisory/Oper Event: GA - ATLANTA - EMERGENCY MAINTENANCE - NCC-14400 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45027.3669 | 45029.9583 | 45030.2083 | 45029.9326 | 45030.0417 | 45030.3317 | 45030.3319 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45027.3719 | 45027.3719 | 45029.9454 | 45030.3319 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294720 | AL, Greene County ICON Ring, Insert SFP at Bassett Creek port B | Medium | Successful | Moderate | Planned | RPY | TT | 45027.6645 | 45040.375 | 45040.7083 | 45040.375 | 45040.5833 | 45040.6133 | 45041.4077 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45033.8954 | 45029.5522 | 45040.3621 | 45340.9658 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294722 | AL, Greene County ICON Ring, Insert SFP at Greene County MW A | Medium | Successful | Moderate | Planned | RPY | TT | 45027.6649 | 45048.375 | 45048.7083 | 45048.375 | 45048.7083 | 45049.0354 | 45049.0377 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45033.8947 | 45030.6291 | 45048.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000294911 | AL, GA, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45028.4744 | 45036 | 45036.0833 | 45036.0062 | 45036.0528 | 45036.4657 | 45036.4679 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45029.5957 | 45029.5492 | 45035.9871 | 45036.4679 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294923 | GA, Soperton ENODEB, DC Plant Modification | Low | Successful | Minor | Planned | LPE | TT | 45028.5495 | 45043.3958 | 45043.9375 | 45043.3958 | 45043.4181 | 45044.4723 | 45044.4725 | 2023 | 2023-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45033.4124 | 45032.962 | 45043.376 | 45044.4725 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000294933 | MS, PASCAGOULA, PASCAGOULA Loop substations - CGR Conversions to Ethernet | Medium | Successful | Moderate | Planned | DRB | TT | 45028.7609 | 45041.375 | 45041.75 | 45041.3806 | 45041.7076 | 45042.3806 | 45042.3835 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.7056 | 45032.9595 | 45041.362 | 45042.3835 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295010 | GA, Augusta, South Augusta ENODEB, Emergency Hybrid Replacement | Low | Successful | Minor | Planned | LPE | TT | 45028.4901 | 45034.375 | 45034.7083 | 45034.375 | 45034.7083 | 45035.4041 | 45035.4042 | 2023 | 2023-04 | Successful | Facilities Component | Cables, jumpers, and connectors | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45029.5862 | 45029.5456 | 45034.3629 | 45035.4042 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295113 | GA, ATL ICON Ring, Provision alt PLM/SFP Epipe for correct circuit flow | Low | Successful | Minor | Planned | RPY | TT | 45029.5686 | 45048.375 | 45048.7083 | 45048.4222 | 45048.5243 | 45048.5759 | 45048.5761 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45033.5853 | 45032.9642 | 45048.3622 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000295312 | GA, ATL ICON ring, System error log clean up - cross connect issue | Medium | Successful | Moderate | Planned | RPY | TT | 45029.5007 | 45055.375 | 45055.7083 | 45055.5771 | 45055.616 | 45061.4044 | 45061.4063 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45033.8935 | 45032.9683 | 45055.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000295317 | AL, Birmingham, ACP HQ, Linc LTE Core, Emergency Power Maintenance on Vertiv UPS | Medium | Successful | Moderate | Unplanned | MJR | TT | 45029.5276 | 45033 | 45033.25 | 45033 | 45033.25 | 45033.6885 | 45034.3999 | 2023 | 2023-04 | Successful | Facilities Component | DC Backup System | Repair | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45029.5962 | 45029.5439 | 45032.9869 | 45034.3999 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295512 | MS, Moss Point Area, Insert New Moss Point IFN/Hub SAR into NGTAN Network | Medium | Successful | Moderate | Planned | DRB | TT | 45030.4411 | 45036.4167 | 45036.5833 | 45036.5174 | 45036.8215 | 45037.454 | 45037.4555 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.7073 | 45030.6185 | 45036.4039 | 45037.4555 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295516 | GA, MACON, 930 KEY ST DDC, ADDITION OF 2ND DC BATTERY STRING | Low | Successful | Minor | Planned | KNL | TT | 45030.479 | 45049.2917 | 45051.7083 | 45049.2917 | 45051.7083 | 45054.4004 | 45054.4007 | 2023 | 2023-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45033.4127 | 45032.9669 | 45049.2788 | 45498.7092 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000295530 | AL, Ohatchee Neely Henry Dam Upgrade Nokia SAR Software | Low | Successful | Minor | Planned | GPB | TT | 45030.6536 | 45040.4375 | 45040.5208 | 45040.4375 | 45040.5208 | 45041.4059 | 45041.4061 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.5871 | 45032.9543 | 45040.4177 | 45041.4061 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295531 | AL, Birmingham, APC HQ, Linc LTE Data Center Core, Emergency Power Maintenance | Medium | Successful | Moderate | Planned | MJR | TT | 45030.662 | 45037 | 45037.75 | 45037 | 45037.75 | 45041.4022 | 45041.4074 | 2023 | 2023-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Migrate | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45033.4172 | 45032.9446 | 45036.9879 | 45041.4074 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295532 | AL, FL, All Alabama and Florida LTE Sites, LTE Software Upgrades | Medium | Successful | Moderate | Planned | LHA | TT | 45030.6725 | 45039.9583 | 45040.2083 | 45039.9583 | 45040.2083 | 45041.4048 | 45041.4075 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JLH | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45037.3158 | 45035.4985 | 45039.9452 | 45041.4075 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295533 | AL, FL, All Alabama and Florida LTE Sites, LTE Software Upgrades (BACKUP DATE) | Medium | Successful | Moderate | Planned | LHA | TT | 45030.6726 | 45047.9583 | 45048.2083 | 45047.9583 | 45048.2083 | 45048.5748 | 45048.5778 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JLH | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45037.3263 | 45035.4994 | 45047.9454 | 45048.5778 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000295534 | AL, Anniston Transport, Upgrade Nokia SAR Software on ANTNALX01SAR004 | Medium | Successful | Moderate | Planned | GPB | TT | 45030.6794 | 45040.75 | 45040.8333 | 45040.7597 | 45040.7896 | 45041.4065 | 45041.4078 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45036.5294 | 45034.6005 | 45040.7363 | 45041.4078 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295537 | GA, All Georgia LTE Sites, LTE Software Upgrades | Medium | Successful | Moderate | Planned | LHA | TT | 45030.7012 | 45042.9583 | 45043.2083 | 45042.9583 | 45043.2083 | 45043.4478 | 45043.4508 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JLH | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45037.3274 | 45035.8295 | 45042.9454 | 45043.4508 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295539 | MS, All Mississippi LTE Sites, LTE Software Upgrades | Medium | Successful | Moderate | Planned | LHA | TT | 45030.7078 | 45041.9583 | 45042.2083 | 45041.9583 | 45042.2083 | 45042.3852 | 45042.3863 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JLH | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45037.3271 | 45035.5039 | 45041.9455 | 45042.3863 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000295607 | MS, Meridian Area, Convert MRDN-Laurel Hub & MRDN-Newton WAN Circuits to Ethernet | Low | Successful | Minor | Planned | DRB | TT | 45030.4756 | 45037.3333 | 45037.75 | 45037.3333 | 45037.5014 | 45037.5627 | 45037.5628 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.589 | 45032.9461 | 45037.3213 | 45037.5628 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000296101 | Advisory/Oper Event: AL - HUNTSVILLE - EMERGENCY MAINTENANCE - NCC-14412 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45033.3259 | 45036.0417 | 45036.25 | 45036.0938 | 45036.1889 | 45036.346 | 45036.3461 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45033.3285 | 45033.3284 | 45036.0288 | 45036.3461 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000296115 | AL, LTE router software upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45033.5166 | 45042 | 45042.0833 | 45042 | 45042.0507 | 45042.3817 | 45042.3837 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45037.3258 | 45035.5169 | 45041.9871 | 45042.3837 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000296207 | AL, Alex City, Dadeville, and Roanoke NGTAN Circuit Cut. | Low | Successful | Minor | Planned | GPB | TT | 45033.4906 | 45042.4167 | 45042.6667 | 45042.4167 | 45042.5264 | 45043.4428 | 45043.4431 | 2023 | 2023-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45036.4883 | 45035.4876 | 45042.4039 | 45043.4431 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000296325 | GA, Fairburn, Transmission ROW, Splice new section of cable | Low | Successful | Minor | Planned | JLM | TT | 45033.7648 | 45049.7708 | 45050.0833 | 45049.7708 | 45049.9313 | 45050.4811 | 45050.4812 | 2023 | 2023-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45036.4777 | 45035.5627 | 45049.7508 | 45519.4679 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000296520 | GA, Plant Scherer Transport, Add Optical Pad to Ciena Module. | Low | Successful | Minor | Planned | GPB | TT | 45034.6125 | 45042.7083 | 45042.875 | 45042.7104 | 45042.7229 | 45043.4454 | 45043.4456 | 2023 | 2023-04 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45036.4893 | 45035.5582 | 45042.6953 | 45043.4456 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000297112 | GA, Cumming, Sawnee Mtn Transport, Replace DC breakers and wire for Datel fuse panel | Low | Successful | Minor | Planned | JMN | TT | 45036.6231 | 45050.375 | 45050.75 | 45050.375 | 45050.5667 | 45051.489 | 45051.4891 | 2023 | 2023-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45041.564 | 45041.47 | 45050.3621 | 45519.4736 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000297113 | AL, Dadeville, Point Broadband Handoff, splicing fibers | Low | Successful | Minor | Planned | RCA | TT | 45036.7 | 45047.3333 | 45049.7917 | 45047.3896 | 45048.7229 | 45049.4517 | 45049.4518 | 2023 | 2023-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45041.6618 | 45041.4659 | 45047.3204 | 45519.4588 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000297314 | AL, Clanton, Lay Dam Hydro, Power Work | Low | Successful | Minor | Planned | MSM | TT | 45037.529 | 45045.2917 | 45045.7917 | 45045.3222 | 45045.8 | 45046.9285 | 45046.9286 | 2023 | 2023-04 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45037.5773 | 45037.5666 | 45045.2788 | 45519.4508 | 2023-Q2 | 2023-04 | 2023-Q2
CRQ000000298016 | GA, Savannah ICON Ring, SFP insertion | Medium | Successful | Moderate | Planned | RPY | TT | 45040.6983 | 45055.375 | 45055.6667 | 45055.4187 | 45055.5229 | 45061.4036 | 45061.4062 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45041.6675 | 45041.4829 | 45055.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000298308 | GA, Savannah ICON Ring, Turn ports up for SWAN to DHA & LFL | Medium | Successful | Moderate | Planned | RPY | TT | 45041.48 | 45071.375 | 45071.7083 | 45071.375 | 45071.7083 | 45075.6486 | 45075.6544 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45049.4683 | 45043.481 | 45071.3629 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000298401 | GA, Douglas, West Douglas ENODEB, TS Low Fiber Light Levels on Sector 1 | Low | Successful | Minor | Planned | LPE | TT | 45041.3618 | 45050.5417 | 45050.7083 | 45050.5417 | 45050.7083 | 45051.4907 | 45051.4908 | 2023 | 2023-05 | Successful | Facilities Component | Patch panel/Fiber distribution panel | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45041.5627 | 45041.4315 | 45050.5292 | 45051.4908 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000298403 | GA, Austell OH MW, Stacks Rd MW, Forest Park MW, 6GHz to 11GHz MW radio upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45041.3861 | 45054.375 | 45056.75 | 45054.375 | 45055.2083 | 45055.4621 | 45061.3922 | 2023 | 2023-05 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45041.5947 | 45041.4805 | 45054.3621 | 45519.4736 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000298604 | AL, Birmingham APC HQ, Turn down Adtran OPTI ring at APC HQ. | Medium | Successful | Moderate | Planned | GPB | TT | 45042.3867 | 45055.4167 | 45055.6667 | 45055.4167 | 45055.6667 | 45061.4072 | 45061.4077 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45049.4525 | 45043.4648 | 45055.4038 | 45061.4077 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000298901 | GA, Cartersville, Plt Bowen 500, NOKIA NGTAN circuit & SWAN Hub migration on Nokia. | Medium | Successful | Moderate | Planned | TSE | TT | 45043.3685 | 45057.3333 | 45057.75 | 45057.3333 | 45057.4583 | 45057.5233 | 45061.4064 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45049.453 | 45043.4796 | 45057.3219 | 45341.1766 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299001 | AL, Fayette Transport, NGTAN Circuit Cutover. | Low | Successful | Minor | Planned | GPB | TT | 45043.3968 | 45056.4167 | 45056.8333 | 45056.4167 | 45056.8333 | 45057.5246 | 45057.5247 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45049.4481 | 45043.4697 | 45056.4038 | 45057.5247 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299002 | AL, Fayette Transport NGTAN Circuit Cutover. (BACKUP DATE) | Low | Successful | Minor | Planned | GPB | TT | 45043.3969 | 45063.4167 | 45063.8333 | 45063.4167 | 45063.8333 | 45063.9498 | 45063.9499 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45049.4485 | 45043.4713 | 45063.4038 | 45063.9499 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299020 | MS, Meridian Area, Insert Meridian SC SAR nodes into NGTAN Region 4 | Low | Successful | Minor | Planned | DRB | TT | 45043.6235 | 45050.375 | 45050.7083 | 45050.3931 | 45050.7063 | 45051.4864 | 45051.4866 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45049.4506 | 45049.4499 | 45050.3621 | 45051.4866 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299114 | GA, North Shallowford LTE, AT&T Circuit migration | Low | Successful | Minor | Planned | DRI | TT | 45044.6621 | 45054.5 | 45054.6667 | 45054.5 | 45054.6667 | 45055.4743 | 45055.4744 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45048.6264 | 45048.6112 | 45054.4873 | 45055.4744 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299115 | GA, Chastain Park LTE, Circuit Migration | Low | Successful | Minor | Planned | DRI | TT | 45044.6671 | 45054.3333 | 45054.5 | 45054.3333 | 45054.5 | 45055.4596 | 45055.4597 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45048.6279 | 45048.609 | 45054.3204 | 45055.4597 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299124 | GA, Cobb Co Hwy 5, ASEoD Circuit Migration | Low | Successful | Minor | Planned | DRI | TT | 45044.7498 | 45055.3333 | 45055.5 | 45055.3333 | 45055.4583 | 45055.4711 | 45055.4712 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45048.6261 | 45048.6127 | 45055.3204 | 45055.4712 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299210 | AL, Birmingham, BHAM ICON Ring, SYS Error Log clear, UCAD tx'd/rcv'd twice | Medium | Successful | Moderate | Planned | RPY | TT | 45044.473 | 45061.375 | 45061.6667 | 45061.6562 | 45061.6854 | 45061.8039 | 45061.8058 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5327 | 45048.6359 | 45061.362 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299303 | GA, Old National Transport, Replacing LIM 2-2 AMP card toward Virginia Avenue. | Low | Successful | Minor | Planned | ADL | TT | 45044.5179 | 45055.75 | 45055.9583 | 45055.7556 | 45055.7937 | 45061.4098 | 45061.4101 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45049.4588 | 45048.6339 | 45055.737 | 45061.41 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299309 | GA, ALBANY, PLANT MITCHELL, MOVE SAR VPLS FIBER LINK TO NORTH TIFTON | Medium | Successful | Moderate | Planned | WKA | TT | 45044.605 | 45062.4167 | 45062.5 | 45062.4167 | 45062.4514 | 45062.4531 | 45062.4624 | 2023 | 2023-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45051.5352 | 45050.6545 | 45062.4052 | 45519.4801 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299608 | GA, SAV ICON Ring, Priority on protection circuit needs to be swapped, System error | Medium | Successful | Moderate | Planned | RPY | TT | 45047.5945 | 45068.375 | 45068.7083 | 45068.5146 | 45068.5243 | 45068.5264 | 45068.5276 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45049.4688 | 45048.697 | 45068.362 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299609 | AL, Green County ICON Ring, Priority on protection circuit needs to be swapped, system error | Medium | Successful | Moderate | Planned | RPY | TT | 45047.5946 | 45069.375 | 45069.7083 | 45069.375 | 45069.5625 | 45069.5949 | 45069.5977 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5334 | 45050.6477 | 45069.3628 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299716 | GA, N. GA ICON Ring, set up new DHA & LFL SWAN circuit | Medium | Successful | Moderate | Planned | RPY | TT | 45047.5748 | 45063.375 | 45063.7083 | 45063.375 | 45063.5208 | 45063.5308 | 45063.5373 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5338 | 45048.7122 | 45063.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299728 | AL, GA, MS, LTE Cell site router software upgrades & reboots | Low | Successful | Minor | Planned | DRI | TT | 45047.7604 | 45063 | 45063.0833 | 45063 | 45063.2465 | 45063.5345 | 45063.5347 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45048.6257 | 45048.6232 | 45062.987 | 45063.5347 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299812 | GA, CARROLLTON SUB TRANSPORT, LIFECYCLE REPLACEMENT OF GENERATOR, ATS, MTS | Low | Successful | Minor | Planned | KNL | TT | 45047.4713 | 45061.2917 | 45065.7083 | 45061.2917 | 45061.7917 | 45062.4525 | 45062.4526 | 2023 | 2023-05 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45049.3953 | 45048.6929 | 45061.2786 | 45498.7092 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000299818 | GA, SAV Ring, Circuit needs to be reprovisioned, System Error | Medium | Successful | Moderate | Planned | RPY | TT | 45047.5688 | 45061.375 | 45061.7083 | 45061.4326 | 45061.4757 | 45061.5679 | 45061.5696 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5341 | 45048.6942 | 45061.362 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300212 | GA, ATL ICON Ring, EBAM ports wrongfully assigned. Need to be removed, clearing system error | Medium | Successful | Moderate | Planned | RPY | TT | 45049.498 | 45062.375 | 45062.6667 | 45062.4785 | 45062.5062 | 45063.5317 | 45063.5368 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5345 | 45050.6405 | 45062.3635 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300217 | GA, ATL ICON Ring, Buckhead & Lindbergh, System Error. Circuit needs to be reprovisioned. | Medium | Unsuccessful | Moderate | Planned | RPY | TT | 45049.5489 | 45069.375 | 45069.7083 | 45069.375 | 45069.4167 | 45069.5958 | 45069.5976 | 2023 | 2023-05 | Unsuccessful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.535 | 45050.643 | 45069.3628 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300218 | GA, ATL ICON Ring, System Error. Circuit needs to be reprovisioned Buckhead & Lindbergh BACKUP DATE | Medium | Successful | Moderate | Planned | RPY | TT | 45049.549 | 45070.375 | 45070.7083 | 45070.4569 | 45070.6667 | 45071.4971 | 45071.4983 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5356 | 45050.6435 | 45070.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300219 | GA, SAV ICON Ring, System Error, Clear VT terminated to unused Dpipe | Medium | Successful | Moderate | Planned | RPY | TT | 45049.5622 | 45082.375 | 45082.6667 | 45082.4278 | 45082.5729 | 45082.5903 | 45082.5923 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.536 | 45050.6487 | 45082.362 | 45340.9658 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000300224 | GA, ATL and SAV ICON Ring, Nodes need to be upgraded for server module | Medium | Successful | Moderate | Planned | RPY | TT | 45049.6021 | 45063.375 | 45063.7215 | 45063.5132 | 45063.5208 | 45063.5298 | 45063.5372 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45051.5366 | 45050.4927 | 45063.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300228 | AL, Roanoke Area, Migrate Roanoke and Dadeville Traffic to NGTAN | Medium | Successful | Moderate | Planned | DRB | TT | 45049.6789 | 45062.7083 | 45062.9167 | 45062.7465 | 45062.9618 | 45063.5354 | 45063.5371 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45051.6783 | 45050.4903 | 45062.6953 | 45063.5371 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300303 | GA, Austell and Forest Park Transport NOKIA NEXT GEN circuit migration. | Medium | Successful | Moderate | Planned | TSE | TT | 45049.479 | 45064.625 | 45064.875 | 45064.625 | 45064.875 | 45065.5869 | 45068.4048 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45051.5369 | 45050.4953 | 45064.614 | 45341.1766 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300406 | MS, Meridian Area, Move MRDN-LAUD E. 1G link & Turn Up New MRDN DO-SC 10G | Low | Successful | Minor | Planned | DRB | TT | 45049.5072 | 45055.375 | 45055.75 | 45055.375 | 45055.4167 | 45055.4721 | 45055.473 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45051.663 | 45050.4835 | 45055.3621 | 45055.473 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300512 | AL, Demopolis Local Office, moving ONTs from utility power to a UPS | Low | Successful | Minor | Planned | JGL | TT | 45050.474 | 45061.75 | 45061.8333 | 45061.7542 | 45061.7854 | 45061.8063 | 45061.8064 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45050.736 | 45050.4864 | 45061.7384 | 45061.8064 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300602 | AL, Mobile, NUG, Splicing splitters and drops for service to ONT's. | Low | Successful | Minor | Planned | RCA | TT | 45050.4057 | 45061.3333 | 45064.8333 | 45061.3333 | 45064 | 45065.5896 | 45068.4051 | 2023 | 2023-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45051.5162 | 45050.4852 | 45061.3203 | 45519.4588 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300608 | Advisory/Oper Event: GA - ATLANTA - FIBER AUDIT - NCC-14644 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45050.5817 | 45068.9583 | 45069.2083 | 45068.9583 | 45069.2083 | 45069.4016 | 45069.4018 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45050.5943 | 45050.5942 | 45068.946 | 45069.4018 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300709 | Advisory/Oper Event: GA - ATLANTA - FIBER AUDIT - NCC-14644 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45050.5767 | 45057.9583 | 45058.2083 | 45058 | 45058.1694 | 45058.3555 | 45058.3556 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45050.5944 | 45050.5944 | 45057.9455 | 45058.3556 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000300814 | AL, Haleyville Office, WAN upgrade | Low | Successful | Minor | Planned | WJL | TT | 45051.6664 | 45055.7917 | 45055.9167 | 45055.7917 | 45055.9167 | 45061.3973 | 45061.3974 | 2023 | 2023-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45054.5962 | 45053.8505 | 45055.7787 | 45061.3974 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000301307 | AL, Ring 6 Area, Turn off Ring 6 Non-Traffic Carrying In-Service Ckts | Low | Successful | Minor | Unplanned | DRB | TT | 45054.5165 | 45061.375 | 45061.75 | 45061.375 | 45061.75 | 45062.3901 | 45062.3902 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45061.4192 | 45055.4753 | 45061.4245 | 45062.3902 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000301907 | GA, Sawnee Mtn & Gainesville IDEN, NOKIA NEXT GEN circuit migration. | Medium | Successful | Moderate | Planned | TSE | TT | 45056.4142 | 45069.3333 | 45069.875 | 45069.3632 | 45069.875 | 45070.4781 | 45070.4797 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45063.6156 | 45062.6779 | 45069.3211 | 45341.1766 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000301908 | GA, Sawnee Mtn & Gainesville IDEN, NOKIA NEXT GEN circuit migration. (BACKUP DATE) | Medium | Successful | Moderate | Planned | TSE | TT | 45056.4143 | 45077.3333 | 45077.875 | 45077.3958 | 45077.4701 | 45078.6446 | 45078.6483 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45070.5367 | 45070.4828 | 45077.3211 | 45341.1766 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000302504 | GA, Savannah ICON Ring, Insert SFPs to go from OC-3 to OC-12 network Crossgate-Weyerhauser-Cherokee | Medium | Successful | Moderate | Planned | RPY | TT | 45058.4522 | 45071.375 | 45071.7083 | 45071.3854 | 45071.7083 | 45075.6516 | 45075.6543 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45063.6183 | 45062.4058 | 45071.3629 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000302701 | AL, Pelham Office, Move ONT to UPS Power | Low | Successful | Minor | Planned | MSM | TT | 45058.423 | 45069.75 | 45069.8333 | 45069.7785 | 45069.7868 | 45070.4773 | 45070.4775 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45063.719 | 45062.6807 | 45069.737 | 45519.4508 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000302706 | GA, ATL ICON ring, Moreland Ave & Grady Circuit needs to be reprovisioned to clear system error | Medium | Successful | Moderate | Planned | RPY | TT | 45058.4969 | 45068.375 | 45068.7083 | 45068.375 | 45068.7083 | 45069.4071 | 45069.4088 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45063.6219 | 45061.5667 | 45068.3621 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000302707 | GA, ATL ICON ring, Moreland Ave & Grady Ckt needs to be reprovisioned to clear system error BACKUP | Medium | Successful | Moderate | Planned | RPY | TT | 45058.497 | 45069.375 | 45069.7083 | 45069.375 | 45069.4306 | 45069.4407 | 45069.4456 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45063.6208 | 45061.5671 | 45069.3628 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000302708 | AL, Greene County ICON Ring, Clear PLM System error for Bassett Creek | Low | Successful | Minor | Planned | RPY | TT | 45058.5025 | 45069.375 | 45069.7083 | 45069.4826 | 45069.5903 | 45069.5928 | 45069.5933 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45063.5968 | 45062.4 | 45069.3628 | 45340.9658 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000302900 | AL, WEST POINT TRANSPORT\LANETT EBTS, DC PLANT/BATTERY UPGRADE | Low | Successful | Minor | Planned | KNL | TT | 45060.6953 | 45069.25 | 45072.7917 | 45069.25 | 45072.7917 | 45075.6557 | 45075.6572 | 2023 | 2023-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45062.4786 | 45062.416 | 45069.2377 | 45498.7092 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000303005 | AL, Auburn, Splicing dark fibers for Point Broadband | Low | Successful | Minor | Planned | RCA | TT | 45061.3841 | 45068.2917 | 45072.25 | 45068.2917 | 45072.25 | 45075.655 | 45075.6571 | 2023 | 2023-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45063.597 | 45061.5656 | 45068.2787 | 45519.4588 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000303206 | GA, Surrency ILA Site, Installing new power connection. | Low | Successful | Minor | Planned | SDG | TT | 45061.484 | 45069.9167 | 45070.25 | 45069.9569 | 45070.0208 | 45070.4836 | 45070.4837 | 2023 | 2023-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45062.4798 | 45062.417 | 45069.9037 | 45070.4837 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000303310 | AL, Greenville, Migrate Greenville MW/TS Traffic to NGTAN | Medium | Successful | Moderate | Unplanned | DRB | TT | 45062.4555 | 45069.4167 | 45069.75 | 45069.4167 | 45069.566 | 45069.5828 | 45069.5853 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45068.5224 | 45065.5818 | 45069.4045 | 45069.5853 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000303402 | AL, Elliotsville, Splicing new cable for road move on South Shades Crest Rd | Low | Successful | Minor | Planned | RCA | TT | 45062.407 | 45076.7917 | 45079.2917 | 45076.7917 | 45079.2917 | 45079.3747 | 45079.3748 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45063.5934 | 45062.6821 | 45076.7793 | 45519.4588 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000303404 | AL, Calera, GSC complex, Splicing fiber for road move between buildings 9 and 9c | Low | Successful | Minor | Planned | RCA | TT | 45062.428 | 45076.75 | 45079.2917 | 45076.75 | 45079.2917 | 45079.374 | 45079.3743 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45063.5932 | 45063.5405 | 45076.7377 | 45519.4588 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000303607 | AL, Jasper Crew Headquarters, Move ONT to UPS Power | Low | Successful | Minor | Planned | MSM | TT | 45063.4459 | 45077.75 | 45077.9167 | 45077.7528 | 45077.7806 | 45078.6433 | 45078.6441 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45063.6763 | 45063.5396 | 45077.7377 | 45519.4508 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000303704 | AL, Jasper Local Office, Move ONT to UPS Power | Low | Successful | Minor | Planned | MSM | TT | 45063.4398 | 45077.75 | 45077.9167 | 45077.7688 | 45077.7806 | 45078.6426 | 45078.6439 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45063.7187 | 45063.5389 | 45077.7377 | 45519.4508 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000304000 | FL, Sneads ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45064.3376 | 45077.4583 | 45077.625 | 45077.4583 | 45077.5576 | 45078.6461 | 45078.6467 | 2023 | 2023-06 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45070.4029 | 45068.5831 | 45077.4463 | 45078.6467 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000304108 | MS, Region 4 Area, Reboot (7) NGTAN Routers in Region 4 due to Persistence Issue | Medium | Successful | Moderate | Planned | DRB | TT | 45064.568 | 45071.4167 | 45071.7917 | 45071.5104 | 45071.7861 | 45075.6472 | 45075.6546 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45070.6221 | 45068.5792 | 45071.4046 | 45075.6545 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000304113 | AL, Plant Barry, Reconfigure Plt Barry NGTAN Links for Improved Network Resiliency | Medium | Successful | Moderate | Planned | DRB | TT | 45064.7004 | 45076.5417 | 45076.9583 | 45076.584 | 45076.6194 | 45076.7274 | 45076.7301 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45069.4731 | 45068.5816 | 45076.5292 | 45076.7301 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000304114 | AL, Plant Barry, Reconfigure Plt Barry NGTAN Links for Improved Network Resiliency (BACKUP DATE) | Medium | Successful | Moderate | Planned | DRB | TT | 45064.7004 | 45097.5417 | 45097.9583 | 45097.5833 | 45097.6951 | 45098.4486 | 45098.4529 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45089.7039 | 45084.4933 | 45097.5292 | 45098.4528 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000304115 | AL, Region 6 Area, Remove TSOP Provisioning in Mobile SAR104 and Webb SAR001 | Low | Successful | Minor | Planned | DRB | TT | 45064.7266 | 45071.375 | 45071.7083 | 45071.6319 | 45071.6465 | 45075.6479 | 45075.6539 | 2023 | 2023-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45070.5735 | 45068.5772 | 45071.3629 | 45075.6539 | 2023-Q2 | 2023-05 | 2023-Q2
CRQ000000304801 | GA, Warm Springs-Athens NOKIA NEXT GEN Secondary COAM LINC LTE circuit. | Low | Successful | Minor | Planned | TSE | TT | 45068.3527 | 45090.5417 | 45090.75 | 45090.5417 | 45090.5799 | 45090.5835 | 45090.5837 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45083.6813 | 45083.4951 | 45090.5286 | 45341.1766 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000304807 | GA, MACON DCC, BATTERY UPGRADE | Low | Successful | Minor | Planned | KNL | TT | 45068.4437 | 45083.25 | 45086.75 | 45083.25 | 45086.75 | 45089.4598 | 45089.4599 | 2023 | 2023-06 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45070.4033 | 45068.6658 | 45083.2334 | 45498.7092 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000304901 | AL, PINCKARD TRANSPORT (OLD BUILDING) DC BATTERY UPGRADE | Low | Successful | Minor | Unplanned | KNL | TT | 45068.391 | 45078.2917 | 45079.7917 | 45078.2917 | 45079.7917 | 45082.405 | 45082.4051 | 2023 | 2023-06 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45077.4998 | 45077.4918 | 45078.2794 | 45498.7092 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000305111 | GA, ATL ICON ring, Airport nodes ethernet settings needs to be reprovisioned. | Medium | Successful | Moderate | Planned | RPY | TT | 45069.5836 | 45083.375 | 45083.7083 | 45083.4083 | 45083.4375 | 45083.4867 | 45083.488 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45082.4223 | 45076.4252 | 45083.3584 | 45340.9658 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000305617 | AL, Tallasee, Thurlow Dam and Yates Dam NGTAN Circuit Cutover | Medium | Successful | Moderate | Planned | GPB | TT | 45071.6857 | 45092.4167 | 45092.8333 | 45092.4167 | 45092.659 | 45093.5289 | 45093.5303 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45082.5609 | 45082.5269 | 45092.4045 | 45093.5303 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000305801 | AL, Anniston, Anniston Transport Remove Nokia SAR Config | Low | Successful | Minor | Planned | GPB | TT | 45071.3989 | 45082.5833 | 45082.6667 | 45082.5833 | 45082.6667 | 45082.7166 | 45082.7181 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45077.7763 | 45077.4319 | 45082.5709 | 45082.7181 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000306520 | AL, Wedowee ITC fiber POP, repair fiber damage | Low | Successful | Minor | Planned | DWM | TT | 45076.7295 | 45092.7917 | 45093.125 | 45092.7917 | 45093.125 | 45093.4513 | 45093.4514 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45079.9093 | 45078.552 | 45092.7795 | 45519.4679 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000306523 | AL, Demopolis EBTS, Grounding audit | Low | Successful | Minor | Planned | RBK | TT | 45077.0092 | 45084.4167 | 45084.7083 | 45084.4167 | 45084.7083 | 45085.4523 | 45085.4525 | 2023 | 2023-06 | Successful | Facilities Component | Cables, jumpers, and connectors | Repair | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45078.6992 | 45078.6498 | 45084.4069 | 45085.4525 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000306812 | AL, Tallassee, Yates Dam/MW, reconfigure fiber splices in can | Medium | Successful | Moderate | Planned | DHA | TT | 45077.6536 | 45089.7917 | 45089.9583 | 45089.7917 | 45089.9583 | 45090.407 | 45090.4087 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45082.4472 | 45078.6807 | 45089.7793 | 45519.4679 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000306820 | AL, Clanton Lay Dam and Wetumpka Jordan Comm. Room Nokia Config Change | Medium | Successful | Moderate | Planned | GPB | TT | 45077.717 | 45084.5833 | 45084.6667 | 45084.6278 | 45084.6618 | 45085.4537 | 45085.4558 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45082.4544 | 45078.6555 | 45084.5709 | 45085.4558 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307309 | GA, AL, FL, LTE cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45078.5876 | 45091 | 45091.0833 | 45091.0062 | 45091.0535 | 45091.475 | 45091.4759 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45083.404 | 45082.601 | 45090.9872 | 45091.4759 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307310 | MS, Meridian Area, Meridian DO to Meridian SC ASR Migrations/Transport Rework | Medium | BackedOut | Moderate | Planned | DRB | TT | 45078.5972 | 45091.7083 | 45092.041 | 45091.7083 | 45091.7188 | 45092.4134 | 45092.4178 | 2023 | 2023-06 | Unsuccessful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45083.6842 | 45082.6082 | 45091.696 | 45092.4178 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307311 | MS, Meridian Area, Meridian DO to Meridian SC ASR Migrations/Transport Rework (BACKUP DATE) | Medium | Successful | Moderate | Planned | DRB | TT | 45078.5972 | 45092.7083 | 45093.041 | 45092.7083 | 45092.9097 | 45093.447 | 45093.4527 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45083.6847 | 45082.6093 | 45092.6961 | 45093.4527 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307313 | MS, Hattiesburg, Reconfigure Hattiesburg SW Telecom Panel for New FDP Installs | Low | Successful | Minor | Planned | DRB | TT | 45078.6185 | 45090.4167 | 45090.75 | 45090.4222 | 45091.45 | 45091.4766 | 45091.4767 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45079.9113 | 45078.6841 | 45090.4044 | 45091.4767 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307617 | AL, LTE Cell site router software upgrades & reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45079.7137 | 45093 | 45093.0833 | 45093.0139 | 45093.059 | 45093.4478 | 45093.4534 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45086.524 | 45086.4709 | 45092.9879 | 45093.4533 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000307902 | AL, Whitman Colo and Holt Colo NGTAN circuit cutover | Low | Successful | Minor | Planned | GPB | TT | 45082.4484 | 45090.4167 | 45090.6667 | 45090.4181 | 45090.5 | 45090.567 | 45090.5672 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45083.6818 | 45083.4911 | 45090.4044 | 45090.5672 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308017 | AL, Gadsden TS, NGTAN Circuit Cutover | Low | Successful | Minor | Planned | GPB | TT | 45082.4581 | 45098.4167 | 45098.5833 | 45098.4167 | 45098.6278 | 45098.7145 | 45098.7147 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45089.6859 | 45085.5511 | 45098.4045 | 45098.7147 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308107 | AL, Montgomery, SDC NGTAN SWAN Circuit Cutover. | Medium | Successful | Moderate | Planned | GPB | TT | 45082.426 | 45091.4167 | 45091.6667 | 45091.4167 | 45091.5806 | 45092.4143 | 45092.4176 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45083.6875 | 45083.5321 | 45091.404 | 45092.4176 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308305 | AL, GA, Adtran OPTI Transport Ring 3 South Decommission | Medium | Successful | Moderate | Planned | TSE | TT | 45083.4705 | 45098.5417 | 45098.9993 | 45098.5417 | 45098.6618 | 45098.7176 | 45098.7191 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45096.5772 | 45092.7155 | 45098.5307 | 45341.1766 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308415 | GA, Savannah ICON Ring, Millhaven & Rossignol Overloaded Dpipe System Error | Medium | Successful | Moderate | Planned | RPY | TT | 45083.6294 | 45097.4167 | 45097.7083 | 45097.4167 | 45097.4264 | 45097.4347 | 45097.4363 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45089.7044 | 45085.5451 | 45097.3974 | 45340.9658 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308417 | GA, Savannah ICON Ring, Plant McIntosh, System log error cleanup | Medium | Successful | Moderate | Planned | DAP | TT | 45083.6473 | 45097.4167 | 45097.7083 | 45097.3972 | 45097.4125 | 45097.4311 | 45097.4362 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45089.7048 | 45085.5431 | 45097.3974 | 45097.4362 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308420 | GA, ATL ICON Ring, Northwest 230 ICON insertion into ring | Medium | Successful | Moderate | Planned | RPY | TT | 45083.6566 | 45098.4167 | 45098.7083 | 45098.4167 | 45098.6951 | 45098.7198 | 45098.7211 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45089.7069 | 45085.5483 | 45098.4046 | 45340.9658 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308511 | AL, Trussville, Splicing dark fiber for CSpire | Low | Successful | Minor | Planned | JFE | TT | 45084.7448 | 45091.7403 | 45092.741 | 45091.7403 | 45092.741 | 45093.5282 | 45093.5284 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JFE | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45085.5927 | 45085.5362 | 45091.7238 | 45519.4588 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308710 | GA, AL, Adtran OPTI Transport Ring 3 Express Decommission | Medium | Successful | Moderate | Planned | TSE | TT | 45084.6658 | 45104.5417 | 45104.9993 | 45104.5417 | 45104.8111 | 45104.8382 | 45104.8389 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45097.4857 | 45096.6605 | 45104.5292 | 45341.1766 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000308805 | GA, REIDSVILLE EBTS, TOOMBS CENTRAL EBTS, REPLACE SFP MODULES ON MINI-LINK PATH | Low | Unsuccessful | Minor | Planned | WKA | TT | 45085.403 | 45092.5417 | 45092.625 | 45092.5417 | 45092.625 | 45093.5297 | 45093.5298 | 2023 | 2023-06 | Unsuccessful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45085.5925 | 45085.5384 | 45092.5292 | 45519.4801 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000309705 | GA, AL, Adtran OPTI Transport Ring 3 North Decommission | Medium | Successful | Moderate | Planned | TSE | TT | 45089.3741 | 45104.5417 | 45104.9993 | 45104.5417 | 45104.8097 | 45104.8376 | 45104.8388 | 2023 | 2023-06 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45097.483 | 45096.6573 | 45104.5292 | 45341.1766 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000309723 | GA, SAV ICON Ring, Crossgate ICON PLM 1 needs to be reset | Medium | Successful | Moderate | Planned | RPY | TT | 45089.5664 | 45112.375 | 45112.7083 | 45112.375 | 45112.7083 | 45113.5573 | 45113.5581 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45089.7035 | 45089.5982 | 45112.3619 | 45340.9658 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000309724 | GA, SAV ICON Ring, Crossgate ICON PLM 1 needs to be reset (BACKUP DATE) | Medium | SuccessfulwithIssues | Moderate | Planned | RPY | TT | 45089.5664 | 45113.375 | 45113.7083 | 45113.375 | 45113.7083 | 45114.5478 | 45114.549 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45089.7031 | 45089.599 | 45113.3642 | 45340.9658 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000309741 | GA, Roopville, Transmission R.O.W., Open spice can for troubleshooting | Low | Successful | Minor | Planned | JLM | TT | 45089.8532 | 45098.75 | 45098.9792 | 45098.75 | 45098.9354 | 45099.4847 | 45099.4848 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45096.5489 | 45093.5392 | 45098.7392 | 45519.4679 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000310006 | AL & MS, Various sites, Turn Adtran OPTI Ring 4 Down | Low | Successful | Minor | Planned | GPB | TT | 45090.4853 | 45099.4167 | 45099.6667 | 45099.4167 | 45099.6111 | 45100.4083 | 45100.4084 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Remove/Retire | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45096.5488 | 45092.5311 | 45099.4061 | 45100.4084 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000310108 | GA, Ocilla ENODEB, Grounding Audit (BACKUP DATE) | Low | Successful | Minor | Planned | LPE | TT | 45090.5538 | 45098.375 | 45098.7083 | 45098.375 | 45098.7083 | 45099.482 | 45099.4842 | 2023 | 2023-06 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45091.4128 | 45090.7054 | 45098.3628 | 45099.4842 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000310701 | GA, Gainesville Transmission R.O.W., Repair OPGW at splice can | Low | Successful | Minor | Planned | JLM | TT | 45092.3263 | 45115.3333 | 45115.75 | 45115.3333 | 45115.5042 | 45117.4112 | 45117.4112 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45110.4313 | 45104.6995 | 45115.3224 | 45519.4679 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000310719 | AL, Bucks, Barry SP/Ellicott 230 SH, fiber testing | Low | Successful | Minor | Planned | DHA | TT | 45092.6514 | 45099.7917 | 45100 | 45099.7924 | 45099.8757 | 45100.3751 | 45100.3753 | 2023 | 2023-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45096.6769 | 45096.651 | 45099.7787 | 45519.4679 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000311007 | GA, Virginia Ave, relocate the Eltek DC Rectifier (AC) power feed to new AC Panel | Low | Successful | Minor | Planned | HFL | TT | 45093.5107 | 45118.2917 | 45118.625 | 45118.3799 | 45118.625 | 45119.4256 | 45119.4257 | 2023 | 2023-07 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | HEF | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45112.4053 | 45110.5628 | 45118.2803 | 45498.7092 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000311713 | AL, Stapleton ENODEB, Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45096.4302 | 45104.3333 | 45104.7083 | 45104.3333 | 45104.7083 | 45105.4215 | 45105.4216 | 2023 | 2023-06 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45096.6844 | 45096.6748 | 45104.3211 | 45105.4216 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000311732 | GA, AL, MS, LTE Cell site router software upgrades and reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45096.7125 | 45104 | 45104.0833 | 45104.0042 | 45104.0521 | 45104.3917 | 45104.3963 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45099.3442 | 45098.466 | 45103.9877 | 45104.3963 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000312019 | AL, MS, GA, LTE router software upgrades and reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45097.6512 | 45105 | 45105.0833 | 45105.0042 | 45105.0542 | 45105.4204 | 45105.4228 | 2023 | 2023-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45099.3449 | 45098.4743 | 45104.9878 | 45105.4228 | 2023-Q2 | 2023-06 | 2023-Q2
CRQ000000312203 | GA, St Mary's ENODEB, Shelter Maintenance for roof replacement | Low | Successful | Minor | Planned | LPE | TT | 45097.442 | 45117.3333 | 45123.7083 | 45117.3333 | 45123.7083 | 45124.412 | 45124.4121 | 2023 | 2023-07 | Successful | Facilities Component | Cable management system | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45098.7303 | 45098.5188 | 45117.3209 | 45124.4121 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000312414 | MS, GA, LTE router software upgrades and reboots | Medium | SuccessfulwithIssues | Moderate | Planned | DRI | TT | 45098.4944 | 45113 | 45113.0833 | 45113 | 45113.0833 | 45113.5202 | 45113.5559 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45104.7053 | 45104.6841 | 45112.9891 | 45113.5559 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000312905 | AL, Dadeville, splicing dark fibers for Point Broadband handoff | Low | Successful | Minor | Planned | RCA | TT | 45100.4493 | 45107.3333 | 45113.7917 | 45107.3333 | 45113.7917 | 45114.5483 | 45114.5486 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45104.445 | 45100.7017 | 45107.3212 | 45519.4588 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000313000 | GA, Ochlocknee ENODEB, Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45100.3653 | 45125.3958 | 45125.6458 | 45125.3958 | 45125.6458 | 45126.417 | 45126.4176 | 2023 | 2023-07 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45117.5495 | 45117.4211 | 45125.38 | 45126.4176 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000313416 | GA, Plant McDonough, Move CGRs that service CC4/5 and CC6 to Ethernet. | Low | Successful | Minor | Planned | JHW | TT | 45103.6738 | 45118.4167 | 45118.5417 | 45118.4167 | 45118.5417 | 45119.4273 | 45119.4275 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45112.4063 | 45110.6607 | 45118.4054 | 45119.4275 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000313713 | MS, GA, LTE router software upgrades and reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45104.848 | 45114 | 45114.0833 | 45114.0201 | 45114.1132 | 45114.5507 | 45114.551 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45110.5526 | 45110.5166 | 45113.9808 | 45114.551 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000314201 | Various sites, Nokia SAR's QoS Policy Changes | Low | Successful | Minor | Planned | GPB | TT | 45105.6578 | 45113.4167 | 45113.9167 | 45113.4167 | 45113.9167 | 45114.5494 | 45114.5496 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45110.5177 | 45110.4418 | 45113.4059 | 45114.5496 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000314203 | AL, Birmingham, 12th St Complex Splicing fibers for Connectivity to Corporate HQ | Low | Successful | Minor | Planned | RCA | TT | 45105.6627 | 45112.2917 | 45114.75 | 45112.2917 | 45114.75 | 45117.4101 | 45117.4104 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45110.5177 | 45110.4437 | 45112.2786 | 45519.4588 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000314517 | AL, Anniston ICON Ring, Correct SWAN configuration (BACKUP DATE) | Medium | Successful | Moderate | Planned | RPY | TT | 45106.5994 | 45120.4167 | 45120.5417 | 45120.4215 | 45120.4458 | 45121.4168 | 45121.4182 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45112.712 | 45112.5506 | 45120.4059 | 45340.9658 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000315906 | Various sites, Nokia SAR's QoS Policy Changes Day 2 | Low | Successful | Minor | Planned | GPB | TT | 45112.3922 | 45118.4167 | 45118.9167 | 45118.4167 | 45118.9167 | 45119.4264 | 45119.4265 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45112.6508 | 45112.407 | 45118.4054 | 45119.4265 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000315913 | Various sites, Nokia SAR's QoS Policy Changes Day 3 | Low | Successful | Minor | Planned | GPB | TT | 45112.4945 | 45119.4167 | 45119.9167 | 45119.4167 | 45119.9167 | 45120.4336 | 45120.4338 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45112.6509 | 45112.5463 | 45119.4053 | 45120.4338 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000315921 | AL, Gorgas, Sumiton, Smith Dam, Alcatel MDR8000 Upgrade to Nokia Wavence radios | Medium | Successful | Moderate | Unplanned | WJL | TT | 45112.6206 | 45118.3333 | 45122.75 | 45118.3333 | 45122.75 | 45124.41 | 45124.4114 | 2023 | 2023-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45117.5703 | 45114.558 | 45118.3219 | 45124.4114 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000315922 | AL, Gorgas, Sumiton, Smith Dam, Alcatel MDR8000 Upgrade to Nokia Wavence radios (BACKUP DATE) | Medium | Successful | Moderate | Planned | WJL | TT | 45112.6207 | 45124.3333 | 45128.75 | 45124.3333 | 45128.75 | 45131.3971 | 45131.3982 | 2023 | 2023-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45117.5699 | 45114.5592 | 45124.3217 | 45131.3982 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000316706 | AL, Birmingham, audit splice can for traffic in can | Low | Successful | Minor | Planned | DWM | TT | 45114.5305 | 45124.7917 | 45126.0208 | 45124.7917 | 45124.9097 | 45124.9425 | 45124.9427 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45121.6991 | 45117.6353 | 45124.7807 | 45519.4679 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000317026 | AL, Ward LTE, replace SPDs and DC breakers | Low | Successful | Minor | Planned | RBK | TT | 45117.6509 | 45141.5 | 45141.6667 | 45141.5 | 45141.6667 | 45142.467 | 45142.4671 | 2023 | 2023-08 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45137.6258 | 45137.6241 | 45141.4878 | 45142.4671 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000317033 | AL, Linden, OPGW Fiber can testing | Low | Successful | Minor | Planned | DHA | TT | 45117.7845 | 45134.7917 | 45135 | 45134.7917 | 45135 | 45138.4586 | 45138.4594 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45121.6995 | 45119.6506 | 45134.7808 | 45519.4679 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000317319 | GA, Atlanta, Powers Ferry Substation, Move FDP's to new T.O. rack | Low | Successful | Minor | Planned | JLM | TT | 45118.5826 | 45132.3333 | 45132.75 | 45132.3618 | 45132.5222 | 45133.4384 | 45133.4386 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45125.4484 | 45124.4556 | 45132.3219 | 45519.4679 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000317322 | AL, Calera EBTS, GSC A9150, Dish wireless installing a dish on the CCI tower | Low | Successful | Minor | Planned | CDL | TT | 45118.6442 | 45124.5833 | 45128.8333 | 45124.5833 | 45128.8333 | 45131.3976 | 45131.3977 | 2023 | 2023-07 | Successful | Transport Device | Tower Structure | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45119.7905 | 45119.6562 | 45124.5723 | 45131.3977 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000317323 | AL, Calera EBTS, GSC A9150, Dish wireless installing a dish on the CCI tower (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45118.6443 | 45131.375 | 45135.8333 | 45131.375 | 45135.8333 | 45138.4567 | 45138.4569 | 2023 | 2023-07 | Successful | Transport Device | Tower Structure | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45119.7882 | 45119.6573 | 45131.3627 | 45138.4569 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000317718 | AL, Autaugaville, Plant Harris, splicing into dark fiber | Low | Successful | Minor | Planned | DHA | TT | 45119.672 | 45127.7917 | 45127.9583 | 45127.7917 | 45127.9076 | 45128.4478 | 45128.4479 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45121.6996 | 45120.4377 | 45127.7808 | 45519.4679 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000318011 | GA, North GA ICON Ring, Epipe addition to Plant Tugalo for Gen. Network | Medium | Successful | Moderate | Planned | RPY | TT | 45120.5704 | 45131.4167 | 45131.5417 | 45131.4167 | 45131.4493 | 45131.4695 | 45131.471 | 2023 | 2023-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45125.4584 | 45124.6002 | 45131.4044 | 45340.9658 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000318117 | AL, Altamont School LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45120.8845 | 45132 | 45132.0417 | 45132 | 45132.0417 | 45132.3221 | 45132.3225 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45126.4669 | 45124.7533 | 45131.9885 | 45132.3225 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000318608 | GA, Westpoint, Kia Plant, G9160, moving from COW to site. (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45124.4265 | 45136.375 | 45138.875 | 45136.375 | 45138.875 | 45139.4042 | 45139.4044 | 2023 | 2023-08 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45126.4666 | 45124.7417 | 45136.3627 | 45139.4044 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000318721 | MS, GA, LTE router software upgrades and reboots | Medium | Successful | Moderate | Planned | DRI | TT | 45124.7128 | 45132 | 45132.0833 | 45132 | 45132.0833 | 45132.3177 | 45132.3211 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45125.4573 | 45124.757 | 45131.9885 | 45132.3211 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000318806 | GA, Westpoint, Kia Plant, G9160, moving from COW to site. | Low | Successful | Minor | Planned | CDL | TT | 45124.4264 | 45131.375 | 45135.875 | 45131.375 | 45135.875 | 45138.4553 | 45138.4563 | 2023 | 2023-07 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45126.4662 | 45124.7408 | 45131.3627 | 45138.4563 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000318807 | GA, Columbus DCC Transport, Migrate Columbus 115kv SWAN from point to point to Ethernet | Low | Successful | Minor | Planned | JHW | TT | 45124.4327 | 45139.375 | 45139.4583 | 45139.375 | 45139.4583 | 45140.4539 | 45140.4547 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45128.4713 | 45124.7598 | 45139.3634 | 45140.4547 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000318829 | MS, MERIDIAN NE - MERIDIAN HWY 80, REPAIR 36-COUNT DAMAGED FIBER CABLE | Medium | Successful | Moderate | Planned | SEV | TT | 45124.7452 | 45131.2917 | 45131.875 | 45131.7917 | 45131.8014 | 45132.3191 | 45132.321 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | SE | SCS | INFRASTRUCTURE SERVICES | FO MS FIBER OPS AND PROJECTS | 45128.4785 | 45125.5962 | 45131.2794 | 45519.4714 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000319005 | GA, GAINESVILLE, EBTS/TRANSPORT BLDG, ATS REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45125.4017 | 45140.3333 | 45140.7083 | 45140.3361 | 45140.6708 | 45141.4296 | 45141.4298 | 2023 | 2023-08 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45126.4709 | 45126.4479 | 45140.3217 | 45498.7092 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000319021 | AL, Calera, Splice fibers to tie Calera Fiber Yard Longview DS OLT cabinet. | Low | Successful | Minor | Planned | RCA | TT | 45125.6522 | 45132.3333 | 45135.7917 | 45132.3333 | 45135.7917 | 45137.6565 | 45137.6566 | 2023 | 2023-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45128.4714 | 45126.4403 | 45132.3219 | 45519.4588 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000319110 | GA, St Mary's ENODEB, Shelter Maintenance/Move Transport Back to Shelter | Low | Successful | Minor | Planned | LPE | TT | 45125.6074 | 45147.4167 | 45147.7083 | 45147.4167 | 45147.7083 | 45149.408 | 45149.4081 | 2023 | 2023-08 | Successful | Facilities Component | Cable management system | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45138.4852 | 45138.4406 | 45147.4045 | 45149.4081 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000319111 | GA, St Mary's ENODEB, Shelter Maintenance/Move Transport Back to Shelter (BACKUP DATE) | Low | Successful | Minor | Planned | LPE | TT | 45125.6075 | 45148.4167 | 45148.7083 | 45148.4167 | 45148.7083 | 45149.4085 | 45149.4087 | 2023 | 2023-08 | Successful | Facilities Component | Cable management system | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45138.4854 | 45138.4439 | 45148.4046 | 45149.4087 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000319215 | GA, Appling, South Appling ENODEB, Hybrid Replacement | Low | Successful | Minor | Planned | LPE | TT | 45126.4427 | 45134.375 | 45134.7083 | 45134.375 | 45134.7083 | 45138.4578 | 45138.4579 | 2023 | 2023-07 | Successful | Facilities Component | Cables, jumpers, and connectors | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45126.4717 | 45126.4705 | 45134.3636 | 45138.4579 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000319222 | MS, MERIDIAN, MOVE SWAN CIRCUITS FROM SERVICE CENTER TO MERIDIAN TELECOM | Medium | Successful | Moderate | Unplanned | AEN | TT | 45126.6339 | 45133.4167 | 45133.7083 | 45133.4167 | 45133.5243 | 45133.6198 | 45133.6213 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Migrate | Transport | AEN | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45131.5474 | 45131.4333 | 45133.4052 | 45133.6213 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000319322 | MS, MERIDIAN, MOVE SWAN CIRCUITS FROM SERVICE CENTER TO MERIDIAN TELECOM | Medium | Successful | Moderate | Planned | AEN | TT | 45126.6417 | 45134.4167 | 45134.7083 | 45134.4167 | 45134.7083 | 45137.614 | 45137.6151 | 2023 | 2023-07 | Successful | Transport Device | Other Transport Device | Migrate | Transport | AEN | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45131.5595 | 45131.4359 | 45134.4053 | 45137.6151 | 2023-Q3 | 2023-07 | 2023-Q3
CRQ000000319520 | AL, Trussville, Splicing dark fiber for CSpire Handoff | Low | Successful | Minor | Planned | RCA | TT | 45127.6301 | 45138.3333 | 45140.7917 | 45138.3333 | 45140.7917 | 45141.4289 | 45141.4291 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45131.5155 | 45131.4678 | 45138.3217 | 45519.4588 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000320804 | GA, Atlanta, LTE, Glenridge G9784 moving LTE sector 1 on penthouse (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45132.3435 | 45152.3333 | 45156.8333 | 45152.3333 | 45154.3333 | 45154.4555 | 45154.4556 | 2023 | 2023-08 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45139.5681 | 45139.5563 | 45152.3217 | 45154.4556 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000320825 | MS, Baxter EBTS, Modify rectifier DC output wiring to reflect correct amps. | Low | Successful | Minor | Planned | RBK | TT | 45132.9445 | 45141.4167 | 45141.5 | 45141.4167 | 45141.5 | 45142.4662 | 45142.4664 | 2023 | 2023-08 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45135.5779 | 45134.4249 | 45141.4045 | 45142.4664 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000320905 | AL, Dadeville, Splicing new cable to replace damaged cable. | Low | Successful | Minor | Planned | RCA | TT | 45132.4486 | 45140.2917 | 45142.75 | 45140.2917 | 45142.75 | 45145.5037 | 45145.5038 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45135.5775 | 45134.4236 | 45140.28 | 45519.4588 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000320915 | GA, Canton Ops Center to Canton Transport/EBTS, 6GHz to 11GHz MW Radio Upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45132.6562 | 45143.3333 | 45143.8333 | 45143.3333 | 45143.7965 | 45145.5028 | 45145.5041 | 2023 | 2023-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45138.486 | 45138.4368 | 45143.3211 | 45519.4736 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000321010 | GA, ATL ICON Ring, GA Tech out of service for P&C work. | Medium | Successful | Moderate | Planned | RPY | TT | 45132.5383 | 45189.3333 | 45189.75 | 45189.3375 | 45189.4257 | 45190.4264 | 45190.4274 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45148.4587 | 45146.6053 | 45189.325 | 45340.9658 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000321129 | AL, Columbia, Farley EBTS/Transport Bldg, Test DC Battery Bank | Low | Successful | Minor | Planned | JEN | TT | 45133.7333 | 45140.375 | 45140.875 | 45140.375 | 45140.875 | 45141.4308 | 45141.4309 | 2023 | 2023-08 | Successful | Facilities Component | DC Backup System | Repair | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45137.6056 | 45137.6044 | 45140.3634 | 45519.4508 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000321130 | AL, Columbia, Farley EBTS/Transport Bldg, Test DC Battery Bank (BACKUP DATE) | Low | Successful | Minor | Planned | JEN | TT | 45133.7333 | 45141.375 | 45141.875 | 45141.375 | 45141.875 | 45142.4656 | 45142.4657 | 2023 | 2023-08 | Successful | Facilities Component | DC Backup System | Repair | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45137.6056 | 45137.6047 | 45141.3628 | 45519.4508 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322205 | GA, Atlanta, GPC HQ and VAV Ciena 6500 Circuit Cuts #1 | Medium | Successful | Moderate | Planned | GPB | TT | 45138.3888 | 45145.7083 | 45146 | 45145.7083 | 45145.984 | 45146.3941 | 45146.396 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45139.3756 | 45138.4694 | 45145.6967 | 45146.396 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322206 | AL and GA, PCC, Colonnade, and VAV Ciena 6500 Circuit Cuts Group #2 | Medium | Successful | Moderate | Planned | GPB | TT | 45138.4022 | 45146.75 | 45147.041 | 45146.75 | 45147.041 | 45147.5683 | 45147.5693 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45139.3759 | 45138.4731 | 45146.7377 | 45147.5692 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322218 | GA, AL, Douglas Hills A and Leaf Lake, NOKIA IXR node insertion. | Medium | Successful | Moderate | Planned | TSE | TT | 45138.6262 | 45155.5417 | 45155.875 | 45155.5417 | 45155.6562 | 45155.6588 | 45155.66 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45142.539 | 45141.486 | 45155.5292 | 45341.1766 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322305 | AL, Linden, OPGW Fiber repair | Low | Successful | Minor | Planned | DHA | TT | 45138.4898 | 45155.7917 | 45156 | 45155.809 | 45155.9479 | 45156.5324 | 45156.5325 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45142.5248 | 45141.5059 | 45155.7794 | 45519.4679 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322502 | AL, Montgomery, Jefferson Street, Testing alarms for new OLT for Montgomery FTD | Low | Successful | Minor | Planned | JGL | TT | 45138.9675 | 45146.5833 | 45146.6667 | 45146.5833 | 45146.6667 | 45147.5668 | 45147.567 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45141.552 | 45140.5152 | 45146.5709 | 45147.567 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322503 | AL, Montgomery, Jefferson Street, Testing alarms for new OLT for Montgomery FTD (BACKUP DATE) | Low | Successful | Minor | Planned | JGL | TT | 45138.9676 | 45152.5833 | 45152.6667 | 45152.5833 | 45152.6667 | 45154.3948 | 45154.3948 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45141.5522 | 45140.516 | 45152.5723 | 45154.3948 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322721 | GA, Atlanta ICON Ring, provision Protection circuit from Lawrenceville to Norcross #2 | Medium | Successful | Moderate | Planned | DAP | TT | 45139.5387 | 45169.4167 | 45169.5 | 45169.4167 | 45169.5 | 45170.4486 | 45170.4558 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45160.33 | 45159.6689 | 45169.4045 | 45170.4558 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000322730 | GA, LTE router software update & reboot | Medium | Successful | Moderate | Planned | DRI | TT | 45139.8084 | 45146.9583 | 45147.041 | 45146.9583 | 45147.041 | 45147.566 | 45147.5678 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45141.3865 | 45140.5175 | 45146.9461 | 45147.5678 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000322809 | AL, Auburn, Splicing dark fiber for Point Broadband handoff | Low | Successful | Minor | Planned | RCA | TT | 45139.7388 | 45146.3333 | 45148.7917 | 45146.3333 | 45148.7917 | 45149.4074 | 45149.4076 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45141.5265 | 45140.5093 | 45146.3218 | 45519.4588 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323004 | AL & GA, APC HQ, GPC HQ, Anniston, and VAV Ciena 6500 Circuit Cuts Group #4 | Medium | Successful | Moderate | Planned | GPB | TT | 45140.401 | 45148.75 | 45149.041 | 45148.75 | 45149.041 | 45149.41 | 45149.4106 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45142.5398 | 45140.5258 | 45148.7362 | 45149.4106 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323016 | GA, Rincon, SCS fiber hut, G8174 Plant McIntosh LTE install | Low | Successful | Minor | Planned | CDL | TT | 45140.7352 | 45145.3333 | 45149.8333 | 45145.3333 | 45149.8333 | 45151.7464 | 45151.7465 | 2023 | 2023-08 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45141.525 | 45141.4668 | 45145.3223 | 45151.7465 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323017 | GA, Rincon, SCS fiber hut, G8174 Plant McIntosh LTE install (BACKUP DATE) | Medium | Successful | Moderate | Planned | CDL | TT | 45140.7353 | 45152.3333 | 45156.8333 | 45152.3333 | 45156.8333 | 45158.6385 | 45158.644 | 2023 | 2023-08 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45141.5417 | 45141.4678 | 45152.3217 | 45158.644 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323104 | AL, Birmingham, APC HQ and PCC Ciena 6500 Circuit Cuts Group #3 | Medium | Successful | Moderate | Planned | GPB | TT | 45140.3949 | 45147.75 | 45148.041 | 45147.75 | 45147.8403 | 45148.4699 | 45149.4069 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45142.5394 | 45140.5232 | 45147.7377 | 45149.4069 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323200 | FL, Jacksonville, Jacksonville MH#2, Splicing for Hargray | Low | Successful | Minor | Planned | SDG | TT | 45140.4131 | 45152.9375 | 45153.25 | 45152.975 | 45153.0174 | 45154.3971 | 45154.3972 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45142.5261 | 45141.4686 | 45152.9197 | 45154.3972 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323201 | FL, Jacksonville, Jacksonville MH#2, Splicing for Hargray (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45140.4132 | 45153.9375 | 45154.25 | 45153.9375 | 45154.25 | 45154.3987 | 45154.3989 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45142.5261 | 45141.4691 | 45153.919 | 45154.3989 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323412 | GA, Kathleen Transmission ROW, Replace damage section of OPGW | Low | Successful | Minor | Planned | MAR | TT | 45141.626 | 45190.3333 | 45190.75 | 45190.3333 | 45190.5694 | 45191.4564 | 45191.4565 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45180.6961 | 45176.4477 | 45190.321 | 45519.4626 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000323509 | AL, West Point to Bartlett's Ferry, Emergency Replace OPGW between Str 33 and 32 | Low | Successful | Minor | Unplanned | RRR | TT | 45141.4491 | 45146 | 45146.25 | 45146 | 45146.25 | 45146.3954 | 45146.3956 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45145.5106 | 45145.5062 | 45145.9884 | 45519.4679 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323510 | AL, West Point to Bartlett's Ferry Emergency Replace OPGW between Str 33 and 32 (BACKUP DATE) | Low | Successful | Minor | Planned | RRR | TT | 45141.4492 | 45147 | 45147.25 | 45147 | 45147.25 | 45147.5688 | 45147.569 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45145.5551 | 45145.5536 | 45146.9877 | 45519.4679 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323616 | AL, Various, APC HQ, Colonnade, and PCC Ciena 6500 Circuit Cuts Group #5 | Medium | Successful | Moderate | Planned | GPB | TT | 45142.598 | 45152.75 | 45153.041 | 45152.75 | 45152.9104 | 45154.3943 | 45154.3964 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45148.4908 | 45145.5811 | 45152.7391 | 45154.3964 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000323618 | AL & GA, APC, GPC, Colonnade, Anniston, VAV and PCC Ciena 6500 Circuit Cuts Group #6-9 | Medium | Successful | Moderate | Planned | GPB | TT | 45142.6134 | 45153.75 | 45156.041 | 45153.75 | 45156.041 | 45156.5306 | 45156.5334 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45148.4913 | 45145.579 | 45153.7383 | 45156.5334 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324203 | AL, Alabaster, Splicing dark fiber handoff for C-Spire | Low | Successful | Minor | Planned | RCA | TT | 45145.4241 | 45154.7917 | 45155.7917 | 45154.7917 | 45155.7917 | 45156.532 | 45156.5321 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45148.4269 | 45146.6159 | 45154.7794 | 45519.4588 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324205 | GA, Canton Transport, Reconfigure Canton 9500MPR | Low | Successful | Minor | Planned | JWH | TT | 45145.4554 | 45152.7083 | 45152.875 | 45152.7083 | 45152.875 | 45154.3955 | 45154.3956 | 2023 | 2023-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JAW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45145.5957 | 45145.5708 | 45152.6974 | 45154.3956 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324206 | GA, Canton Transport, Reconfigure Canton 9500MPR (BACKUP DATE) | Low | Successful | Minor | Planned | JWH | TT | 45145.4555 | 45153.7083 | 45153.875 | 45153.7083 | 45153.875 | 45154.3959 | 45154.396 | 2023 | 2023-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JAW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45145.596 | 45145.5713 | 45153.6967 | 45154.396 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324413 | GA, NO GA ICON Ring, New SWAN circuit build due lack of IP ranges | Medium | Successful | Moderate | Planned | RPY | TT | 45145.6463 | 45174.3958 | 45174.625 | 45174.3972 | 45174.4847 | 45174.5545 | 45174.5594 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45170.5032 | 45167.6672 | 45174.3766 | 45340.9658 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000324415 | GA, SAV ICON Ring, New SWAN circuit build due lack of IP ranges | Medium | Successful | Moderate | Planned | RPY | TT | 45145.6498 | 45166.3958 | 45166.5833 | 45166.3958 | 45166.5833 | 45166.8039 | 45166.8049 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45159.5911 | 45155.4775 | 45166.3835 | 45340.9658 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324529 | GA, WAYNESBORO, PLANT VOGTLE 3&4 BLDGS 147A/B, GENERATOR EXERCISE ASSUMING LOAD | Low | Successful | Minor | Planned | WKA | TT | 45146.6548 | 45181.3333 | 45181.625 | 45181.4243 | 45181.6215 | 45182.6489 | 45182.689 | 2023 | 2023-09 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45148.6475 | 45148.6263 | 45181.3217 | 45519.4801 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000324537 | AL, Boaz, Aurora LTE, tower grounding audit. | Low | Successful | Minor | Planned | RBK | TT | 45146.7885 | 45183.375 | 45183.7917 | 45183.375 | 45183.7917 | 45184.4325 | 45184.4326 | 2023 | 2023-09 | Successful | Facilities Component | Cables, jumpers, and connectors | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45177.5651 | 45176.4522 | 45183.3634 | 45184.4326 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000324538 | AL, Boaz, Aurora LTE, tower grounding audit. (BACKUP DATE) | Low | Successful | Minor | Planned | RBK | TT | 45146.7886 | 45184.375 | 45184.7917 | 45184.375 | 45184.7917 | 45187.4452 | 45187.4453 | 2023 | 2023-09 | Successful | Facilities Component | Cables, jumpers, and connectors | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45177.5653 | 45176.4542 | 45184.3627 | 45187.4453 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000324619 | GA, 241 SAR002 to Klondike SAR001 Network Circuit bouncing and creating CRC errors. | Low | Successful | Minor | Planned | MPH | TT | 45146.5134 | 45159.4167 | 45159.7083 | 45159.4167 | 45159.5278 | 45159.5445 | 45159.5447 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Repair | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45147.7162 | 45146.6542 | 45159.4044 | 45159.5447 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324628 | GA, REIDSVILLE EBTS/TOOMBS CENTRAL EBTS, INTRUSIVE NETWORK TESTING ON MINI-LINK | Low | Successful | Minor | Planned | WKA | TT | 45146.6891 | 45152.3333 | 45156.5 | 45152.3333 | 45156.5 | 45156.5355 | 45156.5356 | 2023 | 2023-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO GA OPERATIONS | 45147.7134 | 45147.6808 | 45152.3217 | 45519.4801 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324709 | MS, MERIDIAN, TELECOM, MOVE SWAN CIRCUITS FROM SERVICE CENTER TO MERIDIAN TELECOM | Medium | Successful | Moderate | Planned | AEN | TT | 45147.432 | 45154.4167 | 45154.5 | 45154.4458 | 45154.5042 | 45154.5989 | 45154.599 | 2023 | 2023-08 | Successful | Transport Device | Service Aggregation Router | Migrate | Transport | AEN | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45152.3607 | 45151.7442 | 45154.4053 | 45154.599 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324717 | AL, Jasper, Splicing dark fiber for C-Spire handoff | Low | Successful | Minor | Planned | RCA | TT | 45147.4678 | 45154.2917 | 45155.75 | 45154.4431 | 45155.75 | 45156.5314 | 45156.5316 | 2023 | 2023-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45148.4272 | 45147.7152 | 45154.2802 | 45519.4588 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000324917 | GA, Various sites, LTE router software update & reboot | Medium | Successful | Moderate | Planned | DRI | TT | 45147.5854 | 45152.9583 | 45153.041 | 45152.9583 | 45153.041 | 45154.3978 | 45154.3983 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45148.3905 | 45147.6795 | 45152.9475 | 45154.3983 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000325004 | AL, Birmingham, Patton Chapel EBTS, Audit splice can for traffic in can | Low | Successful | Minor | Planned | DWM | TT | 45148.3526 | 45181.7917 | 45182 | 45181.7917 | 45182 | 45182.7074 | 45182.712 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45168.8213 | 45166.8084 | 45181.78 | 45519.4679 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000325409 | GA, Macon, Structure 7, Splicing two fibers for Hargray | Low | Successful | Minor | Planned | SDG | TT | 45149.6151 | 45174.9167 | 45175.25 | 45174.9819 | 45175.1208 | 45175.4097 | 45175.4098 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45169.4738 | 45169.4697 | 45174.9044 | 45175.4098 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000326127 | GA, No GA ICON Ring, Change from OC-3 to OC-12 | Medium | Successful | Moderate | Planned | RPY | TT | 45152.7326 | 45166.4167 | 45166.5833 | 45166.4167 | 45166.5833 | 45166.6224 | 45166.6232 | 2023 | 2023-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45160.3332 | 45159.6646 | 45166.3975 | 45340.9658 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000326404 | AL, Tuscaloosa, ALDOT fiber relocation | Low | Successful | Minor | Planned | DWM | TT | 45153.4362 | 45199.2917 | 45199.875 | 45199.3264 | 45199.475 | 45200.8312 | 45200.8313 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45154.951 | 45154.6964 | 45199.273 | 45519.4679 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000326713 | GA, SAV ICON Ring, Swap Server module at Plant Kraft | Low | Successful | Minor | Planned | RPY | TT | 45154.542 | 45175.3958 | 45175.6042 | 45175.3958 | 45175.525 | 45176.4442 | 45176.4443 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45159.7767 | 45159.6624 | 45175.3834 | 45340.9658 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000326908 | GA, Tallulah Intake Building, move 12 fiber cable. (BACKUP DATE) | Medium | Unsuccessful | Moderate | Planned | MAR | TT | 45155.4125 | 45166.3333 | 45166.75 | 45166.3333 | 45166.5174 | 45166.5738 | 45166.576 | 2023 | 2023-08 | Unsuccessful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45159.5878 | 45156.5279 | 45166.314 | 45519.4626 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000327010 | AL, Uniontown EBTS A9229, adding CBRS to the Skymounts | Low | Successful | Minor | Unplanned | CDL | TT | 45155.5266 | 45167.3958 | 45170.7917 | 45167.3958 | 45170.7917 | 45174.4414 | 45174.4415 | 2023 | 2023-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45167.39 | 45167.389 | 45167.392 | 45174.4415 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000327011 | AL, Uniontown EBTS A9229, adding CBRS to the Skymounts (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45155.5266 | 45174.375 | 45177.8333 | 45174.375 | 45177.8333 | 45180.5607 | 45180.5726 | 2023 | 2023-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45156.5332 | 45156.5296 | 45174.3627 | 45180.5726 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000327206 | GA, Smyrna Environmental Lab, Powerware 9170 UPS Replacement. | Low | Successful | Minor | Planned | HFL | TT | 45156.4237 | 45171.2708 | 45171.7083 | 45171.2708 | 45171.566 | 45174.4422 | 45174.4423 | 2023 | 2023-09 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | HEF | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45166.6322 | 45166.4417 | 45171.2523 | 45498.7092 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000327909 | GA, Bremen, Transport Ciena 6500 Troubleshoot Fiber ORL Issue. | Low | Successful | Minor | Planned | GPB | TT | 45159.4769 | 45181.75 | 45182 | 45181.75 | 45182 | 45182.7052 | 45182.7126 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45174.6758 | 45170.5823 | 45181.7383 | 45182.7126 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000328208 | AL, Clanton Lay Dam and Wetumpka Bouldin Dam, add new Generation WAN to Nokia SAR | Low | Successful | Minor | Planned | GPB | TT | 45160.3805 | 45175.4375 | 45175.5208 | 45175.4375 | 45175.5208 | 45176.6522 | 45176.6524 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45170.4454 | 45167.6484 | 45175.4252 | 45176.6524 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000328601 | GA, Atlanta, 241 RALPH MCGILL LINC LTE, changing the traffic path for all SCADA devices | Medium | Successful | Moderate | Planned | RAS | TT | 45161.3806 | 45183.8333 | 45183.9167 | 45183.8333 | 45183.8736 | 45184.4303 | 45184.4319 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | RAS | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45174.7091 | 45170.5977 | 45183.821 | 45184.4319 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000328701 | AL, Birmingham, APC CORP HQ LINC LTE, changing the traffic path for all SCADA devices | Medium | Successful | Moderate | Planned | RAS | TT | 45161.3752 | 45181.8333 | 45181.9167 | 45181.8333 | 45181.9167 | 45182.6364 | 45182.6469 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | RAS | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45174.7098 | 45170.5961 | 45181.8217 | 45182.6469 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000329028 | AL, Vestavia and Spain Park, Migrate leased circuit to new AT&T ASEoD service. (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45162.6299 | 45176.5 | 45177.0833 | 45177.0104 | 45177.0785 | 45180.5731 | 45180.5734 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45167.4151 | 45167.4067 | 45176.4887 | 45180.5734 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000329305 | GA, North Powder Springs LTE ASR920, cell site router replacement | Low | Successful | Minor | Planned | DRI | TT | 45163.494 | 45169.4583 | 45169.625 | 45169.4583 | 45169.4688 | 45169.4731 | 45169.4732 | 2023 | 2023-08 | Successful | Transport Device | Other Transport Device | Repair | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45167.4146 | 45167.4047 | 45169.4462 | 45169.4732 | 2023-Q3 | 2023-08 | 2023-Q3
CRQ000000330408 | AL, Montgomery SDC and J St, Ciena 6500 Circuit and Card Changes (Procedure #2) | Medium | Successful | Moderate | Planned | GPB | TT | 45168.4891 | 45181.75 | 45182.041 | 45181.75 | 45182.041 | 45182.704 | 45182.7125 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45170.5041 | 45169.5369 | 45181.7383 | 45182.7125 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000330422 | AL and GA, Various, Transport, Ciena 6500 Circuit and Card Moves (Procedure 5&6) | Medium | Successful | Moderate | Planned | GPB | TT | 45168.6353 | 45183.75 | 45184.041 | 45183.759 | 45184.041 | 45184.4356 | 45184.4359 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45170.5037 | 45169.5451 | 45183.7376 | 45184.4359 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000330510 | AL and GA, Montgomery and Columbus, Ciena 6500 Circuit Moves (Procedure #1) | Medium | Successful | Moderate | Planned | GPB | TT | 45168.454 | 45180.75 | 45181.041 | 45180.75 | 45181.041 | 45181.3861 | 45181.3864 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45170.4506 | 45169.5353 | 45180.7383 | 45181.3864 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000330617 | AL and GA, N Auburn and Jackson, Ciena 6500 Move Circuits and Cards (Procedure 3&4) | Medium | Successful | Moderate | Planned | GPB | TT | 45168.624 | 45182.75 | 45183.041 | 45182.75 | 45183.041 | 45183.4689 | 45183.4692 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45170.4502 | 45169.5382 | 45182.7383 | 45183.4692 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000330622 | GA, LTE router software update & reboot | Medium | Successful | Moderate | Planned | DRI | TT | 45168.7901 | 45175.9583 | 45176.041 | 45175.9583 | 45176.0132 | 45176.4436 | 45176.4448 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45174.6091 | 45170.4577 | 45175.9468 | 45176.4448 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000330721 | AL, Birmingham, splicing for cable relocation for new apartment complex. | Low | Successful | Minor | Planned | RCA | TT | 45169.7051 | 45181.3333 | 45182.7917 | 45181.3333 | 45182.7917 | 45183.4672 | 45183.4673 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45174.5827 | 45170.6049 | 45181.3217 | 45519.4588 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000331002 | AL, Barry S.P. Unit 6 & 8, repair bad fiber cable | Low | Successful | Minor | Planned | DHA | TT | 45170.4772 | 45180.7917 | 45181 | 45180.7944 | 45180.9806 | 45181.3848 | 45181.385 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45174.582 | 45170.5763 | 45180.7799 | 45519.4679 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000331107 | GA, Kettle Creek Transport, NOKIA SAR, OS Bootloader Mismatch, requires update/reboot | Low | Successful | Minor | Planned | MPH | TT | 45170.5048 | 45180.4167 | 45180.5 | 45180.4167 | 45180.4653 | 45180.5928 | 45180.5937 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Repair | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45174.5799 | 45170.5739 | 45180.4003 | 45180.5937 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000331113 | AL, Autaugaville EBTS A9335, performing tower modification for CBRS. | Low | Successful | Minor | Planned | CDL | TT | 45170.6261 | 45182.375 | 45184.8333 | 45182.375 | 45184.8333 | 45187.4439 | 45187.4439 | 2023 | 2023-09 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45174.5771 | 45174.5576 | 45182.3634 | 45187.4439 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000331115 | AL, Columbia, EBTS/COAM A9488 Plant Farley, performing tower modification for CBRS | Low | Successful | Minor | Planned | CDL | TT | 45170.6274 | 45180.375 | 45184.3333 | 45180.375 | 45184.3333 | 45187.4428 | 45187.4429 | 2023 | 2023-09 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45174.5778 | 45174.5564 | 45180.3586 | 45187.4429 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332115 | AL and GA, Various sites, Nokia Transport, Configure new PTP timing protocol. | Low | Successful | Minor | Planned | TSE | TT | 45174.4689 | 45187.4167 | 45190.9167 | 45187.4167 | 45190.5333 | 45190.5657 | 45190.5658 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45181.2868 | 45177.4273 | 45187.4049 | 45341.1766 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332126 | GA, Macon, Lumen will be splicing fibers on the A to J route. | Low | Successful | Minor | Planned | SDG | TT | 45174.5866 | 45187.9167 | 45188.25 | 45187.9931 | 45188.0347 | 45188.4022 | 45188.4023 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45181.2865 | 45177.43 | 45187.9056 | 45188.4023 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332511 | GA, Ochlocknee ENODEB, Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45176.4952 | 45182.4167 | 45182.7083 | 45182.4167 | 45182.7083 | 45183.4678 | 45183.4678 | 2023 | 2023-09 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45177.5657 | 45177.4216 | 45182.4051 | 45183.4678 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332516 | AL, Birmingham ICON Ring, Build ethernet from APCO to No Side COLO | Low | Successful | Minor | Planned | RPY | TT | 45176.5164 | 45183.5 | 45183.5833 | 45183.5 | 45183.5833 | 45184.4344 | 45184.4345 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45181.2871 | 45177.4235 | 45183.4884 | 45340.9658 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332720 | GA, MACON, KEY ST DCC, GENERATOR REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45176.5617 | 45187.375 | 45192.7083 | 45187.375 | 45192.7083 | 45194.4264 | 45194.4265 | 2023 | 2023-09 | Successful | Facilities Component | Generator | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45177.5677 | 45177.4252 | 45187.3633 | 45498.7092 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000332728 | MS, Logtown East & MPC OPS, Nokia Transport, Configure new PTP timing. | Low | Successful | Minor | Planned | TSE | TT | 45176.7094 | 45190.4167 | 45190.9167 | 45190.4167 | 45190.559 | 45190.569 | 45190.5692 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45180.6926 | 45177.4487 | 45190.4044 | 45341.1766 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000333014 | AL, Delta EBTS A9128 Cheaha, adding CBRS to the site | Low | Successful | Minor | Planned | CDL | TT | 45177.587 | 45187.4583 | 45191.7917 | 45187.4583 | 45191.7917 | 45194.4547 | 45194.4549 | 2023 | 2023-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45180.6995 | 45180.5906 | 45187.4466 | 45194.4549 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334217 | GA, Tallulah Falls Intake Building, move 12 fiber cable | Medium | Successful | Moderate | Unplanned | MAR | TT | 45181.8468 | 45188.3333 | 45188.75 | 45188.434 | 45188.5813 | 45188.6435 | 45188.6454 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45188.4083 | 45183.554 | 45188.4196 | 45519.4626 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334422 | GA, HENRY COUNTY CCC, UPS REPLACEMENT/COMMISSIONING | Low | Successful | Minor | Planned | MVW | TT | 45182.6471 | 45199.25 | 45199.75 | 45199.3514 | 45199.7257 | 45200.8262 | 45200.8263 | 2023 | 2023-10 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45183.5881 | 45183.5513 | 45199.2313 | 45498.7092 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000334426 | GA, Plant Hatch to Offerman, splicing new Lumen fiber route (EMERGENCY) | Low | Successful | Minor | Planned | TAT | TT | 45182.6727 | 45183.9993 | 45184.2083 | 45183.9993 | 45184.0757 | 45184.4251 | 45184.4319 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | TAT | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45182.7065 | 45182.6937 | 45183.9876 | 45184.4319 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334609 | GA, Savannah ICON Ring, Turn ports up for SWAN to DHA & LFL | Low | Successful | Minor | Planned | RPY | TT | 45183.4223 | 45196.4167 | 45196.5417 | 45196.4194 | 45196.6139 | 45197.4359 | 45197.4361 | 2023 | 2023-09 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.6869 | 45183.5493 | 45196.4051 | 45340.9658 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334631 | AL, Maxwell AFB, Migrate leased circuit to new AT&T ASEoD service. (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45183.6897 | 45196.4167 | 45196.4583 | 45196.4167 | 45196.4583 | 45196.6233 | 45196.6234 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45187.4663 | 45184.6057 | 45196.4051 | 45196.6234 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334633 | GA, Senoia, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45183.7695 | 45204.375 | 45204.5417 | 45204.375 | 45204.4979 | 45204.5892 | 45204.5893 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45197.605 | 45196.6296 | 45204.3619 | 45204.5893 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000334635 | GA, Kennesaw, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45183.778 | 45196.4583 | 45196.5 | 45196.4583 | 45196.5 | 45196.5367 | 45196.5368 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45187.702 | 45187.472 | 45196.4468 | 45196.5368 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000334637 | GA, Kellytown, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45183.7842 | 45204.375 | 45204.5417 | 45204.375 | 45204.4993 | 45204.5879 | 45204.588 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45197.6048 | 45196.6286 | 45204.3619 | 45204.588 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000334640 | AL, North Borden Springs, Migrate leased circuit to new AT&T ASEoD service. (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45183.85 | 45195.4583 | 45195.5 | 45195.4583 | 45195.5 | 45196.4116 | 45196.4117 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45187.4647 | 45187.4484 | 45195.4474 | 45196.4117 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000335001 | AL, Batesville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45186.4066 | 45201.375 | 45201.5 | 45201.375 | 45201.5 | 45201.6201 | 45201.6203 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45187.7034 | 45187.4891 | 45201.3619 | 45201.6203 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335100 | AL, Midway ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45186.4282 | 45201.5417 | 45201.6667 | 45201.5417 | 45201.6667 | 45202.3852 | 45202.3862 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45187.7034 | 45187.4897 | 45201.5285 | 45202.3862 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335323 | AL, Tuscaloosa EBTS A9223 South Tuscaloosa, adding CBRS | Low | Successful | Minor | Planned | CDL | TT | 45187.6375 | 45190.375 | 45191.8333 | 45190.375 | 45191.8333 | 45194.4576 | 45194.4577 | 2023 | 2023-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45187.7034 | 45187.6467 | 45190.3627 | 45194.4577 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000335509 | GA, Savannah ICON Ring, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45188.5358 | 45208.375 | 45208.7083 | 45208.375 | 45208.7125 | 45208.8217 | 45208.8285 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7151 | 45190.5842 | 45208.3619 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335511 | GA, Atlanta ICON Ring, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45188.5398 | 45209.4583 | 45209.7083 | 45209.4583 | 45209.6625 | 45210.4264 | 45210.4298 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7173 | 45190.5928 | 45209.4453 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335515 | GA, Bowen-Big Shanty, 2 Bainbridge ICON Server upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45188.5488 | 45211.3958 | 45211.7083 | 45211.3958 | 45211.7083 | 45212.4184 | 45212.4192 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7206 | 45190.6 | 45211.3776 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335524 | GA, Atlanta Motor Speedway ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45188.6343 | 45198.5833 | 45198.7083 | 45198.5833 | 45198.7083 | 45200.8302 | 45200.8303 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45190.5283 | 45190.4669 | 45198.5702 | 45200.8303 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335615 | GA, North Georgia ICON Ring, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45188.5438 | 45210.3958 | 45210.7083 | 45210.3958 | 45210.6701 | 45210.689 | 45210.693 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45198.5773 | 45197.4405 | 45210.38 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335619 | GA, Jonesboro ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45188.5629 | 45198.4167 | 45198.5417 | 45198.4167 | 45198.5417 | 45200.829 | 45200.8291 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45190.5273 | 45190.465 | 45198.4053 | 45200.8291 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335626 | GA, McDonough ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45188.6257 | 45198.5 | 45198.625 | 45198.5 | 45198.625 | 45200.8296 | 45200.8297 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45190.5277 | 45190.4662 | 45198.4887 | 45200.8297 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335629 | AL, Trussville, Splicing dark fiber for CSpire handoff. | Low | Successful | Minor | Planned | RCA | TT | 45188.6788 | 45195.2917 | 45196.75 | 45195.2917 | 45196.75 | 45197.4706 | 45197.4707 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45190.5225 | 45190.4573 | 45195.2807 | 45519.4588 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000335630 | AL, Geneva EBTS A9153, adding CBRS to the existing Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45188.6798 | 45208.4583 | 45212.8333 | 45208.4583 | 45212.8333 | 45215.3904 | 45215.3905 | 2023 | 2023-10 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45191.706 | 45191.4585 | 45208.4453 | 45215.3905 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000335632 | AL, Trussville, Splicing dark fiber for CSpire Handoff | Low | Successful | Minor | Planned | RCA | TT | 45188.7007 | 45195.7917 | 45196.75 | 45195.2917 | 45196.75 | 45197.471 | 45197.4711 | 2023 | 2023-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45190.5252 | 45190.4626 | 45195.78 | 45519.4588 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000336202 | GA, Lafayette EBTS G9223, Taylor Ridge, migrating LTE from old tower to new tower | Low | Successful | Minor | Planned | CDL | TT | 45189.4643 | 45196.375 | 45198.8333 | 45196.375 | 45198.8333 | 45200.8278 | 45200.8279 | 2023 | 2023-10 | Successful | Transport Device | Antenna System | Migrate | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45190.5262 | 45190.4634 | 45196.3634 | 45200.8279 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336211 | AL, Birmingham ICON Ring, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45189.6144 | 45210.3958 | 45210.7083 | 45210.3958 | 45210.6701 | 45210.69 | 45210.6922 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7203 | 45190.5979 | 45210.38 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336213 | AL, Snowdoun, Green County and Barry ICON Rings, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45189.6269 | 45208.3958 | 45208.7083 | 45208.3972 | 45208.7125 | 45208.8225 | 45208.8286 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7161 | 45190.5851 | 45208.3758 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336215 | AL, Anniston - Gorgas - Holt- Clay ICON Ring, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45189.6346 | 45209.4583 | 45209.7083 | 45209.4583 | 45209.6632 | 45210.4278 | 45210.4296 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7211 | 45190.5885 | 45209.4453 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336220 | AL, White Plains LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45189.6392 | 45195.5 | 45195.5417 | 45195.5 | 45195.5417 | 45196.412 | 45196.4121 | 2023 | 2023-09 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45190.5241 | 45190.4615 | 45195.4891 | 45196.4121 | 2023-Q3 | 2023-09 | 2023-Q3
CRQ000000336403 | MS, Pascagoula and Hattiesburg ICON Rings, Server firmware upgrades | Medium | Successful | Moderate | Planned | RPY | TT | 45189.6185 | 45210.3958 | 45210.7083 | 45210.3958 | 45210.6701 | 45210.6909 | 45210.6921 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.7187 | 45190.5965 | 45210.38 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336606 | AL, Dadeville Substation, Cutting new OLT into fiber ERPS | Low | Unsuccessful | Minor | Planned | JGL | TT | 45190.437 | 45208.4167 | 45208.5417 | 45208.4271 | 45208.5444 | 45208.8279 | 45208.8287 | 2023 | 2023-10 | Unsuccessful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.5005 | 45190.5864 | 45208.4036 | 45208.8287 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336607 | AL, Dadeville Substation, Cutting new OLT into fiber ERPS (BACKUP DATE) | Low | Successful | Minor | Planned | JGL | TT | 45190.4371 | 45211.4167 | 45211.5417 | 45211.4201 | 45211.65 | 45212.4436 | 45212.4437 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45194.5007 | 45190.587 | 45211.4054 | 45212.4437 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000336804 | GA, Holcomb Bridge ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45191.4626 | 45201.625 | 45201.75 | 45201.625 | 45201.75 | 45202.386 | 45202.3861 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45197.6062 | 45196.6363 | 45201.6119 | 45202.3861 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337005 | GA, Eastside Cobb ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45191.4519 | 45201.375 | 45201.5 | 45201.375 | 45201.5 | 45201.6196 | 45201.6197 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45197.6056 | 45196.6345 | 45201.3619 | 45201.6197 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337007 | GA, Bull Sluice ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45191.4575 | 45201.5 | 45201.625 | 45201.5 | 45201.625 | 45202.3847 | 45202.3848 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45197.606 | 45196.6356 | 45201.4869 | 45202.3848 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337507 | AL and GA Various Ciena 6500 Circuit Cuts Ring 3N | Low | Successful | Minor | Planned | GPB | TT | 45194.4259 | 45202.75 | 45203 | 45202.75 | 45202.8208 | 45203.4351 | 45203.4352 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45198.5543 | 45196.6396 | 45202.7383 | 45203.4352 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337516 | GA, Manchester, Transmission ROW, Splice fiber into substation for SAR connection | Low | Successful | Minor | Planned | JLM | TT | 45194.5909 | 45203.75 | 45203.9993 | 45203.75 | 45203.8229 | 45204.4327 | 45204.4327 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45198.5551 | 45198.4599 | 45203.7369 | 45519.4626 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337810 | FL, Sneads ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45195.5087 | 45203.4167 | 45203.5417 | 45203.4167 | 45203.5417 | 45204.4306 | 45204.4307 | 2023 | 2023-10 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45197.6078 | 45197.4421 | 45203.405 | 45204.4307 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000337932 | AL, Shoal Creek LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45195.6404 | 45210.375 | 45210.5417 | 45210.375 | 45210.5417 | 45210.6976 | 45210.6989 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45198.603 | 45197.4529 | 45210.3661 | 45210.6989 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338012 | AL, Woodlawn, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45195.6529 | 45210.375 | 45210.5417 | 45210.375 | 45210.5417 | 45210.6967 | 45210.697 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45198.6053 | 45197.455 | 45210.3661 | 45210.697 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338014 | AL, Vestavia, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45195.6595 | 45210.375 | 45210.5417 | 45210.375 | 45210.5417 | 45210.6942 | 45210.6958 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45198.6023 | 45197.4475 | 45210.3661 | 45210.6958 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338122 | AL, Auburn, Moving PON to combo card | Low | Successful | Minor | Planned | ALL | TT | 45196.6559 | 45203.5833 | 45203.6667 | 45203.5854 | 45203.6618 | 45204.432 | 45204.4322 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | AC | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45198.602 | 45197.4453 | 45203.5702 | 45204.4322 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338312 | GA, Eagles Landing LTE site, MTU Setting change | Low | Successful | Minor | Planned | DRI | TT | 45196.6593 | 45203.4375 | 45203.4583 | 45203.4375 | 45203.4514 | 45204.4312 | 45204.4313 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45198.6013 | 45197.4431 | 45203.4189 | 45204.4313 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338515 | GA, Norwood, Transmission ROW, Repair damaged section of OPGW | Medium | Successful | Moderate | Planned | JLM | TT | 45197.7007 | 45206.3333 | 45206.75 | 45206.3333 | 45206.6062 | 45208.3997 | 45208.4003 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45198.577 | 45198.4631 | 45206.3203 | 45519.4626 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338815 | MS, Necaise EBTS, Modify DC bus to reflect proper amp draw. | Low | Successful | Minor | Planned | RBK | TT | 45198.5601 | 45208.4167 | 45208.5 | 45208.4167 | 45208.5 | 45208.8293 | 45208.8304 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45201.6177 | 45201.6078 | 45208.4036 | 45208.8304 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338817 | MS, Wiggins EBTS, modify rectifier plant to reflect correct amp draw. | Low | Successful | Minor | Planned | RBK | TT | 45198.5746 | 45209.4167 | 45209.5 | 45209.4167 | 45209.5 | 45210.433 | 45210.4332 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45201.6181 | 45201.6109 | 45209.4036 | 45210.4332 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338825 | AL, Safford EBTS, Upgrade Ericsson Microwave Path to Catherine | Low | Successful | Minor | Planned | JEN | TT | 45198.7561 | 45209.2917 | 45209.7917 | 45209.2917 | 45209.7917 | 45210.4315 | 45210.4317 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45204.6816 | 45204.5763 | 45209.2786 | 45519.4508 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338827 | AL, Pine Hill EBTS, Upgrade Ericsson Microwave Path to Catherine | Low | Successful | Minor | Planned | JEN | TT | 45198.7641 | 45210.2917 | 45210.7917 | 45210.4306 | 45210.7556 | 45211.382 | 45211.3821 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45204.6826 | 45204.5792 | 45210.2828 | 45519.4508 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338901 | AL, Montgomery, J St Transport, retrieve OTDR traces on outside plant fiber | Medium | Successful | Moderate | Unplanned | ADL | TT | 45198.4357 | 45201.7083 | 45202 | 45201.784 | 45202 | 45202.3867 | 45202.3876 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45198.6333 | 45198.4583 | 45201.6952 | 45202.3876 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338915 | AL, Massey DS, cut and splice protection ring fibers | Low | Successful | Minor | Planned | DWM | TT | 45198.7085 | 45225.7917 | 45226.1667 | 45225.8361 | 45226.1667 | 45229.3823 | 45229.3824 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45202.4646 | 45201.617 | 45225.7786 | 45519.4679 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338916 | AL, Massey DS, cut and splice protection ring fibers (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45198.7086 | 45232.7917 | 45233.1667 | 45232.7917 | 45233.1667 | 45233.4108 | 45233.4109 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45202.4646 | 45201.6176 | 45232.7786 | 45519.4679 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000338917 | AL, Pine Hill EBTS, Upgrade Ericsson Microwave Path to South Thomasville | Low | Successful | Minor | Planned | JEN | TT | 45198.7748 | 45216.2917 | 45216.7917 | 45216.2917 | 45216.7917 | 45217.5733 | 45217.5741 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45204.6853 | 45204.5831 | 45216.2786 | 45519.4508 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338919 | AL, South Thomasville EBTS, Upgrade Microwave Path to Thomasville | Low | Successful | Minor | Planned | JEN | TT | 45198.7791 | 45217.2917 | 45217.7917 | 45217.2917 | 45217.7917 | 45218.5194 | 45218.521 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45204.6862 | 45204.5844 | 45217.2794 | 45519.4508 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000338923 | AL, Thomasville EBTS, Upgrade Microwave Path to Dixon Mill | Low | Successful | Minor | Planned | JEN | TT | 45198.7943 | 45218.2917 | 45218.7917 | 45218.4049 | 45218.6139 | 45222.4007 | 45222.4008 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45204.6883 | 45204.5859 | 45218.28 | 45519.4508 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339205 | GA, Jackson and Manchester, Ciena 6500 Upgrade to MLA-2 AMP | Low | Successful | Minor | Planned | GPB | TT | 45201.4718 | 45215.75 | 45216 | 45215.7917 | 45215.8465 | 45216.3931 | 45216.3938 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45208.904 | 45202.6707 | 45215.7369 | 45216.3938 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339309 | AL, N Auburn, SDC, & J St, Ciena 6500 Upgrade AMP Configuration. | Low | Successful | Minor | Planned | GPB | TT | 45201.5067 | 45218.75 | 45219 | 45218.75 | 45218.9042 | 45222.4028 | 45222.4029 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45208.9041 | 45202.6738 | 45218.7383 | 45222.4029 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339407 | GA, Columbus and Manchester, Ciena 6500 Upgrade to MLA-2 AMP | Low | Successful | Minor | Planned | GPB | TT | 45201.4816 | 45216.75 | 45217 | 45216.75 | 45217 | 45217.5786 | 45217.5789 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45208.9041 | 45202.672 | 45216.7376 | 45217.5789 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339408 | AL & GA, N Auburn and Columbus, Ciena 6500 Upgrade AMP Configuration | Low | Successful | Minor | Planned | GPB | TT | 45201.4948 | 45217.75 | 45218 | 45217.75 | 45218 | 45218.5233 | 45218.524 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45208.904 | 45202.6729 | 45217.7383 | 45218.524 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339518 | AL, Mobile, Splicing Mobile North Connector to West Mobile loop | Low | Successful | Minor | Planned | RCA | TT | 45202.6772 | 45210.3333 | 45211.7917 | 45211.4299 | 45211.534 | 45212.4402 | 45212.4403 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45208.5276 | 45202.6885 | 45210.3245 | 45519.4588 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339521 | GA, Cartersville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45202.7344 | 45212.5 | 45212.6667 | 45212.5 | 45212.6667 | 45215.392 | 45215.392 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.4949 | 45205.4599 | 45212.4888 | 45215.392 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339605 | GA, Atlanta, East Atlanta ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45202.5627 | 45211.3333 | 45211.5 | 45211.3333 | 45211.5 | 45212.4408 | 45212.4409 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45203.4474 | 45202.6615 | 45211.3217 | 45212.4409 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339607 | GA, Panthersville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45202.5796 | 45211.5 | 45211.6667 | 45211.5 | 45211.6667 | 45212.4445 | 45212.4446 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45203.4477 | 45202.6621 | 45211.4888 | 45212.4446 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339728 | GA, Mossy Branch, New NOKIA SAR, Add to Transport Network | Low | Successful | Minor | Planned | TSE | TT | 45202.5951 | 45216.4167 | 45216.9167 | 45216.4236 | 45216.7194 | 45217.5696 | 45217.5697 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | TLS | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45208.904 | 45202.6753 | 45216.4036 | 45341.1766 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339739 | GA, White ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45202.7278 | 45212.3333 | 45212.5 | 45212.3333 | 45212.5 | 45215.3914 | 45215.3916 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.4937 | 45205.4593 | 45212.3221 | 45215.3916 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339740 | MS, MOSS POINT, ITC DELTACOM HUT, REPLACE STAND BY GENERATOR ATS | Low | Successful | Minor | Planned | SEV | TT | 45202.8002 | 45211.375 | 45211.7917 | 45211.375 | 45211.6757 | 45212.4415 | 45212.4416 | 2023 | 2023-10 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | SE | SCS | INFRASTRUCTURE SERVICES | FO MS FIBER OPS AND PROJECTS | 45204.6846 | 45204.5816 | 45211.3635 | 45519.4714 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339809 | GA, Locust Grove ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45203.4697 | 45215.5 | 45215.6667 | 45215.5 | 45215.6667 | 45215.7212 | 45215.7217 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.629 | 45205.4613 | 45215.4883 | 45215.7217 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000339820 | GA, Shannon ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45203.5898 | 45219.5 | 45219.6667 | 45219.5 | 45219.6667 | 45222.4053 | 45222.4054 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.4954 | 45205.4626 | 45219.4884 | 45222.4054 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340010 | GA, Atlanta Motor Speedway ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45203.458 | 45215.3333 | 45215.5 | 45215.334 | 45215.3917 | 45215.7165 | 45215.7168 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.6289 | 45205.4606 | 45215.3216 | 45215.7168 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340029 | GA, Adairsville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45203.5833 | 45219.3333 | 45219.5 | 45219.3333 | 45219.5 | 45222.4048 | 45222.4049 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45205.4957 | 45205.462 | 45219.3217 | 45222.4049 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340042 | AL, Wilsonville and J St, Ciena module add and Nokia circuit turn down. | Low | Successful | Minor | Planned | GPB | TT | 45203.7112 | 45210.75 | 45210.9583 | 45210.75 | 45211 | 45211.3828 | 45211.3829 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45208.9041 | 45205.4579 | 45210.7383 | 45211.3829 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340134 | GA, NW Pine Mountain ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45204.7823 | 45216.5417 | 45216.7083 | 45216.5417 | 45216.7083 | 45217.5772 | 45217.5774 | 2023 | 2023-10 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45212.7157 | 45210.4941 | 45216.5292 | 45217.5774 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340223 | AL, Phenix City, Phenix City ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45204.7184 | 45216.375 | 45216.7083 | 45216.375 | 45216.7083 | 45217.576 | 45217.5767 | 2023 | 2023-10 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45208.5248 | 45208.4833 | 45216.3619 | 45217.5767 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340319 | AL, Fitzpatrick ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45204.7901 | 45218.375 | 45218.7083 | 45218.375 | 45218.7083 | 45222.4021 | 45222.4022 | 2023 | 2023-10 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45208.5255 | 45208.4858 | 45218.3633 | 45222.4022 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340407 | GA, East Dallas, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45205.4319 | 45215.4167 | 45215.5 | 45215.4299 | 45215.5 | 45215.7177 | 45215.7183 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45208.5241 | 45208.4808 | 45215.4049 | 45215.7183 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340413 | GA, Savannah ICON Ring, PLM firmware upgrade on all nodes | Low | Successful | Minor | Planned | RPY | TT | 45205.5092 | 45230.3958 | 45230.7083 | 45230.3958 | 45230.7083 | 45231.4382 | 45231.4383 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.904 | 45208.4867 | 45230.3773 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340416 | GA, Atlanta ICON Ring, PLM firmware upgrade on all nodes | Low | Successful | Minor | Planned | RPY | TT | 45205.5228 | 45231.3958 | 45231.7083 | 45231.3958 | 45231.6056 | 45232.4118 | 45232.412 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.9041 | 45208.4881 | 45231.3766 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340418 | GA, N GA ICON Ring, Bainbridge, Bowen & Shanty PLM Upgrades | Low | Successful | Minor | Planned | RPY | TT | 45205.5355 | 45232.3958 | 45232.7083 | 45232.4083 | 45232.6 | 45233.408 | 45233.4081 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.904 | 45208.4895 | 45232.3779 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340422 | AL, BHM Gorgas, Anniston ICON Ring, Leeds/Clay, PLM firmware upgrade on all nodes | Low | Successful | Minor | Planned | RPY | TT | 45205.5607 | 45236.3958 | 45236.7083 | 45236.3986 | 45236.6097 | 45237.3834 | 45237.3835 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.904 | 45208.4911 | 45236.3758 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340425 | AL, Green County/Barry, Tuscaloosa & Southern ICON Ring, PLM firmware upgrade on all nodes | Low | Successful | Minor | Planned | RPY | TT | 45205.5709 | 45237.3958 | 45237.7083 | 45237.4299 | 45237.7083 | 45238.3974 | 45238.3975 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.9033 | 45208.4924 | 45237.3765 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340426 | AL, Green County/Barry, Tuscaloosa & Southern ICON Ring, PLM firmware upgrade on all nodes (BACKUP) | Low | Successful | Minor | Unplanned | RPY | TT | 45205.5709 | 45238.4375 | 45238.5 | 45238.4521 | 45238.5076 | 45240.3826 | 45240.3827 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45238.4187 | 45238.4185 | 45238.4322 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340602 | AL, Paint Rock LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45205.4414 | 45215.4583 | 45215.5417 | 45215.4583 | 45215.5417 | 45215.7195 | 45215.7206 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45208.5262 | 45208.482 | 45215.4466 | 45215.7206 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340609 | MS, Hattiesburg and Pascagoula PLM upgrades on all nodes | Low | Successful | Minor | Planned | RPY | TT | 45205.5757 | 45238.3958 | 45238.7083 | 45238.4 | 45238.5076 | 45240.3833 | 45240.3834 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45208.9033 | 45208.4938 | 45238.3766 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000340907 | GA, Macon, NW Macon ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45208.5533 | 45215.4167 | 45215.5 | 45215.4236 | 45215.4819 | 45215.7189 | 45215.7208 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45212.5427 | 45210.4352 | 45215.4049 | 45215.7208 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340914 | GA, LTE router software update & reboot | Medium | Successful | Moderate | Planned | DRI | TT | 45208.6471 | 45216.9583 | 45217.041 | 45216.9583 | 45217.041 | 45217.5715 | 45217.5726 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45212.5545 | 45210.4925 | 45216.946 | 45217.5726 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340916 | GA, LTE router software update & reboot | Medium | Successful | Moderate | Planned | DRI | TT | 45208.6705 | 45217.9583 | 45218.041 | 45217.9583 | 45218.041 | 45218.4522 | 45218.4527 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45212.5538 | 45210.4932 | 45217.9466 | 45218.4527 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340917 | GA, LTE router software update & reboot | Low | Successful | Minor | Planned | DRI | TT | 45208.6742 | 45215.9583 | 45216.041 | 45215.9583 | 45216.0208 | 45216.3943 | 45216.3944 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45212.5434 | 45210.4917 | 45215.9452 | 45216.3944 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340924 | AL, Guin, Yampertown LTE, repair or replace SAU or BB chassis due to alarm issues. | Low | Successful | Minor | Planned | RBK | TT | 45208.9015 | 45219.5424 | 45219.625 | 45219.5424 | 45219.7389 | 45222.3938 | 45222.3939 | 2023 | 2023-10 | Successful | Transport Device | Synchronization Equipment | Repair | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45212.5934 | 45210.4985 | 45219.5299 | 45222.3939 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000340926 | AL, Clanton, Lay Dam LTE, upgrade AC input ckts to allow for 75 amp rectifiers. | Low | Successful | Minor | Planned | RBK | TT | 45208.9187 | 45223.375 | 45223.7083 | 45223.375 | 45223.7083 | 45224.6081 | 45224.6083 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45212.7191 | 45210.5097 | 45223.3557 | 45224.6083 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341010 | GA, Gray ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45208.5605 | 45215.5833 | 45215.6667 | 45215.5833 | 45215.6667 | 45215.7221 | 45215.7224 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45212.7157 | 45210.4358 | 45215.5702 | 45215.7224 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341109 | GA, No GA ICON Ring, Tallulah Lodge #1, WAN port build for iSTAR | Medium | Successful | Moderate | Planned | RPY | TT | 45208.592 | 45222.4167 | 45222.6667 | 45222.4167 | 45222.5771 | 45222.6065 | 45222.6104 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45210.5621 | 45210.5061 | 45222.4042 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341110 | GA, No GA ICON Ring, Tallulah Lodge #1, WAN port build for iSTAR (BACKUP DATE) | Medium | Successful | Moderate | Planned | RPY | TT | 45208.5921 | 45223.4167 | 45223.6667 | 45223.4167 | 45223.6667 | 45224.6093 | 45224.611 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45210.5621 | 45210.5067 | 45223.4091 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341225 | GA, Atlanta, College Park ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45209.6623 | 45217.5 | 45217.6667 | 45217.5 | 45217.6667 | 45218.5229 | 45218.5237 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45212.7164 | 45210.4976 | 45217.4878 | 45218.5237 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341226 | AL, Irondale, relocate fiber cable for Lumen Night 2 | Low | Successful | Minor | Planned | DWM | TT | 45209.6639 | 45233 | 45233.2917 | 45233 | 45233.2917 | 45233.4114 | 45233.4115 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45210.5232 | 45210.5125 | 45232.9869 | 45519.4679 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000341228 | GA, Various Sites, Ciena 6500 Software Upgrades | Medium | Successful | Moderate | Planned | ADL | TT | 45209.6778 | 45222.7917 | 45223 | 45222.7917 | 45223 | 45223.4969 | 45223.499 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45215.3337 | 45210.5081 | 45222.7723 | 45223.499 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341229 | GA, Various Sites, Ciena 6500 Software Upgrades (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45209.6778 | 45229.7917 | 45230 | 45229.7917 | 45230 | 45230.3965 | 45230.3972 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45215.3342 | 45210.5086 | 45229.78 | 45230.3972 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341415 | AL, Irondale, relocate fiber cable for Lumen Night 1 | Low | Successful | Minor | Planned | DWM | TT | 45209.6431 | 45232 | 45232.2917 | 45232 | 45232.1979 | 45232.4176 | 45232.4177 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45210.5239 | 45210.5113 | 45231.989 | 45519.4679 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000341417 | GA, Atlanta, Cleveland Ave ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45209.6552 | 45217.375 | 45217.5 | 45217.375 | 45217.5 | 45218.5218 | 45218.5236 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45212.7164 | 45210.497 | 45217.3627 | 45218.5236 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341811 | GA, Conyers, Flovilla, Splicing two dark fibers | Low | Successful | Minor | Planned | SDG | TT | 45211.5909 | 45218.9583 | 45219.25 | 45218.9583 | 45219.0375 | 45222.4035 | 45222.4036 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45212.7184 | 45212.4393 | 45218.9467 | 45222.4036 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341812 | AL/GA, Various Sites, Ciena 6500 Software Upgrades | Low | Successful | Minor | Planned | ADL | TT | 45211.5978 | 45231.75 | 45232 | 45231.75 | 45232 | 45232.4165 | 45232.4167 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45223.6012 | 45223.5619 | 45231.7389 | 45232.4167 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000341813 | AL, Various Sites, Ciena 6500 Software Upgrades | Low | Successful | Minor | Planned | ADL | TT | 45211.6079 | 45232.75 | 45233 | 45232.75 | 45233 | 45233.4103 | 45233.4104 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45218.5273 | 45217.5875 | 45232.7369 | 45233.4104 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000341819 | GA, Campbell Rd, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45211.6339 | 45224.4167 | 45224.5417 | 45224.4167 | 45224.5417 | 45225.3974 | 45225.3975 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45216.4123 | 45215.7008 | 45224.4036 | 45225.3975 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341908 | GA, Various Sites. Ciena 6500 Software Upgrades | Low | Successful | Minor | Planned | ADL | TT | 45211.4641 | 45223.75 | 45224 | 45223.75 | 45224 | 45224.6099 | 45224.6101 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45216.4134 | 45215.5517 | 45223.7369 | 45224.6101 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341917 | AL, Birmingham ICON Ring, Massey Rd ICON node insertion | Medium | Successful | Moderate | Planned | RPY | TT | 45211.5812 | 45229.4167 | 45229.6667 | 45229.4167 | 45229.6667 | 45230.3921 | 45230.3936 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45219.3793 | 45216.6521 | 45229.4036 | 45340.9658 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341919 | AL/MS, Various Sites, Ciena 6500 Software Upgrades | Low | Successful | Minor | Planned | ADL | TT | 45211.5869 | 45229.75 | 45230 | 45229.75 | 45230 | 45230.3951 | 45230.3954 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45218.5273 | 45216.6544 | 45229.7383 | 45230.3954 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341924 | GA, Porterdale, Flovilla, splicing two dark fibers | Low | Successful | Minor | Planned | SDG | TT | 45211.6101 | 45222.9583 | 45223.25 | 45222.9819 | 45223.0194 | 45223.5014 | 45223.5015 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45218.86 | 45215.5496 | 45222.939 | 45223.5015 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000341930 | AL, Various sites LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Unsuccessful | Minor | Planned | JHW | TT | 45211.6935 | 45224.4167 | 45224.5417 | 45224.4236 | 45224.6375 | 45225.3961 | 45225.3962 | 2023 | 2023-10 | Unsuccessful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45216.4116 | 45215.6991 | 45224.4036 | 45225.3962 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342007 | GA, Macon, Key St EBTS/Transport, Change Modulation on Nokia MPR to Round Oak | Low | Successful | Minor | Planned | JWH | TT | 45211.4436 | 45222.5 | 45222.5833 | 45222.5 | 45222.5097 | 45222.6033 | 45222.6034 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JAW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45216.4314 | 45216.4191 | 45222.4876 | 45222.6034 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342011 | GA, Various Sites, Ciena 6500 Software Upgrades | Low | Successful | Minor | Planned | ADL | TT | 45211.4748 | 45225.75 | 45226 | 45225.75 | 45226 | 45229.3809 | 45229.3818 | 2023 | 2023-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45218.5259 | 45216.532 | 45225.7369 | 45229.3818 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342607 | GA, Riverdale ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45215.4311 | 45222.4167 | 45222.5 | 45222.4187 | 45222.4924 | 45222.8414 | 45222.8416 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45216.4105 | 45215.6973 | 45222.4042 | 45222.8416 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342608 | GA, Forsyth ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45215.4356 | 45222.5833 | 45222.6667 | 45222.5833 | 45222.6431 | 45222.8423 | 45222.8425 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45216.4131 | 45215.6978 | 45222.5716 | 45222.8425 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342617 | TEST CASE FOR SMART IT FOR ECM CHANGE MANAGEMENT | Low | Successful | Minor | Unplanned | TAT | TT | 45215.5785 | 45215.6667 | 45217.75 | 45215.6667 | 45215.6701 | 45215.6723 | 45215.675 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | TAT | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45215.6604 | 45215.6592 | 45215.6674 | 45215.675 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342705 | AL, Moody EBTS A9111 Bald Rock, CBRS is being added to the existing Skymounts. | Low | Successful | Minor | Planned | CDL | TT | 45215.4221 | 45243.4583 | 45247.7917 | 45243.4583 | 45247.2917 | 45251.4106 | 45251.4107 | 2023 | 2023-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45218.5287 | 45218.4485 | 45243.4467 | 45251.4107 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000342813 | AL, Auburn EBTS adding Auburn Tech Park to middle of MW path | Low | Successful | Minor | Planned | CDL | TT | 45215.734 | 45224.375 | 45226.3333 | 45224.375 | 45226.3333 | 45229.3794 | 45229.3803 | 2023 | 2023-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45218.5238 | 45216.5283 | 45224.3619 | 45229.3803 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000342814 | AL, Auburn EBTS adding Auburn Tech Park to middle of MW path (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45215.735 | 45229.375 | 45233.8333 | 45233.5229 | 45233.6708 | 45236.3854 | 45236.3856 | 2023 | 2023-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45218.5245 | 45216.5301 | 45229.3619 | 45236.3856 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343012 | TEST------GA, Various Sites. Ciena 6500 Software Upgrades | Low | Successful | Minor | Unplanned | TAT | TT | 45216.5488 | 45216.5694 | 45216.5764 | 45216.5694 | 45216.5764 | 45216.5778 | 45216.5787 | 2023 | 2023-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | TAT | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45216.5629 | 45216.5621 | 45216.5709 | 45216.5787 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000343025 | AL, GA, MS, All Linc RAN Sites Systemwide, LTE Uplink and Downlink Parameter Change. | Medium | Successful | Moderate | Planned | MJR | TT | 45216.7639 | 45231.5 | 45232.25 | 45231.5 | 45232.25 | 45232.4153 | 45232.4188 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45219.671 | 45218.6387 | 45231.4877 | 45232.4188 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343026 | AL, BESSEMER, 150 LEAF LAKE PKWY, TELECOM ROOM A & B, BATTERY AND AC POWER ADD | Medium | Successful | Moderate | Planned | MVW | TT | 45216.7759 | 45236.3333 | 45237.7083 | 45236.3333 | 45237.7083 | 45238.3962 | 45238.3985 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45229.5197 | 45229.3855 | 45236.3202 | 45498.7092 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343207 | GA, Franklin ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.5288 | 45264.4167 | 45264.5 | 45264.4514 | 45264.4736 | 45264.6438 | 45264.6439 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45246.6806 | 45246.4623 | 45264.3966 | 45264.6439 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000343215 | GA, Atlanta Gwinnett Place ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.6929 | 45233.3542 | 45233.5208 | 45233.3542 | 45233.5208 | 45236.4025 | 45236.4027 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45226.5134 | 45225.3995 | 45233.3342 | 45236.4027 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343218 | AL, Shelby, Lay Dam A8423 adding CBRS at separate level than LTE | Low | Successful | Minor | Planned | CDL | TT | 45217.7959 | 45229.5 | 45233.8333 | 45229.5 | 45233.8333 | 45236.4002 | 45236.402 | 2023 | 2023-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45219.6508 | 45218.6322 | 45229.487 | 45236.402 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343312 | GA, Atlanta, Stacks Rd ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.518 | 45229.3542 | 45229.5208 | 45229.3833 | 45229.4451 | 45229.6072 | 45229.6073 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45219.6501 | 45218.6286 | 45229.3341 | 45229.6073 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000343314 | GA, Senioa ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.533 | 45264.5417 | 45264.6667 | 45264.5417 | 45264.6361 | 45265.3829 | 45265.383 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45246.6806 | 45246.4181 | 45264.5306 | 45265.383 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000343327 | GA, Sandy Plains ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.7001 | 45233.5208 | 45233.6875 | 45233.5208 | 45233.6875 | 45236.4031 | 45236.4031 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45226.5137 | 45225.401 | 45233.5009 | 45236.4031 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343329 | GA, Atlanta, Jefferson St #1 Substation, resplice fiber cable for repairs | Low | Successful | Minor | Planned | JLM | TT | 45217.7322 | 45219.3333 | 45219.75 | 45219.4549 | 45219.5833 | 45222.4043 | 45222.4044 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45218.4866 | 45218.4553 | 45219.3217 | 45519.4626 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000343407 | GA, Atlanta, Palmetto ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45217.5233 | 45229.5208 | 45229.6875 | 45229.5208 | 45229.5431 | 45230.3941 | 45230.3942 | 2023 | 2023-10 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45219.655 | 45218.6348 | 45229.5009 | 45230.3942 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000343504 | GA, Tallapoosa ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45218.497 | 45236.3333 | 45236.5 | 45236.3333 | 45236.5 | 45237.3865 | 45237.3867 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45229.5028 | 45229.3844 | 45236.3202 | 45237.3867 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343604 | GA, Eagles Landing ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45218.467 | 45231.3542 | 45231.5 | 45231.3542 | 45231.5 | 45232.413 | 45232.4131 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45219.655 | 45218.6359 | 45231.3349 | 45232.4131 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343614 | GA, Locust Grove, cut and move OPGW for new substation | Low | Successful | Minor | Planned | JLM | TT | 45218.6189 | 45228.3125 | 45228.9792 | 45228.3146 | 45228.4264 | 45229.3786 | 45229.3788 | 2023 | 2023-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45224.4552 | 45222.4333 | 45228.2924 | 45519.4626 | 2023-Q4 | 2023-10 | 2023-Q4
CRQ000000343705 | MS, MERIDIAN DISTRICT OFFICE, move circuits for relocation | Low | Successful | Minor | Planned | AEN | TT | 45218.4231 | 45231.375 | 45231.75 | 45231.3785 | 45231.5104 | 45231.5392 | 45231.5393 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | AEN | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45218.8593 | 45218.637 | 45231.3627 | 45231.5393 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343710 | GA, Conyers ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45218.4725 | 45231.5 | 45231.6667 | 45231.5049 | 45231.5903 | 45232.4147 | 45232.4149 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45219.6557 | 45218.6377 | 45231.4877 | 45232.4149 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343719 | GA, Temple ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45218.5036 | 45236.4167 | 45236.5833 | 45236.4167 | 45236.5833 | 45237.3871 | 45237.3873 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45229.5075 | 45229.3872 | 45236.4036 | 45237.3873 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343721 | GA, Carrollton ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45218.5086 | 45236.5833 | 45236.75 | 45236.5833 | 45236.75 | 45237.3876 | 45237.3877 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45229.5083 | 45229.3913 | 45236.5709 | 45237.3877 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000343734 | GA, SOUTH BAINBRIDGE TO WEST BAINBRIDGE 9500MPR M/W OUTAGE | Low | Successful | Minor | Planned | WKA | TT | 45218.8756 | 45231.4167 | 45231.4583 | 45231.4194 | 45231.4583 | 45232.4135 | 45232.4137 | 2023 | 2023-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45226.5129 | 45225.3944 | 45231.4044 | 45519.4801 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000344713 | AL, Jasper, Splicing dark fiber for C-Spire handoff to Fayette | Low | Successful | Minor | Planned | RCA | TT | 45222.4611 | 45229.3333 | 45233.7917 | 45233.4688 | 45233.7917 | 45236.3867 | 45236.3868 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45223.6039 | 45223.5039 | 45229.3202 | 45519.4588 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000344809 | AL, Jasper, Splicing dark fiber for C-Spire handoff to Fayette (BACKUP DATE) | Low | Successful | Minor | Planned | RCA | TT | 45222.4612 | 45236.3333 | 45240.7917 | 45236.3333 | 45240.7917 | 45243.4215 | 45243.4218 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45223.6039 | 45223.5046 | 45236.3202 | 45519.4588 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000344811 | AL, Eclectic, Splicing drop for new reclosure device JR472 | Low | Successful | Minor | Planned | RCA | TT | 45222.4675 | 45231.3333 | 45232.7917 | 45231.5007 | 45231.734 | 45233.4096 | 45233.4098 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45223.6026 | 45223.5591 | 45231.3209 | 45519.4588 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000344817 | AL, Western ICON Ring. Adding Holt 2 and 3 S. Bessemer ICON nodes | Low | Successful | Minor | Planned | RPY | TT | 45222.6271 | 45243.3958 | 45243.7083 | 45243.3958 | 45243.6979 | 45243.7017 | 45243.7024 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45224.4552 | 45223.5641 | 45243.3772 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000344818 | AL, Western ICON Ring. Adding Holt 2 and 3 S. Bessemer ICON nodes (BACKUP DATE) | Low | Successful | Minor | Planned | RPY | TT | 45222.6272 | 45244.3958 | 45244.7083 | 45244.3958 | 45244.6458 | 45244.6613 | 45244.6619 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45224.4552 | 45223.565 | 45244.3759 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345208 | AL, Montgomery J St, Wilsonville, APC HQ, Move Ciena 6500 Circuits | Medium | Successful | Moderate | Planned | GPB | TT | 45223.6205 | 45231.75 | 45231.875 | 45231.75 | 45231.9597 | 45232.4159 | 45232.4189 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45224.5133 | 45223.6598 | 45231.739 | 45232.4189 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345320 | GA, Lindale Substation, Reroute OPGW route to accommodate new substation | Low | Successful | Minor | Planned | JLM | TT | 45224.5616 | 45234.3333 | 45234.75 | 45234.3368 | 45234.7535 | 45236.4037 | 45236.4038 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45226.6648 | 45225.4407 | 45234.3217 | 45519.4626 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345605 | GA, Morrow to Jonesboro PLM Firmware upgrade | Low | Successful | Minor | Planned | RPY | TT | 45225.4133 | 45238.4167 | 45238.4583 | 45238.4361 | 45238.5083 | 45240.3842 | 45240.3844 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45232.4067 | 45231.4327 | 45238.4044 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345808 | GA, Dacula ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45225.4979 | 45240.3542 | 45240.5208 | 45240.3542 | 45240.5208 | 45240.5677 | 45240.5682 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45232.8018 | 45232.4644 | 45240.3349 | 45240.5682 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345810 | GA, N GA ICON Ring, Provision T1 circuit to carry ethernet for iSTAR | Medium | Successful | Moderate | Planned | RPY | TT | 45225.5083 | 45245.5417 | 45245.625 | 45245.5479 | 45245.6646 | 45246.3923 | 45246.3934 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45239.6284 | 45237.5235 | 45245.5292 | 45340.9658 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000345812 | GA, Lawrenceville2 ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45225.5098 | 45240.5208 | 45240.6875 | 45240.5208 | 45240.6875 | 45243.4234 | 45243.4239 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45233.5232 | 45232.4703 | 45240.5016 | 45243.4239 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346101 | GA, FOLKSTON EBTS, REINSTALL PARABOLIC ANTENNA ON MINI-LINK TO SE WAYCROSS LTE | Low | Successful | Minor | Planned | WKA | TT | 45226.4198 | 45240.375 | 45240.7083 | 45240.4549 | 45240.6715 | 45243.4223 | 45243.4224 | 2023 | 2023-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45232.7997 | 45232.4623 | 45240.3627 | 45519.4801 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346201 | GA, Columbus Air ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.4054 | 45240.375 | 45240.5417 | 45240.375 | 45240.5417 | 45240.5686 | 45240.5688 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45232.799 | 45232.4603 | 45240.3627 | 45240.5688 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346202 | GA, Columbus, Crystal Valley ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.4118 | 45240.5417 | 45240.7083 | 45240.5417 | 45240.7083 | 45243.4244 | 45243.4245 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45233.5232 | 45232.4665 | 45240.5299 | 45243.4245 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346300 | GA, Auburn University ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.427 | 45243.375 | 45243.5417 | 45243.375 | 45243.5417 | 45243.7045 | 45243.7056 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45236.7298 | 45236.4084 | 45243.3633 | 45243.7056 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346301 | AL, Loachapoka ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.4339 | 45243.5417 | 45243.7083 | 45243.5417 | 45243.7083 | 45244.4053 | 45244.4055 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45236.7311 | 45236.4105 | 45243.5285 | 45244.4055 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346302 | GA, Sandy Plains ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.4584 | 45243.5208 | 45243.6875 | 45243.5208 | 45243.6875 | 45243.705 | 45243.7057 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45236.7305 | 45236.4096 | 45243.5022 | 45243.7057 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346400 | GA, Gwinnett Place ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45228.4509 | 45243.3542 | 45243.5208 | 45243.3542 | 45243.5208 | 45243.7036 | 45243.7052 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45236.7298 | 45236.4075 | 45243.3355 | 45243.7052 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346403 | GA, Statesboro EBTS G9215, adding MW dish near exisitng MW mount | Low | Successful | Minor | Planned | CDL | TT | 45228.6684 | 45257.375 | 45261.75 | 45257.375 | 45261.75 | 45264.4169 | 45264.4171 | 2023 | 2023-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45243.4489 | 45240.4006 | 45257.3619 | 45264.4171 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000346628 | GA, Moreland Way Substation, Add new section of OPGW | Low | Successful | Minor | Planned | MAR | TT | 45229.7681 | 45241.3333 | 45241.75 | 45241.3333 | 45241.625 | 45243.4251 | 45243.4252 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45236.5902 | 45233.419 | 45241.3217 | 45519.4626 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346910 | AL, Auburn EBTS, adding Auburn Tech Park to middle of MW path | Low | Successful | Minor | Planned | CDL | TT | 45230.4311 | 45238.375 | 45240.75 | 45238.375 | 45238.7063 | 45240.3988 | 45240.3998 | 2023 | 2023-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45232.4066 | 45231.4286 | 45238.3627 | 45240.3998 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346911 | AL, Abbeville, Splicing dark fibers for Great Southern Wood handoffs. | Low | Successful | Minor | Planned | DKG | TT | 45230.4508 | 45237.2917 | 45239.75 | 45237.2917 | 45239.75 | 45240.4082 | 45240.4083 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45236.5902 | 45231.4228 | 45237.2793 | 45519.4588 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000346934 | GA, Jackson Lake, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45230.6813 | 45238.375 | 45238.5 | 45238.375 | 45238.5 | 45240.3795 | 45240.3796 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45232.7983 | 45231.4305 | 45238.3627 | 45240.3796 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000347425 | GA, Tucker LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45232.7155 | 45239.375 | 45239.5 | 45239.375 | 45239.5 | 45240.4035 | 45240.4039 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45236.7312 | 45236.4544 | 45239.3563 | 45240.4039 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000347711 | GA, Minola Rd Transport, Upgrade NOKIA SAR Chassis from SAR-H to SAR-8 | Low | Successful | Minor | Planned | MPH | TT | 45233.6309 | 45243.7083 | 45243.9993 | 45243.7104 | 45243.7854 | 45244.3974 | 45244.3975 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45239.6152 | 45236.4369 | 45243.6952 | 45244.3975 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000347806 | AL and GA Various Ciena 6500 Circuit Cuts | Medium | Successful | Moderate | Planned | GPB | TT | 45233.4352 | 45243.75 | 45243.9583 | 45243.75 | 45243.9583 | 45244.406 | 45244.4063 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45236.6006 | 45236.4395 | 45243.7369 | 45244.4063 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000347812 | AL and GA Various Ciena 6500 ADM Module Fiber Connections | Low | Successful | Minor | Planned | GPB | TT | 45233.506 | 45244.75 | 45246.9583 | 45244.75 | 45246.9583 | 45247.3889 | 45247.4022 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45236.5909 | 45236.4474 | 45244.7369 | 45247.4022 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348001 | AL, GA, Multi Site NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45235.5262 | 45243.375 | 45247.7083 | 45243.375 | 45247.7083 | 45251.4084 | 45251.4086 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45238.6233 | 45236.4355 | 45243.3633 | 45251.4086 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348311 | GA, Columbus, Fortson Sub, Upgrade fiber between the sub and transport building | Medium | Successful | Moderate | Planned | JLM | TT | 45236.4633 | 45245.3333 | 45245.5833 | 45245.3396 | 45245.5306 | 45246.3942 | 45246.3946 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45239.627 | 45238.4003 | 45245.3203 | 45519.4626 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348316 | GA, Lakeland ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45236.5022 | 45244.375 | 45244.4583 | 45244.375 | 45244.4583 | 45244.6622 | 45244.6624 | 2023 | 2023-11 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45238.6226 | 45237.5177 | 45244.362 | 45244.6624 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348317 | GA, Lakeland ENODEB, Site Grounding Audit (BACKUP DATE) | Low | Successful | Minor | Planned | LPE | TT | 45236.5023 | 45245.375 | 45245.4583 | 45245.375 | 45245.4583 | 45246.3953 | 45246.3954 | 2023 | 2023-11 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45238.6226 | 45237.5182 | 45245.362 | 45246.3954 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348318 | GA, Pearson, South Pearson ENODEB, Site Grounding Audit | Low | Successful | Minor | Planned | LPE | TT | 45236.5055 | 45244.5417 | 45244.625 | 45244.5417 | 45244.625 | 45244.6628 | 45244.6631 | 2023 | 2023-11 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45238.624 | 45237.5189 | 45244.5285 | 45244.6631 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348319 | GA, Pearson, South Pearson ENODEB, Site Grounding Audit (BACKUP DATE) | Low | Successful | Minor | Planned | LPE | TT | 45236.5056 | 45245.5417 | 45245.625 | 45245.5417 | 45245.625 | 45246.3957 | 45246.3958 | 2023 | 2023-11 | Successful | Facilities Component | Surge Suppression | Repair | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45238.624 | 45237.5194 | 45245.5292 | 45246.3958 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348500 | GA, Vidalia, Tarrytown, Splicing Dark Fibers | Low | Successful | Minor | Planned | SDG | TT | 45236.3055 | 45243.9583 | 45244.25 | 45243.9778 | 45244.1111 | 45244.4068 | 45244.407 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45236.5909 | 45236.4452 | 45243.9453 | 45244.407 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348512 | GA, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45236.6074 | 45260.375 | 45260.7083 | 45260.3854 | 45260.5417 | 45260.5445 | 45260.5447 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45251.3911 | 45247.645 | 45260.3634 | 45260.5447 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348624 | AL, Dadeville Substation, Official Redundancy Testing for OLT | Low | Unsuccessful | Minor | Planned | JGL | TT | 45237.6555 | 45246.4167 | 45246.5 | 45246.4167 | 45246.4389 | 45246.4595 | 45246.4598 | 2023 | 2023-11 | Unsuccessful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45239.6159 | 45238.4251 | 45246.4044 | 45246.4598 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348628 | AL, Union Springs EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45237.9419 | 45246.375 | 45246.5833 | 45246.375 | 45246.5833 | 45247.404 | 45247.4042 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45238.6268 | 45238.4232 | 45246.3627 | 45247.4042 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348828 | AL, Dadeville Substation, Official Redundancy Testing for OLT (BACKUP DATE) | Low | Successful | Minor | Planned | JGL | TT | 45237.6556 | 45247.4167 | 45247.5 | 45247.4167 | 45247.5 | 45247.6562 | 45247.6569 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45239.6159 | 45238.4258 | 45247.4037 | 45247.6569 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000348829 | AL & MS, Various sites, Nokia SAR, Configure new PTP (Precision Timing Protocol). | Low | Successful | Minor | Planned | MPH | TT | 45237.6556 | 45258.4167 | 45261.9167 | 45258.4167 | 45261.9167 | 45264.4178 | 45264.4179 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45251.3911 | 45247.6478 | 45258.4037 | 45264.4179 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000348830 | AL & MS, Various sites, Nokia SAR, Configure new PTP (Precision Timing Protocol). (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45237.6572 | 45264.4167 | 45267.9167 | 45264.4167 | 45267.9167 | 45268.4555 | 45268.4556 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45251.3913 | 45247.6553 | 45264.3966 | 45268.4556 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349005 | GA, Lake Rabun LTE, software upgrade | Low | Successful | Minor | Planned | DRI | TT | 45238.5683 | 45245.9583 | 45246 | 45245.9583 | 45246 | 45246.3962 | 45246.3963 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45243.4497 | 45240.4383 | 45245.946 | 45246.3963 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349322 | AL/GA, Multi Site NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45239.5981 | 45259.375 | 45259.75 | 45259.4271 | 45259.6299 | 45260.4732 | 45260.4733 | 2023 | 2023-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45251.3911 | 45247.4771 | 45259.362 | 45260.4733 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349416 | GA, Cave Springs LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45239.552 | 45247.375 | 45247.5 | 45247.375 | 45247.3833 | 45247.4478 | 45247.4479 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45243.4501 | 45240.439 | 45247.362 | 45247.4479 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349418 | AL, Spain Park, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45239.5568 | 45247.4167 | 45247.5417 | 45247.4208 | 45247.4313 | 45247.4483 | 45247.4485 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45243.4509 | 45240.4448 | 45247.4037 | 45247.4484 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349428 | AL, Birmingham, Pinson EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45239.699 | 45258.5833 | 45258.7917 | 45258.5833 | 45258.7917 | 45259.4295 | 45259.4295 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45247.6666 | 45247.4643 | 45258.5702 | 45259.4295 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349429 | AL, Birmingham Air EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45239.7405 | 45258.375 | 45258.5833 | 45258.375 | 45258.5833 | 45259.4288 | 45259.429 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45247.6659 | 45247.4535 | 45258.362 | 45259.4289 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349430 | AL, Birmingham, Finley Ave EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45239.8266 | 45272.375 | 45272.5417 | 45272.375 | 45272.5417 | 45273.4227 | 45273.4229 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45265.5367 | 45264.4481 | 45272.3641 | 45273.4229 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349431 | AL, Tuscaloosa TS, splicing fiber back to Holt COLO | Low | Successful | Minor | Planned | DWM | TT | 45239.9108 | 45273.7917 | 45274 | 45273.7917 | 45274 | 45274.4314 | 45274.4314 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45259.6139 | 45257.4607 | 45273.7786 | 45519.4679 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349519 | AL, Helena EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6498 | 45261.4167 | 45261.5833 | 45261.4167 | 45261.5833 | 45264.4189 | 45264.419 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45247.6686 | 45247.4868 | 45261.4037 | 45264.419 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349522 | AL, Boligee, Crawford Fork EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6558 | 45267.4167 | 45267.5833 | 45267.4167 | 45267.5833 | 45267.6898 | 45267.69 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45259.9642 | 45259.5964 | 45267.4057 | 45267.69 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349524 | AL, Birmingham, Liberty Park EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6663 | 45300.3958 | 45300.5625 | 45300.3958 | 45300.5625 | 45301.3863 | 45301.3864 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45293.6356 | 45293.5174 | 45300.3759 | 45301.3864 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349526 | AL, Inverness EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6721 | 45315.3958 | 45315.5625 | 45315.3958 | 45315.5625 | 45316.4322 | 45316.4323 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45303.639 | 45303.6306 | 45315.376 | 45316.4323 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349527 | AL, Helena EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6801 | 45314.4167 | 45314.5833 | 45314.4167 | 45314.5833 | 45315.4317 | 45315.4318 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45303.6394 | 45303.6287 | 45314.4032 | 45315.4318 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349618 | AL, Vestavia EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6527 | 45265.3958 | 45265.6042 | 45265.3958 | 45265.6042 | 45266.4056 | 45266.4058 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45259.4199 | 45258.3889 | 45265.378 | 45266.4057 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349619 | AL, Cottondale EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.6587 | 45274.4167 | 45274.5833 | 45274.4167 | 45274.5833 | 45274.7583 | 45274.7583 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45267.7985 | 45267.4642 | 45274.4037 | 45274.7583 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000349620 | AL, Pelham 2 EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45240.6692 | 45302.3958 | 45302.5625 | 45302.3958 | 45302.5625 | 45303.4346 | 45303.4347 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45293.6377 | 45293.5259 | 45302.3766 | 45303.4347 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349706 | AL & GA, Grid Firewall Upgrades | Medium | Successful | Moderate | Planned | GEB | TT | 45240.4898 | 45246.8333 | 45246.9167 | 45246.8431 | 45246.8778 | 45247.4047 | 45247.4049 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45243.4873 | 45240.575 | 45246.8203 | 45247.4049 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349708 | AL, Fultondale EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.499 | 45314.375 | 45314.5424 | 45314.375 | 45314.5424 | 45315.4313 | 45315.4314 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45303.6407 | 45303.6358 | 45314.3616 | 45315.4314 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349710 | AL, No East Jasper EBTS, Rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.5045 | 45321.375 | 45321.5424 | 45321.375 | 45321.5417 | 45321.6201 | 45321.6202 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45313.512 | 45313.4622 | 45321.3641 | 45321.6202 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000349713 | AL, Adamsville EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45240.5125 | 45335.375 | 45335.5424 | 45335.375 | 45335.5424 | 45335.6665 | 45335.6665 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45320.5683 | 45320.5499 | 45335.362 | 45335.6665 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000349715 | AL, Northport, Samantha EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45240.5218 | 45328.375 | 45328.5424 | 45328.375 | 45328.5424 | 45328.6255 | 45328.6257 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45293.6433 | 45293.5417 | 45328.3544 | 45328.6257 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000349717 | GA, Port Wentworth, Transmission ROW, Move OPGW for GDOT Rd expansion. | Low | Successful | Minor | Planned | MAR | TT | 45240.5356 | 45244.3333 | 45244.75 | 45244.3333 | 45244.75 | 45245.4101 | 45245.4104 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45240.566 | 45240.5649 | 45244.3203 | 45519.4626 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000349921 | GA, Roopville, Transmission R.O.W., Splice new section of OPGW | Low | Successful | Minor | Planned | JLM | TT | 45243.6985 | 45269.3333 | 45269.75 | 45269.3333 | 45269.8472 | 45271.4183 | 45271.4184 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45264.5678 | 45261.5115 | 45269.3224 | 45519.4626 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350015 | GA, Hogansville, Transmission ROW, Splice in new section of fiber | Low | Successful | Minor | Planned | JLM | TT | 45243.6628 | 45262.3333 | 45262.75 | 45262.3333 | 45262.5458 | 45264.4196 | 45264.4197 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45251.3908 | 45244.416 | 45262.3217 | 45519.4626 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350115 | AL, Gorgas, Splice lateral fiber cables | Low | Successful | Minor | Planned | DWM | TT | 45243.6295 | 45274.7917 | 45275.25 | 45274.7917 | 45275.25 | 45278.4156 | 45278.4158 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45267.6875 | 45267.4654 | 45274.7779 | 45519.4679 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350212 | GA, Various sites, Nokia SAR, Configure new PTP (Precision Timing Protocol). | Medium | Successful | Moderate | Planned | MPH | TT | 45244.6523 | 45261.4167 | 45261.9167 | 45261.4167 | 45261.7354 | 45264.4159 | 45264.4162 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45247.6936 | 45247.6586 | 45261.4037 | 45264.4162 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350422 | MS, Pascagoula ICON Ring, removing all circuits associated with DS1 Modules | Low | Successful | Minor | Planned | DAP | TT | 45244.6336 | 45266.4167 | 45266.5833 | 45266.4167 | 45266.5833 | 45267.3924 | 45267.3925 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Remove/Retire | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45259.6145 | 45259.4409 | 45266.4037 | 45267.3925 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350514 | GA, Gainesville, North Gainesville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45245.512 | 45264.3542 | 45264.5208 | 45264.3542 | 45264.4062 | 45264.6432 | 45264.6433 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45257.4335 | 45257.4128 | 45264.341 | 45264.6433 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350621 | GA, Shannon, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45245.7508 | 45259.375 | 45259.5 | 45259.375 | 45259.4632 | 45259.5863 | 45259.5864 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45247.6756 | 45247.4711 | 45259.362 | 45259.5864 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000350701 | AL, Trussville, Splicing dark fiber for CSpire Handoff | Low | Successful | Minor | Planned | RCA | TT | 45245.4084 | 45258.2917 | 45259.75 | 45258.2917 | 45259.75 | 45260.4749 | 45260.475 | 2023 | 2023-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45247.6805 | 45247.4511 | 45258.2786 | 45519.4588 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000350705 | GA, Dawsonville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45245.5276 | 45264.5208 | 45264.6875 | 45264.5208 | 45264.6875 | 45265.3822 | 45265.3823 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45257.4346 | 45257.4197 | 45264.5078 | 45265.3823 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350714 | AL, APC CORP PENTHOUSE TRANSPORT/EBTS, MODIFY AC FEED TO RECTIFIER SYSTEM | Low | Successful | Minor | Planned | MVW | TT | 45245.8693 | 45257.3333 | 45258.7083 | 45257.3333 | 45257.75 | 45258.3794 | 45258.3796 | 2023 | 2023-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45247.6652 | 45247.4468 | 45257.3202 | 45498.7092 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000350901 | GA, Doraville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.4024 | 45266.3542 | 45266.5208 | 45266.3542 | 45266.5208 | 45267.3916 | 45267.3917 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45259.9632 | 45259.437 | 45266.3342 | 45267.3917 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350903 | GA, Lilburn ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.4134 | 45266.5208 | 45266.6875 | 45266.5208 | 45266.6875 | 45267.3935 | 45267.3937 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45259.9638 | 45259.4436 | 45266.501 | 45267.3937 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350911 | AL, Attalla LTE, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45246.5057 | 45259.4583 | 45259.5833 | 45259.4583 | 45259.6 | 45259.6046 | 45259.6048 | 2023 | 2023-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45247.6763 | 45247.633 | 45259.4454 | 45259.6048 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000350922 | GA, N Shallowford ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.6323 | 45268.3542 | 45268.5208 | 45268.3542 | 45268.5208 | 45271.4161 | 45271.4163 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45264.4088 | 45260.5538 | 45268.3356 | 45271.4163 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000350923 | GA, Austell ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.6506 | 45271.3542 | 45271.5208 | 45271.3542 | 45271.5208 | 45272.396 | 45272.3961 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45265.5359 | 45264.4222 | 45271.3348 | 45272.3961 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351013 | GA, Johns Creek ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.6402 | 45268.5208 | 45268.6875 | 45268.5208 | 45268.6875 | 45271.4172 | 45271.4173 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45264.4092 | 45260.5547 | 45268.5023 | 45271.4173 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351014 | GA, Fulton Industrial Blvd ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45246.6652 | 45271.5208 | 45271.6875 | 45271.5208 | 45271.6875 | 45272.3971 | 45272.3972 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45265.5363 | 45264.4258 | 45271.5016 | 45272.3971 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351016 | AL, Plant Farley, EBTS/Transport, AC Power Feeder Repair/Rewire | Low | Successful | Minor | Planned | TRC | TT | 45246.9442 | 45258.25 | 45258.9167 | 45258.25 | 45258.9167 | 45259.4308 | 45259.4309 | 2023 | 2023-11 | Successful | Facilities Component | Power Strip | Repair | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45247.6693 | 45247.6318 | 45258.2369 | 45519.476 | 2023-Q4 | 2023-11 | 2023-Q4
CRQ000000351108 | GA, AL and MS, Various sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45247.6682 | 45294.375 | 45294.9993 | 45294.3903 | 45294.7806 | 45295.3926 | 45295.3936 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45281.6647 | 45280.594 | 45294.3616 | 45295.3936 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000351110 | GA, Taylor Ridge, Replacing the DC RECTIFIER SYSTEM | Low | Successful | Minor | Planned | JBT | TT | 45247.6906 | 45265.3333 | 45265.8333 | 45265.3333 | 45265.8333 | 45266.4093 | 45266.4095 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | JBT | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45259.4195 | 45258.3852 | 45265.3224 | 45266.4095 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351313 | MS, Marion, Turn Up Marion SE Substation CGR (New Substation) | Low | Successful | Minor | Planned | DRB | TT | 45247.601 | 45264.4167 | 45264.75 | 45264.4167 | 45264.6042 | 45264.642 | 45264.6421 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45258.3974 | 45257.4161 | 45264.3966 | 45264.6421 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351316 | GA, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45247.6889 | 45299.375 | 45299.9993 | 45299.375 | 45299.6042 | 45299.6142 | 45299.6144 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45293.7083 | 45293.5143 | 45299.3633 | 45299.6144 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000351400 | GA, Cobb Co Hwy 5, ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45248.4069 | 45273.3542 | 45273.5208 | 45273.3542 | 45273.5208 | 45274.4302 | 45274.4303 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45265.5397 | 45265.5149 | 45273.346 | 45274.4303 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351500 | GA, East Dallas ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45248.4137 | 45273.5208 | 45273.6875 | 45273.5208 | 45273.6875 | 45274.4308 | 45274.4308 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45265.5401 | 45265.5155 | 45273.5285 | 45274.4308 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351501 | GA, Rome ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45248.4589 | 45275.3542 | 45275.5208 | 45275.3542 | 45275.5208 | 45278.4163 | 45278.4164 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45268.6616 | 45268.5936 | 45275.3338 | 45278.4164 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000351914 | GA, Buckhead, Transmission R.O.W., Cut and install new section of fiber | Low | Successful | Minor | Planned | JLM | TT | 45250.7832 | 45318.3333 | 45318.75 | 45318.3333 | 45318.75 | 45320.5007 | 45320.5008 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45293.7097 | 45293.5446 | 45318.3209 | 45519.4626 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000351915 | GA, Buckhead, Transmission R.O.W., Cut and install new section of fiber (BACKUP DATE) | Low | Successful | Minor | Planned | JLM | TT | 45250.7834 | 45319.3333 | 45319.75 | 45319.3333 | 45319.75 | 45320.5011 | 45320.5012 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45293.7099 | 45293.5456 | 45319.3202 | 45519.4626 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000352400 | AL, Autaugaville EBTS A9335, adding CBRS to the Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45251.4033 | 45264.5833 | 45268.7917 | 45264.5833 | 45268.7917 | 45271.4072 | 45271.4148 | 2023 | 2023-12 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45257.4353 | 45257.4257 | 45264.5723 | 45271.4148 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353305 | AL, APC HQ and GA, GPC HQ Ciena Card Reconfiguration. | Low | Successful | Minor | Planned | GPB | TT | 45257.4029 | 45265.75 | 45265.9167 | 45265.75 | 45265.9167 | 45266.4116 | 45266.4118 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45258.3972 | 45258.3931 | 45265.7369 | 45266.4117 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353310 | GA, ATL ICON Ring, provision new EBAM Circuit(s) for new EPIPE for ATL NUG | Medium | Successful | Moderate | Planned | RPY | TT | 45257.4745 | 45316.4375 | 45316.6667 | 45316.4375 | 45316.6667 | 45317.4295 | 45317.4297 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45307.6616 | 45303.6488 | 45316.4176 | 45340.9658 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000353406 | AL and GA, Various Ciena 6500 100G MOTR Re-configuration | Medium | Successful | Moderate | Planned | GPB | TT | 45257.4388 | 45266.75 | 45266.9583 | 45266.7569 | 45266.9278 | 45267.3957 | 45267.396 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45259.6324 | 45259.5934 | 45266.739 | 45267.396 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353624 | AL, Auburn, Clean/Replace Fiber Connection Between WSS and MLA2 | Low | Successful | Minor | Planned | DRB | TT | 45258.6879 | 45266.75 | 45266.8333 | 45266.75 | 45266.7625 | 45267.3944 | 45267.3945 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45260.445 | 45259.5904 | 45266.739 | 45267.3945 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353703 | GA, Statesboro EBTS G9215, aligning MW dish to G8172 Statesboro Sub | Low | Successful | Minor | Planned | CDL | TT | 45258.4026 | 45266.375 | 45268.8333 | 45266.375 | 45268.8333 | 45271.4154 | 45271.4155 | 2023 | 2023-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45259.9636 | 45259.4389 | 45266.362 | 45271.4155 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353712 | GA, Vidalia, Tarrytown, Splicing Dark Fibers | Low | Successful | Minor | Planned | SDG | TT | 45258.5709 | 45266.9583 | 45267.25 | 45266.9597 | 45267.0028 | 45267.3965 | 45267.3967 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45259.6162 | 45259.5941 | 45266.9473 | 45267.3967 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353722 | AL, Bessemer TS, Structure 406 Splicing Fiber for ERPS ring | Low | Successful | Minor | Planned | JGL | TT | 45258.6989 | 45272.75 | 45273.2917 | 45272.7569 | 45272.8903 | 45273.4213 | 45273.4216 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45264.6134 | 45264.4558 | 45272.7383 | 45273.4216 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353729 | AL, 4 LTE router reboots | Low | Successful | Minor | Planned | DRI | TT | 45258.8897 | 45266 | 45266.041 | 45266 | 45266.041 | 45266.4124 | 45266.4126 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Repair | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45260.6694 | 45260.4871 | 45265.9869 | 45266.4126 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353805 | GA, SAV ICON Ring, Fiber clean up needed at Boulevard Sub ICON | Low | Successful | Minor | Planned | RPY | TT | 45258.4092 | 45274.3958 | 45274.5625 | 45274.3958 | 45274.5625 | 45274.7541 | 45274.7542 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45267.5453 | 45267.4052 | 45274.3759 | 45340.9658 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000353913 | AL, NW Ashville LTE, replace damaged rectifier plant | Low | Successful | Minor | Planned | RBK | TT | 45259.9287 | 45274.4167 | 45274.5833 | 45274.4167 | 45274.5833 | 45274.7577 | 45274.7578 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Repair | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45267.7989 | 45267.4104 | 45274.4037 | 45274.7578 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000354332 | Upgrade Atlanta and Birmingham PaloAlto 7050 Firewalls | Medium | Successful | Moderate | Planned | GEB | TT | 45260.78 | 45265.5417 | 45266.125 | 45265.5417 | 45266.125 | 45266.41 | 45266.4111 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45264.4207 | 45261.4209 | 45265.5285 | 45266.4111 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000354623 | AL, Smith Dam, New WAN Link Turnup and Southernet Cutover | Low | Successful | Minor | Planned | MPH | TT | 45261.7583 | 45272.4167 | 45272.625 | 45272.4167 | 45272.625 | 45273.4286 | 45273.4287 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45264.6124 | 45264.4532 | 45272.4058 | 45273.4287 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000354625 | AL, SOUTH BESSEMER TS 115 SUBSTATION, SWAN COAM ckt migration | Medium | Successful | Moderate | Planned | MPH | TT | 45261.8008 | 45273.625 | 45273.7917 | 45273.625 | 45273.7917 | 45274.4283 | 45274.4294 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45266.4888 | 45265.5181 | 45273.6119 | 45274.4294 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355206 | GA, SAV ICON Ring. System Error needs clearing. Circuit needs to be rebuilt | Medium | Unsuccessful | Moderate | Planned | RPY | TT | 45264.4265 | 45274.4167 | 45274.5 | 45274.4167 | 45274.5 | 45274.7554 | 45274.7568 | 2023 | 2023-12 | Unsuccessful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45267.5593 | 45267.4074 | 45274.4037 | 45340.9658 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355231 | AL, Birmingham, Upgrade Southern Linc Production Converged Cloud Fabric (CCF) | Medium | Successful | Moderate | Planned | GEB | TT | 45264.8554 | 45277.875 | 45278.0417 | 45277.875 | 45278.0417 | 45278.4168 | 45278.4184 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45272.4902 | 45271.6958 | 45277.8619 | 45278.4184 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355232 | AL, Birmingham, Upgrade Southern Linc Production Converged Cloud Fabric (CCF) (BACKUP DATE) | Medium | Successful | Moderate | Planned | GEB | TT | 45264.8555 | 45293.7917 | 45293.9583 | 45293.7917 | 45293.9583 | 45294.361 | 45294.3614 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45271.3222 | 45265.5568 | 45293.7779 | 45294.3614 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000355402 | GA, Athens transport hub, test the generator with load | Low | Successful | Minor | Planned | PCM | TT | 45264.3744 | 45274.375 | 45274.4583 | 45274.3979 | 45274.6153 | 45274.7527 | 45274.7528 | 2023 | 2023-12 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | PCM | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45268.3775 | 45267.4041 | 45274.362 | 45519.4725 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355504 | AL, Montgomery, Splicing dark Fibers for CSpire, FUN/AFN Partner | Low | Successful | Minor | Planned | DKG | TT | 45265.4232 | 45273.2917 | 45274.75 | 45273.3632 | 45274.75 | 45274.7631 | 45274.7631 | 2023 | 2023-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45266.4305 | 45265.5103 | 45273.2765 | 45519.4588 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355527 | GA, Minola Road Transport, Migrate Brickstore/Stanton 115kv SWAN from PTP to Ethernet (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45265.6442 | 45316.375 | 45316.5833 | 45316.375 | 45316.5833 | 45317.4345 | 45317.4346 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45293.6413 | 45293.5346 | 45316.362 | 45317.4346 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000355602 | GA, Jekyll Island EBTS G9799, adding sector 4 (Delta) | Low | Successful | Minor | Planned | CDL | TT | 45265.4569 | 45271.3333 | 45275.7917 | 45271.3333 | 45275.7917 | 45278.4149 | 45278.415 | 2023 | 2023-12 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45265.5374 | 45265.5086 | 45271.3209 | 45278.415 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355707 | AL, Lafayette ENODEB, DC Plant Upgrade | Low | Successful | Minor | Unplanned | LPE | TT | 45265.5216 | 45271.375 | 45271.5833 | 45271.375 | 45271.5833 | 45272.3966 | 45272.3966 | 2023 | 2023-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45268.6608 | 45268.5923 | 45271.3626 | 45272.3966 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355716 | GA, Various Sites, Slotting New ADM Modules | Low | Successful | Minor | Planned | ADL | TT | 45265.6142 | 45272.75 | 45272.9993 | 45272.75 | 45272.9993 | 45273.4297 | 45273.4299 | 2023 | 2023-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45267.5442 | 45265.6212 | 45272.7383 | 45273.4299 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000355818 | AL, Mobile, Splicing in North connector ERPS fibers. | Low | Successful | Minor | Planned | DKG | TT | 45266.6074 | 45294.2917 | 45295.75 | 45294.4021 | 45295.7562 | 45296.4419 | 45296.4421 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45281.6616 | 45280.5909 | 45294.2783 | 45519.4588 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000356016 | AL, Union Springs LTE, Cisco A920 router reboot. | Low | Successful | Minor | Planned | JHW | TT | 45266.7514 | 45272 | 45272.25 | 45272 | 45272.25 | 45272.3948 | 45272.3949 | 2023 | 2023-12 | Successful | Transport Device | Other Transport Device | Repair | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45268.3787 | 45267.6867 | 45271.989 | 45272.3949 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000357222 | MS, Carriere, Migrate Carriere SW Sub to NGTAN | Low | Successful | Minor | Planned | DRB | TT | 45271.6729 | 45301.4167 | 45301.75 | 45301.4167 | 45301.75 | 45302.3932 | 45302.3933 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45295.3538 | 45293.5242 | 45301.4044 | 45302.3933 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000357521 | GA, Augusta 15th Street Substation, Transport Fiber Move | Medium | Successful | Moderate | Unplanned | MAR | TT | 45272.8847 | 45298.2083 | 45298.75 | 45298.2868 | 45298.6549 | 45299.3981 | 45299.3985 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45296.6314 | 45295.4209 | 45298.1952 | 45519.4626 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000358517 | GA, Statesboro EBTS G9215, azimuth change to support G8172 Statesboro Sub | Low | Successful | Minor | Planned | CDL | TT | 45275.6591 | 45279.4167 | 45279.8333 | 45279.4167 | 45279.8333 | 45280.5878 | 45280.5879 | 2023 | 2023-12 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45278.4365 | 45278.4337 | 45279.4036 | 45280.5879 | 2023-Q4 | 2023-12 | 2023-Q4
CRQ000000359103 | GA, Flovilla, Monticello, ILAs, Installing Breakers in BDFBs | Low | Successful | Minor | Planned | SDG | TT | 45279.3709 | 45300.9583 | 45301.25 | 45300.9583 | 45301.0361 | 45301.3871 | 45301.3872 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45293.6367 | 45293.5204 | 45300.9459 | 45301.3872 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000359104 | GA, Flovilla, Monticello, ILAs, Installing Breakers in BDFBs (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45279.3709 | 45301.9583 | 45302.25 | 45301.9583 | 45302.25 | 45302.5711 | 45302.5713 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45293.6371 | 45293.5209 | 45301.946 | 45302.5713 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000359303 | AL, Upgrade Birmingham LTE Core, Converged Cloud Fabric (CCF) | Medium | Successful | Moderate | Planned | GEB | TT | 45279.5189 | 45302.7917 | 45303.0417 | 45302.7917 | 45303.0417 | 45303.4369 | 45303.4371 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45293.6484 | 45293.5293 | 45302.7786 | 45303.4371 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361102 | MS, AL, Various sites, NOKIA SAR Software Upgrades (BACKUP DATE) | Medium | Successful | Moderate | Planned | MPH | TT | 45289.5793 | 45313.375 | 45313.9993 | 45313.3979 | 45313.7222 | 45314.397 | 45314.3973 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45294.3481 | 45293.6763 | 45313.3619 | 45314.3973 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361103 | MS, Various sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45289.6004 | 45314.375 | 45314.9993 | 45314.375 | 45314.7382 | 45315.4173 | 45315.4177 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45300.4097 | 45295.4306 | 45314.3616 | 45315.4177 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361428 | Advisory/Oper Event: AL - EUFAULA - UNION SPRINGS - NCC16432 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45293.6502 | 45295.25 | 45295.5 | 45294.9535 | 45295.1576 | 45295.2854 | 45295.2855 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45293.6562 | 45293.6562 | 45295.237 | 45295.2855 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361430 | Advisory/Oper Event: AL - EUFAULA - UNION SPRINGS - NCC16432 (BACKUP 2) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45293.6515 | 45296.25 | 45296.5 | 45295.9826 | 45296.3972 | 45296.4009 | 45296.4011 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45293.6561 | 45293.6561 | 45296.2366 | 45296.4011 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361432 | Advisory/Oper Event: GA - FORTSON - WHITESVILLE - EMERGENCY MAINTENANCE - NCC16551 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45293.6637 | 45295.2083 | 45295.4167 | 45294.9535 | 45295.0993 | 45295.2868 | 45295.2871 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45293.6712 | 45293.6712 | 45295.1953 | 45295.2871 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361505 | AL, Quinton EBTS A9185, Miller SP, adding CBRS to the Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45293.5111 | 45313.5 | 45317.7917 | 45313.5 | 45317.7917 | 45320.4997 | 45320.4998 | 2024 | 2024-01 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45295.4788 | 45293.677 | 45313.487 | 45320.4998 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361506 | AL, Quinton EBTS A9185, Miller SP, adding CBRS to the Skymounts (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45293.5112 | 45320.5 | 45324.7917 | 45320.5 | 45324.7917 | 45327.4658 | 45327.4658 | 2024 | 2024-02 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45295.479 | 45293.6775 | 45320.487 | 45327.4658 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000361510 | GA, N. GA ICON Ring, removal of unused modules | Low | Successful | Minor | Planned | RPY | TT | 45293.5332 | 45299.3958 | 45299.7083 | 45299.3958 | 45299.7083 | 45299.8012 | 45299.8014 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45293.7105 | 45293.6713 | 45299.3772 | 45340.9658 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361602 | GA, Flovilla, Monticello, ILAs, Installing Breakers in BDFBs | Low | Successful | Minor | Planned | SDG | TT | 45293.4383 | 45302.9583 | 45303.25 | 45302.9583 | 45303.25 | 45303.4384 | 45303.4385 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45295.3538 | 45293.6731 | 45302.9453 | 45303.4385 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361619 | Advisory/Oper Event: AL - COLLINSVILLE - EMERGENCY FIBER REPAIR - NCC16572 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45293.6779 | 45294.2917 | 45294.4583 | 45294.0521 | 45294.1944 | 45294.2903 | 45294.2905 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45293.682 | 45293.682 | 45294.2783 | 45294.2905 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361709 | AL, Trussville, Splicing dark fibers for CSpire Handoff | Low | Successful | Minor | Planned | DKG | TT | 45294.4736 | 45301.2917 | 45303.7917 | 45301.2917 | 45303.7917 | 45307.5034 | 45307.5041 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45300.4003 | 45295.4226 | 45301.2793 | 45519.4588 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361901 | AL, Various sites, NOKIA 7250 IXR SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45294.3931 | 45302.5417 | 45302.7083 | 45302.5417 | 45302.6382 | 45303.4259 | 45303.4261 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45300.4042 | 45295.4255 | 45302.5285 | 45303.4261 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000361915 | GA, Atlanta, 270 Peachtree, Splicing dark fiber | Low | Successful | Minor | Planned | SDG | TT | 45294.7407 | 45308.9583 | 45309.25 | 45308.9653 | 45309.0993 | 45309.4108 | 45309.4109 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45300.4002 | 45295.4269 | 45308.9453 | 45309.4109 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362011 | AL, Basset Creek to Greene County Steam Plant, moving fibers for FUN/AFN. (BACKUP DATE) | Medium | Successful | Moderate | Planned | DHA | TT | 45295.4518 | 45321.7917 | 45322.125 | 45321.7917 | 45322.125 | 45322.5926 | 45322.5931 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45313.4653 | 45313.4529 | 45321.7786 | 45519.4679 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362022 | GA, WAYCROSS, KETTLE CREEK/OFFERMAN TRANSPORT, MOVE SAR LINK TO NEW FIBER | Low | Successful | Minor | Planned | WKA | TT | 45295.6498 | 45301.4167 | 45301.625 | 45301.4167 | 45301.625 | 45302.3959 | 45302.396 | 2024 | 2024-01 | Successful | Facilities Component | Cables, jumpers, and connectors | Migrate | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45300.4042 | 45299.4102 | 45301.4044 | 45519.4801 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362029 | AL, Albertville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45295.8511 | 45316.4167 | 45316.625 | 45316.4167 | 45316.625 | 45317.4373 | 45317.4374 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45307.5425 | 45303.6781 | 45316.4037 | 45317.4374 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362030 | AL, Jacksonville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45295.8642 | 45337.4167 | 45337.625 | 45337.4167 | 45337.625 | 45338.4569 | 45338.457 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45308.4124 | 45307.6324 | 45337.4037 | 45338.457 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000362109 | AL, Basset Creek to Greene County Steam Plant, moving fibers for FUN/AFN. | Medium | Successful | Moderate | Planned | DHA | TT | 45295.4516 | 45320.7917 | 45321.125 | 45320.7917 | 45321.125 | 45321.3815 | 45321.382 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45313.4709 | 45313.4511 | 45320.7806 | 45519.4679 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362124 | AL, Boaz LTE, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45295.846 | 45315.4167 | 45315.625 | 45315.4167 | 45315.625 | 45316.4326 | 45316.4327 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45303.6405 | 45303.6338 | 45315.4038 | 45316.4327 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362125 | AL, Trussville, Deerfoot Parkway EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45295.855 | 45323.4167 | 45323.625 | 45323.4167 | 45323.625 | 45323.6797 | 45323.6798 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45308.4114 | 45307.5778 | 45323.4044 | 45323.6798 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000362126 | AL, Heflin EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45295.861 | 45330.4167 | 45330.625 | 45330.4167 | 45330.625 | 45331.6075 | 45331.6076 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45308.4127 | 45307.6346 | 45330.4031 | 45331.6076 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000362127 | AL, From Bassett Creek to Greene County SP, splice reconfiguration in cans | Low | Successful | Minor | Planned | DHA | TT | 45295.9155 | 45321.7917 | 45322.125 | 45321.7917 | 45322.125 | 45322.5917 | 45322.5918 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45313.4645 | 45313.4564 | 45321.7786 | 45519.4679 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362128 | AL, From Bassett Creek to Greene County SP, splice reconfiguration in cans (BACKUP DATE) | Low | Successful | Minor | Planned | DHA | TT | 45295.9157 | 45322.7917 | 45323.125 | 45322.7917 | 45323.125 | 45323.4909 | 45323.491 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45313.465 | 45313.4582 | 45322.7793 | 45519.4679 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000362211 | GA, Vogtle Units 3 & 4 SWAN Circuits Migration to new NGTAN SAR node. (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45295.5597 | 45314.375 | 45314.7083 | 45314.375 | 45314.4507 | 45314.4596 | 45314.4597 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45307.6565 | 45303.6681 | 45314.3616 | 45314.4597 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362407 | GA, Dalton, Conasauga Substation, Replace temporary batteries in telecom cabinet | Low | Successful | Minor | Planned | JMN | TT | 45296.4819 | 45314.375 | 45314.5833 | 45314.375 | 45314.5111 | 45315.422 | 45315.4221 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Install | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45307.5417 | 45303.6607 | 45314.3616 | 45519.4736 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362414 | GA, AL, New VPLS service is for the Generation WAN Isolation project. | Low | Successful | Minor | Planned | MPH | TT | 45296.6023 | 45314.375 | 45314.5417 | 45314.375 | 45314.5417 | 45315.4308 | 45315.4309 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45307.6565 | 45303.6586 | 45314.3616 | 45315.4309 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000362417 | AL, Wedowee EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45296.7029 | 45335.4167 | 45335.625 | 45335.4167 | 45335.625 | 45335.6656 | 45335.6657 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45308.412 | 45307.6314 | 45335.4037 | 45335.6657 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000362700 | GA, Currahee Mountain ENODEB, Generator Transfer Switch Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45298.4085 | 45313.3333 | 45313.6667 | 45313.3333 | 45313.6667 | 45314.3978 | 45314.398 | 2024 | 2024-01 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45307.5352 | 45303.6547 | 45313.3202 | 45314.398 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363128 | GA, Atlanta Ring, New Async and Nx64 circuit build | Low | Successful | Minor | Planned | RPY | TT | 45299.7218 | 45321.3958 | 45321.7083 | 45321.3958 | 45321.7083 | 45322.587 | 45322.587 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45307.6567 | 45307.5717 | 45321.378 | 45340.9658 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363304 | AL, Birmingham PCC Install DC Breaker in DC Distribution and DC Cables. | Low | Successful | Minor | Planned | GPB | TT | 45300.3835 | 45315.4167 | 45315.6667 | 45315.4604 | 45315.6667 | 45316.4313 | 45316.4314 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45308.4145 | 45307.6788 | 45315.4038 | 45316.4314 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363320 | AL, Demopolis LO, Replace site UPS batteries | Low | Successful | Minor | Planned | CAH | TT | 45300.7073 | 45315.7708 | 45315.8542 | 45315.7708 | 45315.8542 | 45316.4353 | 45316.4355 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Repair | Transport | CAH | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45308.4169 | 45308.3841 | 45315.7508 | 45519.4508 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363401 | Advisory/Oper Event: MS - MARION - DOT FIBER RELOCATION - NCC16496 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45300.3916 | 45301.0417 | 45301.25 | 45301.0271 | 45301.2438 | 45301.3186 | 45301.3187 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45300.3957 | 45300.3957 | 45301.0293 | 45301.3187 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363504 | Advisory/Oper Event: AL - FL - VARIOUS LOCATIONS - EMERGENCY FIBER REPAIR - NCC16596 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45300.4557 | 45345.375 | 45345.5417 | 45345.3764 | 45345.4882 | 45345.4953 | 45345.4953 | 2024 | 2024-02 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45314.4613 | 45314.4613 | 45345.362 | 45345.4953 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000363713 | AL, Smith Dam, SWAN circuit migration to ethernet | Low | Successful | Minor | Planned | MPH | TT | 45301.4738 | 45320.4167 | 45320.5417 | 45320.4167 | 45320.4507 | 45320.5043 | 45320.5044 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45307.6567 | 45307.5681 | 45320.4036 | 45320.5044 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363912 | AL, 18th St. DS, Clear Circuit Errors we are receiving on the ICON Node | Low | Successful | Minor | Planned | DAP | TT | 45302.5045 | 45313.4167 | 45313.5833 | 45313.4292 | 45313.5618 | 45313.6087 | 45313.6088 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45307.6564 | 45303.6569 | 45313.4036 | 45313.6088 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000363915 | GA, 241 RMB, Clear Circuit Errors on the ICON Node | Low | Successful | Minor | Planned | DAP | TT | 45302.5153 | 45313.4167 | 45313.5833 | 45313.4347 | 45313.5625 | 45313.6078 | 45313.6081 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45307.6564 | 45303.656 | 45313.4036 | 45313.6081 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000364010 | GA, ATL, 241 RM, Linc Core, Emergency rest of Linc LTE SSR Routers | Medium | Successful | Moderate | Unplanned | MJR | TT | 45302.4721 | 45302.5625 | 45302.6042 | 45302.5625 | 45302.6042 | 45303.4353 | 45303.4364 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45302.5075 | 45302.5036 | 45302.5424 | 45303.4364 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000364212 | AL, Plant Farley EBTS/Transport, DC Plant replacement | Low | Successful | Minor | Planned | TRC | TT | 45303.5441 | 45313.375 | 45316.75 | 45313.375 | 45316.75 | 45317.4368 | 45317.437 | 2024 | 2024-01 | Successful | Facilities Component | DC Backup System | Migrate | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45307.5407 | 45303.664 | 45313.3619 | 45519.476 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000364226 | AL, Phenix City M/W, replacing auto throwover switch on generator | Low | Successful | Minor | Planned | JEN | TT | 45303.7793 | 45314.3333 | 45317.7917 | 45314.3333 | 45317.7917 | 45320.5002 | 45320.5003 | 2024 | 2024-01 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45308.4093 | 45307.5614 | 45314.3198 | 45519.4508 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000364310 | GA, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45303.5101 | 45327.375 | 45327.9993 | 45327.3757 | 45327.6132 | 45327.6403 | 45327.6407 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45307.6573 | 45307.5789 | 45327.3614 | 45327.6407 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000364407 | GA, Covington, Brick Store Sub/Madison Transport, Decom Exalt M/W Equipment decommission | Low | Successful | Minor | Planned | JMN | TT | 45303.5008 | 45322.375 | 45322.7083 | 45322.375 | 45322.6153 | 45322.6166 | 45322.6167 | 2024 | 2024-01 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Remove/Retire | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45308.4103 | 45307.5753 | 45322.362 | 45519.4736 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000364410 | AL and MS, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45303.544 | 45329.375 | 45329.9993 | 45329.375 | 45329.8118 | 45330.5646 | 45330.5647 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45307.6559 | 45307.6294 | 45329.362 | 45330.5647 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000364411 | GA, Atlanta ICON Ring, UCAD & NPAD System error clean-up | Medium | Successful | Moderate | Planned | RPY | TT | 45303.5744 | 45327.4375 | 45327.6667 | 45327.5306 | 45327.6431 | 45327.6434 | 45327.6438 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45307.6625 | 45307.6267 | 45327.417 | 45340.9658 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365104 | GA, Virginia Ave Transport, Ciena DWDM ADM Module Installation | Medium | Successful | Moderate | Planned | ADL | TT | 45307.453 | 45314.75 | 45315.0417 | 45314.75 | 45314.9424 | 45315.4195 | 45315.4197 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45310.3982 | 45307.5644 | 45314.7369 | 45315.4197 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000365111 | Atlanta LTE Core, Move Alabama/Mississippi GRID APN's To Birmingham LTE Core | Medium | Unsuccessful | Moderate | Planned | GEB | TT | 45307.555 | 45321.9167 | 45321.9583 | 45321.9236 | 45322.1368 | 45322.5736 | 45322.5739 | 2024 | 2024-01 | Unsuccessful | Transport Device | Other Transport Device | Migrate | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45308.5283 | 45307.6769 | 45321.9036 | 45322.5739 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000365212 | GA, Tallulah Lodge #1 Substation, Replace Telecom Batteries | Low | Successful | Minor | Planned | JTC | TT | 45307.6386 | 45322.4167 | 45322.7083 | 45322.4167 | 45322.4507 | 45323.4889 | 45323.4889 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Repair | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45308.4154 | 45307.6798 | 45322.4037 | 45519.4725 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365411 | GA, Columbus DCC, Tower Reinforcement/Extension (BACKUP DATE) | Low | Successful | Minor | Planned | TAJ | TT | 45308.5923 | 45320.3333 | 45322.6667 | 45320.3333 | 45321.6042 | 45321.6193 | 45321.6194 | 2024 | 2024-01 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | TAJ | SCS | INFRASTRUCTURE SERVICES | FO SE-PROJECTS & NATIONAL | 45314.4522 | 45313.5979 | 45320.3202 | 45519.4828 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000365414 | AL, Western ICON Ring, Holt ethernet correction (System error) | Medium | Successful | Moderate | Unplanned | RPY | TT | 45308.6447 | 45315.3958 | 45315.6667 | 45315.4014 | 45315.5889 | 45316.4295 | 45316.4298 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45313.4717 | 45313.465 | 45315.376 | 45340.9658 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000365505 | GA, 241 RMB, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45308.4795 | 45343.375 | 45343.9993 | 45343.375 | 45343.9993 | 45344.508 | 45344.5081 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45313.654 | 45313.5958 | 45343.362 | 45344.5081 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365506 | GA, 241 RMB, Various sites, NOKIA SAR Software Upgrades (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45308.4798 | 45350.375 | 45350.9993 | 45350.734 | 45350.8104 | 45351.4082 | 45351.4086 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45313.6544 | 45313.5964 | 45350.362 | 45351.4086 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365510 | GA, Savannah, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45308.6422 | 45349.375 | 45349.9993 | 45349.384 | 45349.4701 | 45349.5092 | 45349.5093 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45313.6564 | 45313.6357 | 45349.3634 | 45349.5093 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365610 | GA, Gwinnett, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45308.5023 | 45348.375 | 45348.9993 | 45348.375 | 45348.7819 | 45349.4071 | 45349.4072 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45313.6552 | 45313.6002 | 45348.3619 | 45349.4072 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000365921 | Advisory/Oper Event: AL - TRAFFORD - EMERGENCY FIBER REPAIR - NCC16708 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45309.5956 | 45309.625 | 45310.0417 | 45309.6118 | 45310.6618 | 45313.3784 | 45313.3785 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45309.6092 | 45309.6092 | 45309.6133 | 45313.3785 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000366030 | AL, Pelham Local Office, Swap ONTs | Low | Successful | Minor | Planned | JGL | TT | 45310.6594 | 45320.75 | 45320.9583 | 45320.7569 | 45320.8313 | 45321.3837 | 45321.3839 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45314.4533 | 45314.4074 | 45320.739 | 45321.3839 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000366031 | AL, Demopolis Crew HQ, ONT Swap | Low | Successful | Minor | Planned | JGL | TT | 45310.67 | 45328.75 | 45329.041 | 45328.7597 | 45328.8229 | 45329.4687 | 45329.4688 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45314.4544 | 45314.4146 | 45328.7369 | 45329.4688 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366033 | GA, Atlanta, 241 Ralph McGill Blvd, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45310.6714 | 45321.6667 | 45321.9993 | 45321.6667 | 45321.7924 | 45322.5887 | 45322.5889 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45317.448 | 45317.4355 | 45321.6536 | 45322.5889 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000366036 | AL, Fayette Crew HQ, ONT Swap | Low | Successful | Minor | Planned | JGL | TT | 45310.6768 | 45335.75 | 45336.041 | 45335.7556 | 45335.8215 | 45336.4212 | 45336.4213 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45314.455 | 45314.4153 | 45335.7369 | 45336.4213 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366108 | GA, Atlanta, 241 Ralph McGill Blvd, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45310.6779 | 45322.6667 | 45322.9993 | 45322.6667 | 45322.741 | 45323.4847 | 45323.4848 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45314.5399 | 45314.41 | 45322.6542 | 45323.4848 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366209 | AL, Jasper Office, ONT Swap | Low | Successful | Minor | Planned | JGL | TT | 45310.6811 | 45337.75 | 45338.041 | 45337.75 | 45338.041 | 45338.4574 | 45338.4575 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45314.4554 | 45314.4159 | 45337.7376 | 45338.4575 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366712 | AL, Jasper, Splicing Dark fiber for Downtown Jasper WIFI project. | Low | Successful | Minor | Planned | DKG | TT | 45313.4639 | 45320.2917 | 45324.7917 | 45320.2917 | 45324.7917 | 45327.4039 | 45327.404 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45314.5431 | 45314.4031 | 45320.2786 | 45519.4588 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366713 | AL, Jasper, Splicing Dark fiber for Downtown Jasper WIFI project. (BACKUP DATE) | Low | Successful | Minor | Planned | DKG | TT | 45313.464 | 45327.2917 | 45329.7917 | 45327.2917 | 45329.7917 | 45330.5725 | 45330.5726 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45314.545 | 45314.4038 | 45327.2781 | 45519.4588 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000366728 | AL, Abbeville, Splicing dark fibers for Great Southern Wood | Low | Successful | Minor | Planned | DKG | TT | 45313.6989 | 45320.75 | 45321.0417 | 45320.7792 | 45320.8007 | 45321.383 | 45321.3831 | 2024 | 2024-01 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45314.5459 | 45314.4229 | 45320.739 | 45519.4588 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000366808 | AL and GA, Various Ciena 6500 Card Removal Ring 3N | Low | Successful | Minor | Planned | GPB | TT | 45313.404 | 45320.75 | 45321.9583 | 45320.75 | 45321.9583 | 45322.5865 | 45322.5866 | 2024 | 2024-01 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45317.4455 | 45317.4276 | 45320.739 | 45322.5866 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000366903 | GA, Macon and Atlanta, Ciena 6500 ADM Module Re-configuration | Medium | Successful | Moderate | Planned | GPB | TT | 45313.432 | 45322.7083 | 45323 | 45322.7083 | 45323 | 45323.49 | 45323.4902 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45314.5511 | 45314.4126 | 45322.6959 | 45323.4902 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000367118 | AL, Wetumpka A9235, upgrade LTE controller software | Low | Successful | Minor | Planned | JBT | TT | 45314.5893 | 45321.125 | 45321.1458 | 45321.125 | 45321.1458 | 45321.3808 | 45321.381 | 2024 | 2024-01 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JBT | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45317.4491 | 45317.4289 | 45321.114 | 45321.381 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000367230 | AL, Camden Local Office, Move Utility Power to Microwave | Low | Successful | Minor | Planned | JEN | TT | 45314.8474 | 45321.4583 | 45321.625 | 45321.4583 | 45321.625 | 45322.5878 | 45322.5879 | 2024 | 2024-01 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45317.4466 | 45317.4322 | 45321.4474 | 45519.4508 | 2024-Q1 | 2024-01 | 2024-Q1
CRQ000000367720 | AL, Citronelle ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45316.816 | 45328.375 | 45328.5 | 45328.375 | 45328.5 | 45328.625 | 45328.6251 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.7514 | 45320.6744 | 45328.3544 | 45328.6251 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000367806 | AL, Birmingham, splice fiber for FTD to Ishkooda cell site | Low | Successful | Minor | Planned | DWM | TT | 45316.4745 | 45344.7917 | 45345.125 | 45344.7931 | 45344.8569 | 45345.4417 | 45345.4428 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45321.3848 | 45320.6866 | 45344.7786 | 45519.4679 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000367838 | GA, Currahee Mountain ENODEB, Generator Transfer Switch Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45316.8049 | 45328.375 | 45328.6667 | 45328.375 | 45328.6667 | 45329.4673 | 45329.4675 | 2024 | 2024-02 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.7509 | 45320.6737 | 45328.3544 | 45329.4675 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000367839 | AL, Chatom ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45316.8243 | 45328.5 | 45328.7083 | 45328.5 | 45328.7083 | 45329.4679 | 45329.4681 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.7547 | 45320.6751 | 45328.4794 | 45329.4681 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000368609 | GA, AL, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45320.4777 | 45335.375 | 45335.9993 | 45335.375 | 45335.7285 | 45336.4191 | 45336.4192 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45321.3838 | 45320.6849 | 45335.362 | 45336.4192 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000368613 | AL, Marion EBTS A9433, adding CBRS to the Existing Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45320.5103 | 45334.4583 | 45338.7917 | 45334.4583 | 45338.7917 | 45341.6608 | 45341.6609 | 2024 | 2024-02 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45320.7519 | 45320.6829 | 45334.4453 | 45341.6609 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000368618 | AL, McIntosh ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45320.6172 | 45329.375 | 45329.6667 | 45329.375 | 45329.6667 | 45330.5729 | 45330.5731 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.7542 | 45320.6757 | 45329.362 | 45330.5731 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000368717 | AL, Bay Minette ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45320.6212 | 45330.375 | 45330.5 | 45330.375 | 45330.5 | 45331.6056 | 45331.6058 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.753 | 45320.6763 | 45330.3614 | 45331.6058 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000368719 | AL, Flomaton ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45320.6264 | 45330.5 | 45330.6667 | 45330.5 | 45330.6667 | 45331.608 | 45331.6081 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45320.7525 | 45320.6769 | 45330.4865 | 45331.6081 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369014 | MS, West Biloxi EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45321.6132 | 45335.4167 | 45335.625 | 45335.4167 | 45335.625 | 45335.666 | 45335.6661 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45324.4213 | 45323.6659 | 45335.4037 | 45335.6661 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369017 | MS, Saucier EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45321.6208 | 45337.4167 | 45337.625 | 45337.4167 | 45337.625 | 45338.4565 | 45338.4566 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45324.4223 | 45323.6678 | 45337.4037 | 45338.4566 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369110 | MS, Bayou LaCroix, Splice New Drop Cable into 144-fiber East-West Cable | Low | Successful | Minor | Unplanned | DRB | TT | 45321.5171 | 45337.375 | 45337.75 | 45337.4528 | 45337.7035 | 45338.4541 | 45338.4542 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45337.397 | 45329.4935 | 45337.4037 | 45338.4542 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369117 | MS, North Gulfport EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45321.607 | 45334.4167 | 45334.625 | 45334.4167 | 45334.625 | 45334.6621 | 45334.6622 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45324.4198 | 45323.6653 | 45334.4036 | 45334.6622 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369123 | GA, Tarrytown & Newell ILA's Installing a new string of batteries. | Low | Successful | Minor | Planned | SDG | TT | 45321.8525 | 45335.9167 | 45336.25 | 45336.0417 | 45336.0861 | 45336.4218 | 45336.4219 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45324.4232 | 45323.6686 | 45335.9036 | 45336.4219 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369124 | GA, Tarrytown & Newell ILA's Installing a new string of batteries. (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45321.8525 | 45336.9167 | 45337.25 | 45336.9167 | 45337.25 | 45337.4445 | 45337.4446 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45324.4233 | 45323.6691 | 45336.9036 | 45337.4446 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369203 | MS, Kiln, Splice 36-Fiber Drop Cable to 144-fiber East-West Cable/Rework Fibers | Low | Successful | Minor | Planned | DRB | TT | 45322.4178 | 45342.375 | 45342.7917 | 45342.4062 | 45342.725 | 45343.3948 | 45343.3949 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.4804 | 45323.6707 | 45342.3619 | 45343.3949 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369215 | AL, Tuscaloosa, Yacht Club DS, connecting C spire fibers 93-94 in and out of splice | Low | Successful | Minor | Planned | DWM | TT | 45322.6569 | 45349.7917 | 45350.0833 | 45349.7917 | 45349.9076 | 45351.4066 | 45351.4067 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45324.5141 | 45323.6729 | 45349.7786 | 45519.4679 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369305 | MS, Kiln, Splice 36-Fiber Drop Cable to 144-fiber East-West Cable/Rework Fibers (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45322.4181 | 45343.375 | 45343.7917 | 45343.375 | 45343.7917 | 45344.678 | 45344.6786 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.4804 | 45323.6715 | 45343.362 | 45344.6786 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369630 | AL, Talladega EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45323.5561 | 45330.4167 | 45330.625 | 45330.4167 | 45330.625 | 45331.607 | 45331.6071 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45324.4191 | 45323.663 | 45330.4031 | 45331.6071 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369632 | AL, Altamont EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45323.5681 | 45337.4167 | 45337.625 | 45337.4167 | 45337.625 | 45338.456 | 45338.4561 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45324.4218 | 45323.667 | 45337.4037 | 45338.4561 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000369646 | MS, Marion, Move RLH CHB from Hatt SW Sub to Marion SE Sub (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45323.6764 | 45344.4167 | 45344.7083 | 45344.0604 | 45344.0639 | 45344.6796 | 45344.6797 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.4805 | 45327.4383 | 45344.4036 | 45344.6797 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370501 | Advisory/Oper Event: AL - MORGAN CITY - FIBER MAINTENANCE - NCC16701 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45327.3321 | 45329.0417 | 45329.25 | 45328.9812 | 45329.1792 | 45329.313 | 45329.3131 | 2024 | 2024-02 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.3376 | 45327.3376 | 45329.0286 | 45329.3131 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370508 | AL, Tuscaloosa, Good Springs TS, Splicing dark fibers | Low | Successful | Minor | Planned | DWM | TT | 45327.4625 | 45349.7917 | 45350.25 | 45349.7917 | 45350.25 | 45351.4055 | 45351.4056 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45329.5561 | 45329.497 | 45349.7786 | 45519.4679 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370509 | AL, Tuscaloosa, Good Springs TS, Splicing dark fibers (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45327.4626 | 45350.7917 | 45351.25 | 45350.7917 | 45351.25 | 45351.406 | 45351.4061 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45329.5561 | 45329.4981 | 45350.7792 | 45519.4679 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370520 | Advisory/Oper Event: AL - FL - VARIOUS LOCATIONS - CIRCUIT MIGRATIONS - NCC16631 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45327.6045 | 45357.0417 | 45357.25 | 45357.0417 | 45357.1778 | 45357.2981 | 45357.4232 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.6257 | 45327.6257 | 45357.029 | 45357.4232 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000370611 | Advisory/Oper Event: AL - FL - VARIOUS LOCATIONS - CIRCUIT MIGRATIONS - NCC16631 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45327.5861 | 45356.0417 | 45356.25 | 45356.0417 | 45356.25 | 45356.3977 | 45356.3978 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.6258 | 45327.6258 | 45356.0292 | 45356.3978 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000370700 | Advisory/Oper Event: AL - VARIOUS LOCATIONS - EQUIPMENT UPGRADES - NCC16790 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45327.3615 | 45338 | 45338.5 | 45337.9681 | 45338.1528 | 45338.2957 | 45338.2958 | 2024 | 2024-02 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45327.3664 | 45327.3664 | 45337.9896 | 45338.2958 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370709 | GA, Marietta, Big Shanty Transport, Replace Ciena 6500 CMD Module. | Medium | Successful | Moderate | Planned | ADL | TT | 45327.6641 | 45342.75 | 45343 | 45342.75 | 45342.7917 | 45343.3981 | 45343.3983 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45329.5934 | 45329.4949 | 45342.7369 | 45343.3983 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370710 | GA, Marietta, Big Shanty Transport, Replace Ciena 6500 CMD Module. (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45327.6643 | 45343.75 | 45344 | 45343.75 | 45344 | 45344.5134 | 45344.5137 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45329.5947 | 45329.4955 | 45343.7369 | 45344.5137 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370824 | AL, Jasper, Splicing dark fibers for C-spire | Low | Successful | Minor | Planned | DKG | TT | 45328.6562 | 45335.2917 | 45336.7917 | 45335.2917 | 45336.7917 | 45337.444 | 45337.4442 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45329.5184 | 45329.4892 | 45335.2787 | 45519.4588 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370826 | AL, Abbeville, Splicing dark fibers for Great Southern Wood | Low | Successful | Minor | Planned | DKG | TT | 45328.6724 | 45335.75 | 45336.0417 | 45335.8368 | 45336.0417 | 45336.4207 | 45336.4208 | 2024 | 2024-02 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45329.5191 | 45329.4899 | 45335.7369 | 45519.4588 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000370921 | AL, GREENE COUNTY STEAM PLANT, Clear UCAN/NPAD system errors | Low | Successful | Minor | Planned | DAP | TT | 45328.564 | 45343.4167 | 45343.5833 | 45343.4292 | 45343.5833 | 45344.5092 | 45344.5094 | 2024 | 2024-02 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45336.4044 | 45335.6602 | 45343.4037 | 45344.5094 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000371322 | GA, Atlanta, 270 Peachtree, Installing Breakers & Power to BDFB | Low | Successful | Minor | Planned | SDG | TT | 45329.8903 | 45343.9583 | 45344.25 | 45343.9903 | 45344.0354 | 45344.5143 | 45344.5145 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | SCS | OPERATIONS | STI | 45336.5948 | 45335.6584 | 45343.9452 | 45344.5145 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000371709 | AL, B'ham, Wilsonville, Montgomery Ciena Ring 3 Circuit Cuts Group 1 | Medium | Successful | Moderate | Planned | GPB | TT | 45331.4231 | 45341.75 | 45342 | 45341.75 | 45341.8354 | 45343.3913 | 45343.3918 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45336.4476 | 45331.5839 | 45341.7369 | 45343.3918 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000371713 | AL and GA, J ST, SDC, Macon Ciena Ring 3 Circuit Cuts Group 2 | Medium | Successful | Moderate | Planned | GPB | TT | 45331.4465 | 45342.75 | 45343 | 45342.75 | 45342.8632 | 45343.3973 | 45343.3975 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45336.447 | 45335.63 | 45342.7369 | 45343.3975 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000371714 | AL and GA, SDC, Columbus, Jackson, Macon Ciena Ring 3 Circuit Cuts Group 3 | Medium | Successful | Moderate | Planned | GPB | TT | 45331.4536 | 45343.75 | 45344 | 45343.75 | 45343.8438 | 45344.5126 | 45344.513 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45336.4452 | 45335.6617 | 45343.7369 | 45344.513 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000372621 | GA, Augusta. Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45334.6654 | 45363.375 | 45363.9993 | 45363.5104 | 45363.6549 | 45364.5512 | 45364.5514 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45348.8474 | 45343.4644 | 45363.3619 | 45364.5514 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000372624 | AL, Plant Farley, EBTS/Transport, Replace control board on Generator ATS | Low | Successful | Minor | Planned | TRC | TT | 45334.6779 | 45342.3958 | 45343.0208 | 45342.4285 | 45343.0056 | 45343.396 | 45343.3961 | 2024 | 2024-02 | Successful | Facilities Component | Generator | Repair | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45341.3875 | 45335.6264 | 45342.3758 | 45519.476 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000372712 | GA, Chester, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45334.641 | 45362.375 | 45362.9993 | 45362.375 | 45362.8167 | 45363.4034 | 45363.4037 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45349.3472 | 45343.461 | 45362.3615 | 45363.4037 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000372806 | AL, Michigan Ave ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45335.4055 | 45342.5 | 45342.7083 | 45342.5 | 45342.7083 | 45343.3966 | 45343.3967 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45336.5878 | 45335.6155 | 45342.487 | 45343.3967 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000372904 | AL, SW Mobile ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45335.4088 | 45343.375 | 45343.5 | 45343.375 | 45343.5 | 45344.5062 | 45344.5063 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45338.49 | 45335.6545 | 45343.362 | 45344.5063 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000372905 | AL, Wheelerville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45335.4121 | 45343.5 | 45343.7083 | 45343.5 | 45343.7083 | 45344.5099 | 45344.5099 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45338.4904 | 45335.6553 | 45343.4871 | 45344.5099 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000372906 | AL, Hank Aaron Stadium ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45335.4156 | 45344.375 | 45344.5833 | 45344.375 | 45344.5833 | 45345.4407 | 45345.4412 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45338.4907 | 45338.4737 | 45344.362 | 45345.4412 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000373000 | AL, Toulminville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45335.4006 | 45342.375 | 45342.5 | 45342.375 | 45342.5 | 45343.394 | 45343.3942 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45336.5871 | 45335.6105 | 45342.3619 | 45343.3942 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000373013 | AL, Birmingham, APCO Bank Annex, Upgrade RADWIN RADIO | Low | Successful | Minor | Planned | MSM | TT | 45335.5729 | 45343.4167 | 45343.6667 | 45343.4313 | 45343.4701 | 45344.5052 | 45344.5053 | 2024 | 2024-02 | Successful | Transport Device | Microwave TX/RX (Unlicensed) | Upgrade/Modify | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45341.5614 | 45338.4754 | 45343.4037 | 45519.4508 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000373306 | GA, Bainbridge OH, communications room, Replace house UPS | Low | Successful | Minor | Planned | NSI | TT | 45336.4433 | 45346.375 | 45346.75 | 45346.3757 | 45346.6 | 45347.8213 | 45347.8215 | 2024 | 2024-02 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | NS | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45341.5619 | 45338.4775 | 45346.3627 | 45519.4801 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000373808 | AL, Hartsfield Jackson Substation, Turn down Swan Port | Low | Successful | Minor | Planned | DAP | TT | 45338.5201 | 45350.375 | 45350.4167 | 45350.3785 | 45350.4167 | 45351.4074 | 45351.4075 | 2024 | 2024-02 | Successful | Transport Device | Other Transport Device | Remove/Retire | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45348.8423 | 45343.4541 | 45350.362 | 45351.4075 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000373823 | AL, Wilmer EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45338.881 | 45348.4167 | 45348.5833 | 45348.4167 | 45348.5833 | 45348.6714 | 45348.6715 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45344.6072 | 45343.4525 | 45348.4036 | 45348.6715 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000374613 | GA, N. GA ICON Ring, Remove Port Group 4 & 5 | Medium | Successful | Moderate | Planned | RPY | TT | 45341.5748 | 45348.4167 | 45348.5625 | 45348.4271 | 45348.4951 | 45348.6696 | 45348.67 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45347.9461 | 45343.4489 | 45348.4036 | 45348.67 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000374817 | AL, Auburn, ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45342.6081 | 45350.5833 | 45350.7083 | 45350.5868 | 45350.6819 | 45351.4032 | 45351.4034 | 2024 | 2024-02 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45344.6076 | 45343.4552 | 45350.5709 | 45351.4034 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000374819 | AL, Auburn, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45342.6172 | 45352.375 | 45352.5417 | 45352.375 | 45352.5417 | 45355.4035 | 45355.4036 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45348.8463 | 45343.4563 | 45352.3615 | 45355.4036 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375025 | GA, WAYCROSS, TRANSPORT BUILDING, REPLACE ATS, GENERATOR | Low | Successful | Minor | Planned | MVW | TT | 45342.7467 | 45355.3333 | 45359.6667 | 45355.3333 | 45359.6667 | 45362.4458 | 45362.4459 | 2024 | 2024-03 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45344.61 | 45343.4579 | 45355.3202 | 45498.7092 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375126 | AL, B'ham, APCO HQ, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45343.6901 | 45357.375 | 45357.9993 | 45357.3951 | 45357.825 | 45358.405 | 45358.4054 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45349.3489 | 45345.4359 | 45357.3623 | 45358.4054 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375128 | AL, Lowndesboro EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45343.7516 | 45351.4167 | 45351.625 | 45351.4167 | 45351.625 | 45352.4042 | 45352.4043 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45347.8361 | 45345.4325 | 45351.4043 | 45352.4043 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375130 | MS, Leakesville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45343.9421 | 45349.4375 | 45349.6458 | 45349.4375 | 45349.6458 | 45349.671 | 45349.6711 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45348.8884 | 45345.4335 | 45349.419 | 45349.6711 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000375223 | AL, Selma EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45343.7482 | 45350.4167 | 45350.625 | 45350.4167 | 45350.625 | 45351.409 | 45351.4091 | 2024 | 2024-02 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45347.8356 | 45345.4314 | 45350.4036 | 45351.4091 | 2024-Q1 | 2024-02 | 2024-Q1
CRQ000000375309 | AL, Cheaha, Anniston, Nokia Wavence M/W radio, add 11GHz to existing 6GHz. (BACKUP DATE) | Low | Successful | Minor | Planned | WJL | TT | 45343.497 | 45380.3542 | 45380.8125 | 45380.3542 | 45380.8125 | 45383.4067 | 45383.4069 | 2024 | 2024-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45378.5835 | 45373.4318 | 45380.3342 | 45383.4068 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000375327 | AL, B'ham, APCO HQ, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45343.7004 | 45358.375 | 45358.9993 | 45358.4979 | 45358.7854 | 45359.3823 | 45359.3828 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45349.3483 | 45345.4382 | 45358.362 | 45359.3828 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375423 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 5 Group 1 | Medium | Successful | Moderate | Planned | ADL | TT | 45344.8909 | 45355.75 | 45355.9993 | 45355.75 | 45355.9993 | 45356.3963 | 45356.3967 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45349.5557 | 45349.5149 | 45355.7374 | 45356.3967 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375427 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 5 Group 3 | Medium | Successful | Moderate | Planned | ADL | TT | 45344.899 | 45357.75 | 45357.9993 | 45357.75 | 45357.7924 | 45358.408 | 45358.4082 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45349.6209 | 45349.5183 | 45357.7369 | 45358.4082 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375523 | AL, Fayette, Splicing in Fibers for AFN+Tombigbee | Low | Successful | Minor | Planned | DKG | TT | 45344.8453 | 45350.2917 | 45352.7917 | 45350.2917 | 45352.7917 | 45355.4011 | 45355.4013 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45348.8872 | 45348.6731 | 45350.2786 | 45519.4588 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375626 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 5 Group 2 | Medium | Successful | Moderate | Planned | ADL | TT | 45344.8896 | 45356.75 | 45356.9993 | 45356.75 | 45356.9993 | 45357.4143 | 45357.4151 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45349.5563 | 45349.5167 | 45356.7373 | 45357.4151 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375918 | GA, Alto Mtn, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45345.6243 | 45369.375 | 45369.9993 | 45369.3826 | 45369.7132 | 45370.3974 | 45370.3975 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45349.6906 | 45349.6612 | 45369.3616 | 45370.3975 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000375921 | GA, Albany, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45345.6394 | 45371.375 | 45371.9993 | 45371.375 | 45371.6014 | 45371.6123 | 45371.6137 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45349.7256 | 45349.6679 | 45371.3615 | 45371.6137 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000376200 | AL, Montgomery, Carmichael Rd EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45347.9594 | 45356.4167 | 45356.625 | 45356.4167 | 45356.625 | 45357.4135 | 45357.4138 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45349.7047 | 45349.6598 | 45356.4052 | 45357.4138 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000376439 | AL, Montgomery, splicing 24 fibers to Whitman Colo Hut | Low | Successful | Minor | Planned | DKG | TT | 45348.6959 | 45356.2917 | 45358.7917 | 45356.2917 | 45358.7917 | 45359.3857 | 45359.3858 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45349.7097 | 45349.6586 | 45356.28 | 45519.4588 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000376735 | AL, Tuscaloosa, Replace Damaged Fiber Jumper Between DWDM WSS cards at Tusc 4th St | Low | Successful | Minor | Planned | DRB | TT | 45349.7126 | 45358.75 | 45358.8333 | 45358.75 | 45358.8333 | 45359.3842 | 45359.3843 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45356.3205 | 45352.4095 | 45358.7376 | 45359.3843 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000376915 | AL, South Tuscaloosa TS to Eutaw TS, splice dark fibers | Low | Successful | Minor | Planned | DWM | TT | 45350.5759 | 45372.7917 | 45373.25 | 45372.7917 | 45373.25 | 45373.4499 | 45373.45 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45352.5677 | 45352.4244 | 45372.7779 | 45519.4679 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377012 | AL, Columbia EBTS A9488, Plant Farley, adding CBRS to existing Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45350.6356 | 45369.375 | 45373.8333 | 45369.55 | 45372.4861 | 45376.573 | 45376.5736 | 2024 | 2024-03 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45352.4814 | 45352.4206 | 45369.3616 | 45376.5735 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377103 | AL, Birmingham ICON Ring, AL P&C working on circuit | Low | Successful | Minor | Planned | RPY | TT | 45350.4394 | 45356.375 | 45356.75 | 45356.375 | 45356.75 | 45357.4123 | 45357.4124 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45352.4093 | 45352.4064 | 45356.3634 | 45357.4124 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377112 | AL, South Tuscaloosa TS to Alberta City SS, splice dark fibers | Low | Successful | Minor | Planned | DWM | TT | 45350.5462 | 45372.7917 | 45380.125 | 45372.7917 | 45373.7917 | 45377.4001 | 45377.4004 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45352.5668 | 45352.423 | 45372.7779 | 45519.4679 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377113 | AL, South Tuscaloosa TS to Alberta City SS, splice dark fibers (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45350.5463 | 45376.7917 | 45377.125 | 45376.7917 | 45377.125 | 45377.3915 | 45377.3957 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45352.5671 | 45352.4237 | 45376.7778 | 45519.4679 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377118 | AL, Various Sites, Cut SoNet WAN Ckts at Roanoke BO and Crew HQ to new COAM fiber. | Low | Successful | Minor | Planned | MPH | TT | 45350.5919 | 45363.75 | 45363.8333 | 45363.75 | 45363.8333 | 45364.5529 | 45364.5536 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45352.428 | 45352.4135 | 45363.7369 | 45364.5535 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377120 | GA, Atlanta, 270 Peachtree, Re-Installing Breakers & Power to BDFB | Low | Successful | Minor | Planned | SDG | TT | 45350.6697 | 45356.9375 | 45357.25 | 45356.9375 | 45357.0104 | 45357.4221 | 45357.4222 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45356.3207 | 45352.4071 | 45356.9178 | 45357.4222 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377313 | GA, LaGrange Transmission ROW, Splice new section of OPGW | Low | Successful | Minor | Planned | JLM | TT | 45351.5192 | 45367.2917 | 45367.75 | 45367.2937 | 45367.5917 | 45369.4225 | 45369.4226 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45355.6261 | 45355.4329 | 45367.2793 | 45519.4626 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377330 | AL, Birmingham APC HQ to S Bessemer, Ciena 6500 Fiber Connection | Medium | Successful | Moderate | Planned | GPB | TT | 45351.6426 | 45362.4583 | 45365.041 | 45362.4583 | 45365.041 | 45365.3766 | 45365.3771 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45352.5894 | 45352.5383 | 45362.4449 | 45365.3771 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377408 | AL, Goodsprings TS to Gorgas #1, splice fiber for FUN network | Low | Successful | Minor | Planned | DWM | TT | 45351.4725 | 45378.7917 | 45379.25 | 45378.8326 | 45379.0229 | 45379.4678 | 45379.4679 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45352.5684 | 45352.4264 | 45378.7786 | 45519.4679 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377512 | GA, PEARSON EBTS, REPLACE CHASSIS ON PEARSON - SOUTH PEARSON MINILINK MICROWAVE PATH | Low | Successful | Minor | Planned | WKA | TT | 45352.5325 | 45370.375 | 45370.5417 | 45370.3924 | 45370.5417 | 45370.5874 | 45370.5875 | 2024 | 2024-03 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45359.7222 | 45359.6765 | 45370.3619 | 45519.4801 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377518 | AL, B'ham, Leaf Lake, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45352.6034 | 45383.4167 | 45383.75 | 45383.4451 | 45383.5375 | 45384.4769 | 45384.4784 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45365.4826 | 45364.7035 | 45383.4049 | 45384.4784 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000377523 | AL, Bessemer TS Telecom, OLT Alarm and redundancy testing (BACKUP DATE) | Low | Successful | Minor | Planned | JGL | TT | 45352.6636 | 45371.4375 | 45371.5208 | 45371.4375 | 45371.5208 | 45372.4759 | 45372.4759 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45363.3856 | 45358.4266 | 45371.4171 | 45372.4759 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377617 | AL, Montgomery, Lake Martin, Abbeville, Cabinet ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45352.7183 | 45362.4167 | 45362.5417 | 45362.4215 | 45362.5312 | 45363.405 | 45363.4052 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45356.3211 | 45355.4382 | 45362.4032 | 45363.4052 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377618 | AL, Birmingham, Trussville, Alabaster, Cabinet ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45352.7287 | 45362.75 | 45362.875 | 45362.7549 | 45362.9243 | 45363.4061 | 45363.4061 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45356.3212 | 45355.4389 | 45362.7369 | 45363.4061 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000377710 | AL, Bessemer TS Telecom, OLT Alarm and redundancy testing | Low | Successful | Minor | Planned | JGL | TT | 45352.6636 | 45366.4167 | 45366.5 | 45366.4167 | 45366.5 | 45369.4212 | 45369.4213 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45363.3842 | 45358.4258 | 45366.4036 | 45369.4213 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378004 | AL, Fayette, Demopolis, Jasper, Cabinet ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45355.3813 | 45363.75 | 45363.875 | 45363.7701 | 45363.8118 | 45364.5647 | 45364.5654 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45356.3211 | 45355.4395 | 45363.7369 | 45364.5654 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378109 | AL, Greene County to Bassett Creek ICON Ring, Epipe addition | Low | Successful | Minor | Planned | RPY | TT | 45355.5038 | 45377.4167 | 45377.5417 | 45377.4167 | 45377.5417 | 45378.4629 | 45378.4629 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45356.5397 | 45356.4968 | 45377.4032 | 45378.4629 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378111 | AL, Mobile, Cabinet, ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45355.5154 | 45372.5833 | 45372.7083 | 45372.5889 | 45372.6042 | 45373.4487 | 45373.4488 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45365.4823 | 45356.4958 | 45372.5695 | 45373.4488 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378205 | AL, Anniston, Oxford, Cabinet, ONT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45355.3886 | 45365.375 | 45365.5 | 45365.3882 | 45365.4208 | 45365.482 | 45365.4821 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45356.3211 | 45355.4402 | 45365.3616 | 45365.4821 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378419 | GA, ATL ICON Ring, removed Norcross 1 and install it by Norcross 2 | Medium | Successful | Moderate | Planned | RPY | TT | 45356.5778 | 45420.3958 | 45420.7083 | 45420.4076 | 45420.5743 | 45420.7076 | 45420.7079 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45413.3969 | 45412.6773 | 45420.3848 | 45420.7079 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000378421 | AL, Mobile DCC, UPS PM's. | Low | Successful | Minor | Planned | TRC | TT | 45356.5793 | 45362.4583 | 45362.7083 | 45362.4583 | 45362.7083 | 45363.4055 | 45363.4056 | 2024 | 2024-03 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45356.7046 | 45356.5927 | 45362.4449 | 45519.476 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378425 | GA, Jackson Transport, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45356.6946 | 45364.375 | 45364.9993 | 45364.3799 | 45364.5333 | 45364.584 | 45364.5841 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45359.3835 | 45358.4326 | 45364.3619 | 45364.5841 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378426 | GA, Atlanta, 270 Peachtree, Removing lateral fiber from splice case | Low | Successful | Minor | Planned | SDG | TT | 45356.8154 | 45372.9167 | 45373.25 | 45372.9951 | 45373.1201 | 45373.4368 | 45373.4369 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Remove/Retire | Transport | SDG | APC |  | STI | 45363.3873 | 45358.6166 | 45372.9029 | 45373.4369 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378503 | GA, Macon, South Macon Transport Building, Re-splice 2 fiber connections | Low | Successful | Minor | Planned | JLM | TT | 45356.3737 | 45364.75 | 45364.9993 | 45364.75 | 45364.7812 | 45365.3777 | 45365.3778 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45356.541 | 45356.4944 | 45364.7362 | 45519.4626 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378514 | AL, Southern Division Complex Montgomery, UPS PM's. | Low | Successful | Minor | Planned | TRC | TT | 45356.5747 | 45359.4583 | 45359.7083 | 45359.4583 | 45359.7083 | 45362.4463 | 45362.4465 | 2024 | 2024-03 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45356.7043 | 45356.5918 | 45359.446 | 45519.476 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378625 | GA, Atlanta, Buckhead, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45357.7039 | 45371.4167 | 45371.5417 | 45371.4167 | 45371.4292 | 45371.4581 | 45371.4582 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45358.6148 | 45358.6064 | 45371.4032 | 45371.4582 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378627 | AL, Gadsden, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45357.7227 | 45386.375 | 45386.875 | 45386.384 | 45386.7764 | 45387.4125 | 45387.4128 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45365.4786 | 45364.7052 | 45386.3627 | 45387.4128 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000378817 | AL, Dadeville, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45357.6673 | 45372.4167 | 45372.9993 | 45372.4167 | 45372.9993 | 45373.4337 | 45373.4338 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45363.3833 | 45358.6087 | 45372.4037 | 45373.4338 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000378924 | Atlanta / Birmingham LTE Core Data Center: EPG/SSR Modifications | Medium | Successful | Moderate | Unplanned | GEB | TT | 45358.6818 | 45363.0417 | 45363.1667 | 45363.0674 | 45363.141 | 45363.4071 | 45363.4073 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | SCS | OPERATIONS | CORE NETWORK ENGINEERING | 45359.723 | 45359.6696 | 45363.0285 | 45363.4072 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000379022 | AL, Greensboro EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45358.9019 | 45379.375 | 45379.625 | 45379.375 | 45379.625 | 45380.4338 | 45380.434 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45364.6688 | 45364.6185 | 45379.3619 | 45380.434 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000379313 | AL, Holt Dam, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45359.4457 | 45376.375 | 45376.9993 | 45376.375 | 45376.6146 | 45376.624 | 45376.6249 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45365.4705 | 45364.6826 | 45376.3619 | 45376.6249 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000379417 | AL, Montgomery, Smiley Court EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45359.8834 | 45371.4167 | 45371.625 | 45371.4167 | 45371.625 | 45372.4753 | 45372.4754 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45369.6087 | 45366.3892 | 45371.4032 | 45372.4754 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000379819 | GA, Savannah ICON Ring, SWAP SFP ports at BLVD & River St ICON (BACKUP DATE) | Low | Successful | Minor | Planned | RPY | TT | 45362.6994 | 45399.5 | 45399.7083 | 45399.5083 | 45399.6431 | 45399.6529 | 45399.6535 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45365.4815 | 45364.7113 | 45399.4867 | 45399.6535 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000379912 | GA, ATL ICON Ring, installing Atlantic Drive SEL ICON | Low | Successful | Minor | Planned | RPY | TT | 45362.5308 | 45397.375 | 45397.5833 | 45397.3854 | 45397.6312 | 45398.394 | 45398.3941 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45365.4722 | 45364.6251 | 45397.3619 | 45398.3941 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000379913 | GA, ATL ICON Ring, installing Atlantic Drive SEL ICON (BACKUP DATE) | Low | Successful | Minor | Planned | RPY | TT | 45362.5309 | 45400.375 | 45400.5833 | 45400.4187 | 45400.5618 | 45400.5892 | 45400.5895 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45365.4726 | 45364.6259 | 45400.3634 | 45400.5895 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000380032 | MS, Lyman EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45363.682 | 45372.4167 | 45372.625 | 45372.4167 | 45372.625 | 45373.4481 | 45373.4482 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45365.4679 | 45364.678 | 45372.4037 | 45373.4482 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380036 | AL, BIRMINGHAM, APC CORP, INSTALLING NEW DC POWER CONNECTION | Low | Successful | Minor | Planned | SDG | TT | 45363.7107 | 45377.375 | 45378.25 | 45378.0604 | 45378.1507 | 45378.4615 | 45378.4616 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | SDG | APC |  | STI | 45365.4713 | 45364.6869 | 45377.3615 | 45378.4616 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380131 | MS, Waveland EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45363.6781 | 45371.4167 | 45371.625 | 45371.4167 | 45371.625 | 45372.4748 | 45372.4749 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45365.4674 | 45364.6771 | 45371.4032 | 45372.4749 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380133 | GA, Hoschton Substation, Line cut and move | Low | Successful | Minor | Planned | MAR | TT | 45363.8979 | 45381.2917 | 45381.7917 | 45381.2917 | 45381.7917 | 45383.4079 | 45383.408 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45365.4746 | 45364.6961 | 45381.2781 | 45519.4626 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000380313 | GA, Atlanta, 241 RALPH MCGILL LINC LTE, Migrate GPC Static APNS from ATL to BHM Core. | Medium | Successful | Moderate | Planned | RAS | TT | 45364.3817 | 45378.5833 | 45378.6667 | 45378.6681 | 45378.75 | 45379.4653 | 45379.4663 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RAS | COM |  | CORE NETWORK ENGINEERING | 45365.4785 | 45364.6918 | 45378.5702 | 45379.4663 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380314 | AL, Birmingham, APC CORP HQ LINC LTE, Migrate all APC Static devices from ATL to BHM. | Medium | Successful | Moderate | Planned | RAS | TT | 45364.3875 | 45378.5833 | 45378.6667 | 45378.6694 | 45378.75 | 45379.4657 | 45379.4662 | 2024 | 2024-03 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RAS | COM |  | CORE NETWORK ENGINEERING | 45365.4774 | 45364.6904 | 45378.5702 | 45379.4662 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380328 | GA, Atlanta/Douglas Hills, Migrate EMS Circuit to ADM | Low | Successful | Minor | Planned | ADL | TT | 45364.5897 | 45372.4167 | 45372.7083 | 45372.4167 | 45372.7083 | 45373.4777 | 45373.4778 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45365.4687 | 45364.6798 | 45372.4037 | 45373.4778 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380605 | GA, ATLANTA, PDK AIRPORT COMM ROOM, REPLACEMENT OF 9170 UPS | Low | Successful | Minor | Planned | MVW | TT | 45365.386 | 45374.25 | 45374.7083 | 45374.2694 | 45374.5687 | 45376.5743 | 45376.5748 | 2024 | 2024-03 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45365.4736 | 45365.4182 | 45374.2365 | 45498.7092 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380615 | GA, Macon and Atlanta GPC HQ, Ciena 6500 ADM and T-Series Re-configuration | Low | Successful | Minor | Planned | GPB | TT | 45365.4883 | 45376.75 | 45377 | 45376.7507 | 45377 | 45377.3906 | 45377.3956 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45370.3813 | 45369.4085 | 45376.7362 | 45377.3956 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000380625 | AL and GA, Various Ciena 6500 Circuit Cuts Ring 3S | Medium | Successful | Moderate | Planned | GPB | TT | 45365.663 | 45390.75 | 45393 | 45390.7382 | 45390.9167 | 45391.7925 | 45391.7946 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45373.584 | 45373.425 | 45390.7362 | 45391.7946 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000380628 | GA, Smyrna, Plant McDonough 230kv Substation, Re-terminate FDP | Low | Successful | Minor | Planned | JLM | TT | 45365.6842 | 45377.3333 | 45377.75 | 45377.3333 | 45377.4896 | 45378.4598 | 45378.4599 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45370.4202 | 45369.4109 | 45377.3198 | 45519.4626 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000381023 | AL, Abbeville, Eclectic, Tallassee, Dadeville, Cabinet OLT Firmware Upgrade | Low | Successful | Minor | Planned | NNU | TT | 45366.625 | 45386.375 | 45386.6667 | 45386.3799 | 45386.4993 | 45386.6282 | 45386.6283 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45370.4315 | 45369.472 | 45386.3627 | 45386.6283 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000381726 | AL, Demopolis EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45369.6937 | 45377.4167 | 45377.625 | 45377.4167 | 45377.625 | 45378.4624 | 45378.4625 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45371.7791 | 45370.6433 | 45377.4032 | 45378.4625 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000381729 | AL, Birmingham area, 11 Linc RAN Sites software upgrade to 23.Q4 | Medium | Successful | Moderate | Planned | MJR | TT | 45369.7409 | 45376.9583 | 45377.0833 | 45376.9583 | 45377.0833 | 45377.3922 | 45377.396 | 2024 | 2024-03 | Successful | Transport Device | Remote Terminal Unit (RTU) | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45372.345 | 45370.6424 | 45376.9445 | 45377.396 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000381730 | AL, Andalusia, Babbie EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45369.7719 | 45380.4583 | 45380.6667 | 45380.4583 | 45380.6667 | 45383.4073 | 45383.4075 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45371.7839 | 45370.6455 | 45380.4453 | 45383.4074 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000381731 | AL, Andalusia, Heath EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45369.7791 | 45379.4583 | 45379.6667 | 45379.4583 | 45379.6667 | 45380.4354 | 45380.4355 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45371.7826 | 45370.6448 | 45379.4453 | 45380.4355 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000381926 | AL, Brantley EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45369.7858 | 45378.4583 | 45378.6667 | 45378.4583 | 45378.6667 | 45379.4673 | 45379.4674 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45371.7805 | 45370.6441 | 45378.4448 | 45379.4674 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000381927 | AL, Roanoke, Cut East Roanoke SS SWAN ckt to Leaf Lake Hub. | Low | Successful | Minor | Planned | MPH | TT | 45369.7936 | 45398.4167 | 45398.5417 | 45398.4736 | 45398.6667 | 45399.4368 | 45399.437 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45391.6286 | 45391.6282 | 45398.4032 | 45399.437 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382110 | AL, Trussville, installing new fiber Panel at Turf Club Cross Connect. | Low | Successful | Minor | Planned | DKG | TT | 45370.4583 | 45376.3333 | 45378.7917 | 45376.3333 | 45378.7917 | 45379.4669 | 45379.4669 | 2024 | 2024-03 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45373.408 | 45370.6415 | 45376.3202 | 45519.4588 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000382235 | AL, Birmingham, moving ariel fiber near UAB | Low | Successful | Minor | Planned | DWM | TT | 45370.8227 | 45399.7917 | 45400.25 | 45399.8021 | 45400.25 | 45400.4525 | 45400.4527 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45373.4078 | 45371.6255 | 45399.78 | 45519.4679 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382302 | AL, Dothan, Install ADM Cards/Turn Up 100G Links Between Dothan-Farley-Webb | Medium | Successful | Moderate | Planned | DRB | TT | 45371.3766 | 45378.4167 | 45378.75 | 45378.4167 | 45378.75 | 45379.4634 | 45379.4638 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45373.4108 | 45371.6193 | 45378.4032 | 45379.4638 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000382312 | AL, Plant Farley, EBTS/Transport, DC Plant replace battery cell | Low | Successful | Minor | Planned | TRC | TT | 45371.5246 | 45377.375 | 45377.7292 | 45377.3965 | 45377.7403 | 45378.4607 | 45378.4608 | 2024 | 2024-03 | Successful | Facilities Component | DC Backup System | Repair | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45371.7819 | 45371.6159 | 45377.3615 | 45519.476 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000382324 | GA, Plant Vogtle, Various sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45371.6148 | 45391.375 | 45391.9993 | 45391.3806 | 45391.6806 | 45391.6948 | 45391.6971 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45373.5833 | 45373.4901 | 45391.3615 | 45391.6971 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382335 | AL, Montgomery Jefferson St, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45371.7069 | 45383.4167 | 45383.5417 | 45383.4167 | 45383.4431 | 45383.4461 | 45383.4462 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45373.5763 | 45373.4803 | 45383.4049 | 45383.4461 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382511 | GA, Douglas Hills/Rome, Reconfigure 100G MOTR Channels | Low | Successful | Minor | Planned | ADL | TT | 45371.5263 | 45379.4167 | 45379.6667 | 45379.4854 | 45379.5132 | 45380.4346 | 45380.4347 | 2024 | 2024-03 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45373.5793 | 45373.5184 | 45379.4036 | 45380.4347 | 2024-Q1 | 2024-03 | 2024-Q1
CRQ000000382609 | AL, Montgomery, Cabinet OLT firmware upgrade | Low | Successful | Minor | Planned | NNU | TT | 45372.395 | 45390.375 | 45390.5 | 45390.3771 | 45390.4354 | 45390.5392 | 45390.5399 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45373.5782 | 45373.4821 | 45390.3618 | 45390.5398 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382614 | MS, Hattiesburg Area, Fiber Relocation/New Bypass Due to Transmission Line Rework | Low | Successful | Minor | Planned | DRB | TT | 45372.4468 | 45397.9583 | 45398.3333 | 45397.9583 | 45398.0403 | 45398.3963 | 45398.3964 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3454 | 45391.7286 | 45397.9446 | 45398.3964 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382617 | AL, Fayette, Jasper Cabinet, OLT firmware upgrade | Low | Successful | Minor | Planned | NNU | TT | 45372.4548 | 45391.75 | 45391.9583 | 45391.75 | 45391.9583 | 45392.4194 | 45392.4196 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45373.5804 | 45373.5794 | 45391.7292 | 45392.4196 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382618 | AL, Mobile Cabinet, OLT Firmware Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | NNU | TT | 45372.463 | 45394.375 | 45394.5417 | 45394.3792 | 45394.4951 | 45396.9429 | 45396.9433 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45379.6974 | 45373.5814 | 45394.3628 | 45396.9433 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382815 | AL, Wilsonville, ASR903 LTE Aggregation Router Software Upgrade | Low | Successful | Minor | Planned | DRI | TT | 45372.6865 | 45386.5417 | 45386.5833 | 45386.5431 | 45386.5938 | 45386.6295 | 45386.6297 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45373.6124 | 45373.5823 | 45386.5285 | 45386.6297 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382912 | AL, Birmingham ICON Ring. BOC Gases ICON being moved within same shelter | Medium | Successful | Moderate | Unplanned | RPY | TT | 45373.5217 | 45390.375 | 45390.7917 | 45390.375 | 45390.7361 | 45391.3327 | 45391.3375 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45387.4503 | 45387.4318 | 45390.3619 | 45391.3375 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000382923 | AL, MS, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45373.6779 | 45391.375 | 45391.9993 | 45391.3806 | 45391.7722 | 45391.787 | 45391.7872 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45379.6936 | 45376.4878 | 45391.3615 | 45391.7872 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383014 | GA, Macon, Various sites, NOKIA SAR Software Upgrades (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45373.5952 | 45400.375 | 45400.9993 | 45400.375 | 45400.6792 | 45401.3974 | 45401.3975 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45379.695 | 45376.4941 | 45400.3634 | 45401.3975 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383017 | MS, Kiln, Reconfigure fiber splices (Kiln Sub 36-Fiber Drop Cable to 144-Fiber Cable) | Low | Successful | Minor | Planned | DRB | TT | 45373.629 | 45384.375 | 45384.75 | 45384.375 | 45384.584 | 45385.4623 | 45385.4624 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45383.9567 | 45376.566 | 45384.3633 | 45385.4624 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383116 | AL, Mobile, splicing in four COAM Dark Fibers | Low | Successful | Minor | Planned | DKG | TT | 45373.9698 | 45383.3333 | 45386.7917 | 45383.3333 | 45386.7917 | 45387.4346 | 45387.4349 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45379.6975 | 45376.4842 | 45383.3216 | 45519.4588 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383511 | AL, Summerfield EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45376.6013 | 45384.4167 | 45384.625 | 45384.4167 | 45384.625 | 45385.4634 | 45385.4635 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45378.5857 | 45377.4795 | 45384.405 | 45385.4635 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383608 | AL, Fort Deposit EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45376.6347 | 45384.4583 | 45384.6667 | 45384.4583 | 45384.6667 | 45385.4638 | 45385.4639 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45378.5863 | 45377.4802 | 45384.4467 | 45385.4639 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383609 | AL, Ramer EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45376.6412 | 45386.4583 | 45386.6667 | 45386.4583 | 45386.6667 | 45387.4353 | 45387.4355 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45378.5871 | 45377.482 | 45386.4462 | 45387.4355 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383612 | GA, WAYNESBORO, PLANT VOGTLE 3&4 BLDGS 147A/B, GENERATOR EXERCISE ASSUMING LOAD | Low | Successful | Minor | Planned | WKA | TT | 45376.7057 | 45386.375 | 45386.625 | 45386.4097 | 45386.5549 | 45386.6272 | 45386.6273 | 2024 | 2024-04 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45378.5888 | 45377.4838 | 45386.3627 | 45519.4801 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383708 | MS, Gulfport Alternate Control Center, UPS upgrade | Low | Successful | Minor | Planned | KNL | TT | 45376.6338 | 45383.7083 | 45383.9993 | 45383.7688 | 45383.9139 | 45384.4751 | 45384.4752 | 2024 | 2024-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45378.4095 | 45377.4768 | 45383.6966 | 45498.7092 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000383710 | AL, North Georgiana EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45376.6383 | 45385.4583 | 45385.6667 | 45385.4583 | 45385.6667 | 45386.4009 | 45386.401 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45378.5867 | 45377.4812 | 45385.4502 | 45386.401 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000384803 | AL, Anniston, Oxford, Cabinet OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45380.53 | 45397.5417 | 45397.7083 | 45397.5444 | 45397.5861 | 45398.4039 | 45398.404 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.6873 | 45385.4652 | 45397.5278 | 45398.404 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000384808 | AL, Demopolis, Cabinet, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45380.6256 | 45398.75 | 45398.875 | 45398.7528 | 45398.8604 | 45399.4266 | 45399.4267 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.6161 | 45384.5988 | 45398.7362 | 45399.4267 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000384900 | MS, GULFPORT COAST SERVICE CENTER\TRANSPORT, UPS UPGRADE (BACKUP DATE) | Low | Successful | Minor | Planned | KNL | TT | 45380.4583 | 45397.75 | 45397.9993 | 45397.7521 | 45397.7972 | 45398.395 | 45398.3951 | 2024 | 2024-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45387.362 | 45384.5865 | 45397.7362 | 45498.7092 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000384906 | AL, Tuscaloosa, Cabinet, OLT Firmware Upgrade | Low | Successful | Minor | Planned | NNU | TT | 45380.5482 | 45400.375 | 45400.5 | 45400.3847 | 45400.4229 | 45400.5937 | 45400.5938 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.6169 | 45384.6006 | 45400.3634 | 45400.5938 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385302 | GA, Albany Operating Headquarters, 9170 UPS End of Life Replacement | Low | Successful | Minor | Planned | HFL | TT | 45383.3797 | 45393.3333 | 45393.7083 | 45393.3292 | 45393.491 | 45394.3425 | 45394.3427 | 2024 | 2024-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | HEF | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45387.3629 | 45384.5935 | 45393.3203 | 45498.7092 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385312 | AL, Elliotsville, Shades Crest, Bessemer, Cabinet, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45383.4676 | 45404.375 | 45404.5417 | 45404.3812 | 45404.4396 | 45404.7508 | 45404.7516 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.6843 | 45384.6019 | 45404.3619 | 45404.7516 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385314 | AL, Helena, Alabaster, Cabinet, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45383.4739 | 45405.75 | 45405.9167 | 45405.7562 | 45405.8313 | 45406.3245 | 45406.3246 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.686 | 45384.6032 | 45405.7369 | 45406.3246 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385315 | AL, Birmingham, Cabinet, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45383.4791 | 45407.375 | 45407.5417 | 45407.3785 | 45407.45 | 45408.4885 | 45408.4887 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45386.6867 | 45384.6038 | 45407.3636 | 45408.4887 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385417 | GA, Savannah/Kettle Creek, Migrate DWDM Ring 1 to New Section of Underground Fiber. (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45383.9525 | 45393.75 | 45393.9993 | 45393.7625 | 45393.9993 | 45394.3486 | 45394.3496 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45386.6427 | 45384.5915 | 45393.7377 | 45394.3496 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385715 | AL, Rainbow City EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45384.5495 | 45413.4167 | 45413.625 | 45413.4167 | 45413.625 | 45414.4075 | 45414.4076 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.5586 | 45407.4785 | 45413.3989 | 45414.4076 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000385716 | AL, Centre EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45384.5526 | 45394.4167 | 45394.625 | 45394.4167 | 45394.625 | 45396.9437 | 45396.9439 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45387.3669 | 45384.6513 | 45394.4045 | 45396.9439 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385928 | AL, Tuscaloosa, resplice 3 dark fibers between So Tuscaloosa and Alberta City SS | Low | Successful | Minor | Planned | DWM | TT | 45385.8666 | 45407.7917 | 45407.9583 | 45407.7917 | 45407.9583 | 45408.4916 | 45408.4917 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45386.6886 | 45386.5198 | 45407.7793 | 45519.4679 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000385929 | AL, Tuscaloosa, resplice 3 dark fibers between So Tuscaloosa and Alberta City SS (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45385.8666 | 45411.7917 | 45411.9583 | 45411.7917 | 45411.9583 | 45412.3952 | 45412.3954 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45404.5645 | 45404.5059 | 45411.7737 | 45519.4679 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386013 | AL, Holt TS, resplice 3 dark fibers from Holt COLO to Gorgas M/W | Low | Successful | Minor | Planned | DWM | TT | 45385.8823 | 45408 | 45408.25 | 45408 | 45408.1146 | 45408.4927 | 45408.4929 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45386.6897 | 45386.5217 | 45407.9877 | 45519.4679 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386014 | AL, Holt TS, resplice 3 dark fibers from Holt COLO to Gorgas M/W (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45385.8824 | 45412 | 45412.2083 | 45412 | 45412.2083 | 45412.396 | 45412.3962 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45401.4393 | 45400.5984 | 45411.982 | 45519.4679 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386106 | AL, Trussville, Splicing dark fibers for CSpire Handoff | Low | Successful | Minor | Planned | DKG | TT | 45386.4213 | 45392.25 | 45393.75 | 45392.4146 | 45393.75 | 45394.3575 | 45394.3577 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45386.6179 | 45386.5186 | 45392.2292 | 45519.4588 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386111 | AL, All Alabama LTE Sites, LTE RAN 23.Q4.4 Software Upgrades | Medium | Successful | Moderate | Planned | MJR | TT | 45386.4792 | 45397.9583 | 45398.2083 | 45397.9785 | 45398.1854 | 45398.4048 | 45398.4051 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45387.4052 | 45386.6231 | 45397.9446 | 45398.4051 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386113 | GA, All Georgia LTE Sites, LTE RAN 23.Q4.4 Software Upgrades | Medium | Successful | Moderate | Planned | MJR | TT | 45386.4912 | 45398.9583 | 45399.2083 | 45398.9583 | 45399.2083 | 45399.4388 | 45399.4391 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45387.4055 | 45386.6248 | 45398.9447 | 45399.4391 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386116 | MS & FL, All Mississippi and Florida LTE Sites, LTE RAN 23.Q4.4 Software Upgrades | Medium | Successful | Moderate | Planned | MJR | TT | 45386.5059 | 45399.9583 | 45400.7083 | 45399.9583 | 45400.7083 | 45401.3932 | 45401.3934 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45387.4063 | 45386.6484 | 45399.9466 | 45401.3934 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386409 | AL, Millbrook EBTS, Rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45387.5048 | 45402.4167 | 45402.6667 | 45402.4493 | 45402.6389 | 45404.5046 | 45404.5048 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45390.7084 | 45390.5473 | 45402.4036 | 45404.5048 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386410 | GA, N GA ICON Ring, Remove unused ethernet circuits | Low | Successful | Minor | Planned | RPY | TT | 45387.5256 | 45398.3958 | 45398.5417 | 45398.4125 | 45398.6368 | 45398.6422 | 45398.6434 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45390.5521 | 45387.6313 | 45398.3754 | 45398.6434 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386920 | AL, Dadeville, Camp Hill, rectifier plant replacement | Medium | Successful | Moderate | Planned | RBK | HH | 45390.5848 | 45398.4167 | 45398.625 | 45398.4167 | 45398.625 | 45399.4356 | 45399.4363 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45390.7153 | 45390.6588 | 45398.4032 | 45399.4363 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386925 | GA, PEARSON EBTS - REPLACE COAX ON PEARSON<>SOUTH PEARSON MINILINK | Low | Successful | Minor | Planned | WKA | HH | 45390.6308 | 45400.3333 | 45400.7083 | 45400.3333 | 45400.7083 | 45401.3962 | 45401.3963 | 2024 | 2024-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45394.5004 | 45392.6094 | 45400.3217 | 45519.4801 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000386926 | GA, PEARSON EBTS - REPLACE COAX ON PEARSON<>SOUTH PEARSON MINILINK BACKUP | Low | Successful | Minor | Planned | WKA | HH | 45390.6308 | 45404.3333 | 45404.7083 | 45404.4049 | 45404.4854 | 45404.7479 | 45404.7515 | 2024 | 2024-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45401.4691 | 45401.4689 | 45404.3202 | 45519.4801 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387011 | Georgia, Athens, Athens transport hub, test the generator with load | Low | Successful | Minor | Planned | PCM | HH | 45390.474 | 45400.375 | 45400.4583 | 45400.3812 | 45400.4535 | 45400.5931 | 45400.5932 | 2024 | 2024-04 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | PCM | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45390.7105 | 45390.6405 | 45400.3634 | 45519.4725 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387016 | AL, Highland Home, Highland Home EBTS, rectifier plant replacement | Medium | Successful | Moderate | Planned | RBK | HH | 45390.5648 | 45398.4583 | 45398.6667 | 45398.4583 | 45398.6667 | 45399.4375 | 45399.4378 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45393.3589 | 45391.3495 | 45398.4449 | 45399.4378 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387017 | AL, Banks, Perote EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45390.5678 | 45399.4583 | 45399.6667 | 45399.4583 | 45399.6667 | 45400.4518 | 45400.4521 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.4914 | 45391.7319 | 45399.445 | 45400.4521 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387018 | AL, Troy, Troy University EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | HH | 45390.5704 | 45400.4583 | 45400.6667 | 45400.4583 | 45400.6667 | 45401.398 | 45401.3981 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.4919 | 45391.738 | 45400.4467 | 45401.3981 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387020 | AL, Coker, Coker EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45390.5771 | 45400.4167 | 45400.625 | 45400.4167 | 45400.625 | 45400.6391 | 45400.6394 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.4931 | 45391.743 | 45400.4051 | 45400.6394 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387022 | AL, Collinsville, Collinsville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45390.5901 | 45400.4167 | 45400.625 | 45400.4167 | 45400.625 | 45400.6384 | 45400.6387 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.4935 | 45391.7468 | 45400.4051 | 45400.6387 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387025 | AL, Russellville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45390.6001 | 45407.4167 | 45407.5 | 45407.4167 | 45407.5 | 45408.4905 | 45408.4906 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45400.6912 | 45400.6413 | 45407.4052 | 45408.4906 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387026 | AL, Attalla, DuckSprings EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45390.6033 | 45401.4167 | 45401.625 | 45401.4167 | 45401.625 | 45404.5029 | 45404.503 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.4984 | 45391.7474 | 45401.4044 | 45404.503 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387027 | GA, ALINE, METTER EBTS - REPLACE WAVEGUIDE FLEX JUMPERS ON FOUR NOKIA WAVENCE RADIOS | Low | Successful | Minor | Planned | WKA | HH | 45390.6108 | 45404.3333 | 45404.7083 | 45404.4118 | 45404.7083 | 45404.7453 | 45404.7475 | 2024 | 2024-04 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45398.592 | 45398.5769 | 45404.3202 | 45519.4801 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387401 | MS, Gulfport, Landon Hub/Landon Substation Bandwidth Testing for Video Support | Low | Successful | Minor | Planned | DRB | HH | 45391.6392 | 45399.5417 | 45399.7917 | 45399.5604 | 45399.7917 | 45400.4481 | 45400.4484 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3453 | 45392.6198 | 45399.5299 | 45400.4484 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387403 | Birmingham AL APC HQ LTE Lab - LTE lab 9K routers to be powered down | Low | Successful | Minor | Planned | DRI | HH | 45391.6398 | 45399.4375 | 45399.5 | 45399.4375 | 45399.5069 | 45399.6545 | 45399.6549 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45392.8073 | 45392.6248 | 45399.4172 | 45399.6549 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387421 | GA Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | HH | 45391.7158 | 45398.375 | 45398.9993 | 45398.4132 | 45398.6514 | 45399.4296 | 45399.4297 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45392.6205 | 45391.7602 | 45398.3616 | 45399.4297 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387423 | MS, Long Beach, Equipment & Fiber Migration to New Long Beach Comm Rd Switch House | Low | Successful | Minor | Planned | DRB | HH | 45391.7583 | 45406.375 | 45406.75 | 45406.3639 | 45406.541 | 45406.5555 | 45406.5559 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3453 | 45392.6375 | 45406.362 | 45406.5559 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387501 | AL, Miller SP, Quinton, NOKIA SAR Software Upgrades (BACKUP) | Low | Successful | Minor | Planned | MPH | HH | 45391.6752 | 45404.4167 | 45404.8333 | 45404.4167 | 45404.8333 | 45404.983 | 45404.9834 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45392.6184 | 45391.7103 | 45404.4036 | 45404.9834 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387708 | AL and GA Various Ciena 6500 Circuit Cuts Ring 3S | Low | Successful | Minor | Planned | GPB | HH | 45392.4527 | 45404.75 | 45405 | 45404.75 | 45404.9111 | 45404.9839 | 45404.9852 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3453 | 45392.645 | 45404.7369 | 45404.9851 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387720 | GA, Clermont, Clermont ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | HH | 45392.6413 | 45405.3958 | 45405.5625 | 45405.3958 | 45405.5625 | 45406.3753 | 45406.3756 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45392.7462 | 45392.6535 | 45405.3758 | 45406.3756 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387722 | Alabama; Fayette, Jasper; Cabinet; OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | HH | 45392.6891 | 45400.75 | 45400.875 | 45400.7535 | 45400.825 | 45401.3986 | 45401.3987 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45400.4195 | 45394.3811 | 45400.7376 | 45401.3987 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387725 | GA Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | HH | 45393.0128 | 45399.3333 | 45399.9993 | 45399.3361 | 45399.7583 | 45400.4499 | 45400.45 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7046 | 45394.3966 | 45399.3199 | 45400.45 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387803 | AL, Wilsonville Ciena 6500 Circuit moves and module adds | Low | Successful | Minor | Planned | GPB | HH | 45392.4673 | 45406.75 | 45406.9583 | 45406.7569 | 45406.9583 | 45407.473 | 45407.4732 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3451 | 45392.6538 | 45406.7384 | 45407.4732 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387815 | GA Various sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Unplanned | MPH | HH | 45393.0872 | 45406.375 | 45406.9993 | 45406.3535 | 45406.7 | 45407.3316 | 45407.3343 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45405.4678 | 45405.4572 | 45406.362 | 45407.3343 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387916 | AL, Skinnerton, Skinnerton Regen - Reboot and/or Replace Slot 2 MLA3 Amp Card | Medium | Successful | Moderate | Planned | DRB | HH | 45392.6695 | 45400.75 | 45400.875 | 45400.75 | 45400.8486 | 45401.3914 | 45401.3917 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45398.4811 | 45398.4676 | 45400.7376 | 45401.3917 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387920 | EMERGENCY - AL, Birmingham, APC HQ, Linc LTE Data Center, Emergency Internet Connectivity Reset | Low | Successful | Minor | Unplanned | MJR | HH | 45392.7568 | 45393.125 | 45393.1458 | 45393.125 | 45393.1458 | 45394.3385 | 45394.3389 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Repair | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45392.806 | 45392.7711 | 45393.112 | 45394.3389 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387923 | MS, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | HH | 45393.0418 | 45404.375 | 45404.9993 | 45404.5556 | 45404.8333 | 45404.9799 | 45404.9812 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7046 | 45394.4052 | 45404.3619 | 45404.9812 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000387925 | MS, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | HH | 45393.0592 | 45405.375 | 45405.9993 | 45405.5285 | 45405.6681 | 45406.3186 | 45406.3188 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.706 | 45394.417 | 45405.3619 | 45406.3188 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388002 | GA, LaGrange Transmission ROW, Splice new section of OPGW | Low | Successful | Minor | Planned | MAR | HH | 45393.3811 | 45409.2917 | 45409.75 | 45409.2917 | 45409.75 | 45411.4106 | 45411.4203 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45398.4685 | 45394.4605 | 45409.4388 | 45519.4626 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388008 | MS, Wade, Migrate 12-Fiber OSP Cable to New Wade Telecom Bldg | Low | Successful | Minor | Planned | DRB | HH | 45393.4297 | 45400.375 | 45400.75 | 45400.375 | 45400.5299 | 45400.5949 | 45400.5951 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45394.3451 | 45393.5789 | 45400.3634 | 45400.5951 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388019 | MS, Pascagoula, Bypass Bayou Casotte substation due to Modernization Work | Low | Successful | Minor | Planned | DRB | HH | 45393.5806 | 45418.375 | 45418.75 | 45418.3764 | 45418.691 | 45418.7284 | 45418.7287 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45398.7039 | 45398.6388 | 45418.3577 | 45418.7287 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388033 | AL, Fort Payne, Fort Payne EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45394.0142 | 45407.4167 | 45407.6667 | 45407.4167 | 45407.6667 | 45408.49 | 45408.4901 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.5033 | 45394.4908 | 45407.4052 | 45408.4901 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388034 | AL, Wadley, East Wadley EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45394.0264 | 45407.4167 | 45407.625 | 45407.4167 | 45407.625 | 45408.4895 | 45408.4896 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.5048 | 45394.4911 | 45407.4052 | 45408.4896 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388103 | Georgia, Clarkesville, Plant Burton, Move Fiber Transport Cable at Driveway Entrance | Low | Successful | Minor | Planned | MAR | HH | 45393.3502 | 45400.3333 | 45400.75 | 45400.8465 | 45401.2278 | 45401.395 | 45401.3952 | 2024 | 2024-04 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45398.4682 | 45394.4402 | 45400.3217 | 45519.4626 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388130 | AL, Perdue Hill, Perdue Hill EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | HH | 45394.0082 | 45428.4583 | 45428.6667 | 45428.4583 | 45428.6667 | 45429.3716 | 45429.3719 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45406.4236 | 45406.4219 | 45428.4416 | 45429.3719 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388131 | AL, Collinsville, Lebanon EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45394.0179 | 45408.4167 | 45408.625 | 45408.4167 | 45408.625 | 45411.4078 | 45411.4199 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45394.5059 | 45394.4915 | 45408.4045 | 45411.4199 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388400 | MS, Gulfport, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45394.2195 | 45420.375 | 45420.9993 | 45420.375 | 45420.6667 | 45420.7055 | 45420.7057 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7074 | 45398.5156 | 45420.3571 | 45420.7057 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388425 | AL, Lay Dam, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45395.0337 | 45411.375 | 45411.9993 | 45411.375 | 45411.9993 | 45412.3927 | 45412.3933 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7067 | 45398.5009 | 45411.3661 | 45412.3933 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388427 | GA, Big Shanty, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45395.0525 | 45412.375 | 45412.9993 | 45412.375 | 45412.625 | 45412.6915 | 45412.6917 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45408.6384 | 45408.6372 | 45412.3571 | 45412.6917 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388500 | MS, Bayou Lacroix, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45394.2372 | 45425.375 | 45425.9993 | 45425.375 | 45425.9993 | 45426.3877 | 45426.388 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7074 | 45398.5174 | 45425.3576 | 45426.388 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388502 | AL, North Auburn, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45394.3006 | 45407.375 | 45407.9993 | 45407.375 | 45407.9993 | 45408.4827 | 45408.4828 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45398.7067 | 45398.4974 | 45407.3636 | 45408.4828 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388508 | GA, Atlanta, 689 Virginia Ave, (3) Powerware 9170 UPS Decommissioning | Low | Successful | Minor | Planned | HFL | TT | 45394.5283 | 45402.25 | 45402.625 | 45402.2528 | 45402.4194 | 45404.5037 | 45404.504 | 2024 | 2024-04 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Remove/Retire | Transport | HEF | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45398.5914 | 45398.4954 | 45402.2369 | 45498.7092 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000388510 | FL, Jacksonville, Cologix, Splicing Dark Fiber | Low | Successful | Minor | Planned | SDG | TT | 45394.5812 | 45413.9167 | 45414.25 | 45413.9167 | 45414.25 | 45414.4088 | 45414.4089 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | APC |  | STI | 45398.7074 | 45398.5088 | 45413.899 | 45414.4089 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388511 | FL, Jacksonville, Cologix, Splicing Dark Fiber (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45394.5813 | 45419.9167 | 45420.25 | 45419.4549 | 45420.0271 | 45420.4005 | 45420.4007 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | SDG | APC |  | STI | 45418.6288 | 45414.6911 | 45419.9078 | 45420.4007 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388516 | AL, Trussville Cabinet OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45394.6118 | 45412.75 | 45412.875 | 45412.75 | 45412.875 | 45413.5036 | 45413.5038 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45400.4216 | 45398.5069 | 45412.7322 | 45413.5038 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000388518 | AL, Birmingham, APC Corp Fiber RM 2/Rack, OLT Firmware Upgrades | Low | Successful | Minor | Planned | NNU | TT | 45394.6209 | 45414.75 | 45414.8333 | 45414.7549 | 45414.8076 | 45415.4393 | 45415.4395 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | NN | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45400.424 | 45398.5105 | 45414.7325 | 45415.4395 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000389109 | GA/AL, Various Sites, Testing New DWDMOT Integration WAN Circuits | Medium | Successful | Moderate | Planned | ADL | TT | 45397.6141 | 45404.3333 | 45404.6667 | 45404.3333 | 45404.6667 | 45404.7439 | 45404.7474 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45400.4615 | 45399.4475 | 45404.3202 | 45404.7474 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000389212 | GA, Thomaston ENODEB, DC Plant Modification | Low | Successful | Minor | Planned | LPE | TT | 45398.5144 | 45407.5 | 45407.5833 | 45407.5 | 45407.5833 | 45408.491 | 45408.4911 | 2024 | 2024-04 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45399.6382 | 45399.4554 | 45407.4886 | 45408.4911 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000389509 | GA, Draketown, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45399.4385 | 45406.375 | 45406.5417 | 45406.3951 | 45406.4313 | 45406.6165 | 45406.6171 | 2024 | 2024-04 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45399.6339 | 45399.4546 | 45406.362 | 45406.617 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000389525 | AL, South Alabama Area, Install ADMs at Snowdoun & Pinckard / Turn Up 100G Channels | Medium | Successful | Moderate | Planned | DRB | TT | 45399.6547 | 45406.4167 | 45406.6667 | 45406.384 | 45406.5542 | 45406.5578 | 45406.5598 | 2024 | 2024-04 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45405.4667 | 45401.4054 | 45406.4037 | 45406.5598 | 2024-Q2 | 2024-04 | 2024-Q2
CRQ000000390311 | AL, Bassett Creek, OPGW Can, Correct bad splices for AFN leased fiber | Low | Successful | Minor | Planned | DHA | TT | 45401.5777 | 45418.7917 | 45419.125 | 45418.7917 | 45419.125 | 45419.3961 | 45419.4086 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45412.4806 | 45407.551 | 45418.7745 | 45519.4679 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390712 | MS, PLANT DANIEL TELCOMM\COMMUNICATIONS ROOM, UPS UPGRADE | Low | Successful | Minor | Planned | KNL | TT | 45404.6158 | 45414.7083 | 45414.9993 | 45414.7083 | 45414.916 | 45415.4365 | 45415.4366 | 2024 | 2024-05 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45407.5544 | 45407.5429 | 45414.6908 | 45498.7092 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390714 | MS, PLANT WATSON EBTS, UPS UPGRADE | Low | Successful | Minor | Planned | KNL | TT | 45404.6245 | 45421.7083 | 45421.9993 | 45421.7465 | 45421.8965 | 45422.4433 | 45422.4434 | 2024 | 2024-05 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45407.9268 | 45407.5567 | 45421.6906 | 45498.7092 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390721 | AL, Butler, NorthButlerEBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45404.7219 | 45412.4583 | 45412.6667 | 45412.4583 | 45412.6667 | 45413.5027 | 45413.503 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.5461 | 45406.6393 | 45412.4404 | 45413.503 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390722 | AL, SweetWater, DixonsMIllEBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45404.7283 | 45413.4583 | 45413.6667 | 45413.4583 | 45413.6667 | 45414.408 | 45414.4082 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.5475 | 45406.6397 | 45413.4406 | 45414.4082 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390723 | AL, Thomasville, South Thomasville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45404.7311 | 45420.4583 | 45420.6667 | 45420.4583 | 45420.6667 | 45421.4334 | 45421.4335 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45413.4844 | 45408.642 | 45420.4404 | 45421.4335 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390724 | AL, Centreville, North Centreville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45404.9733 | 45415.4167 | 45415.625 | 45415.4167 | 45415.625 | 45418.3837 | 45418.384 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.5641 | 45407.5471 | 45415.3992 | 45418.384 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390817 | AL, Eclectic, Eclectic EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | HH | 45404.7074 | 45412.4167 | 45412.625 | 45412.4167 | 45412.625 | 45413.5015 | 45413.5018 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.5433 | 45406.6391 | 45412.3988 | 45413.5018 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390818 | AL, Cottondale, Paul Bryant HS EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45404.7134 | 45414.4167 | 45414.625 | 45414.4167 | 45414.625 | 45415.4382 | 45415.4383 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45407.56 | 45407.5233 | 45414.3991 | 45415.4383 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000390905 | GA, AUGUSTA, TRANSPORT BLDG, ADD MTS (MANUAL TRANSFER SWITCH) | Low | Successful | Minor | Planned | MVW | TT | 45405.4134 | 45418.4167 | 45422.5 | 45418.4167 | 45420.4167 | 45420.4256 | 45420.4259 | 2024 | 2024-05 | Successful | Facilities Component | Generator | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45407.5628 | 45407.5493 | 45418.3994 | 45498.7092 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391228 | AL, Wetumpka, dark fiber splicing | Low | Successful | Minor | Planned | DHA | TT | 45406.979 | 45467.7917 | 45468.125 | 45467.7917 | 45468.059 | 45468.4112 | 45468.4113 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45460.4727 | 45460.4469 | 45467.7711 | 45519.4679 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000391401 | GA, Helen ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45406.4001 | 45426.375 | 45426.5833 | 45426.375 | 45426.5833 | 45427.4835 | 45427.4837 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45418.6953 | 45418.6486 | 45426.3578 | 45427.4837 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391402 | GA, Statham ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45406.4112 | 45420.375 | 45420.5417 | 45420.375 | 45420.5417 | 45421.4329 | 45421.433 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45407.5662 | 45407.5552 | 45420.3571 | 45421.433 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391403 | GA, Watkinsville ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45406.4196 | 45420.5417 | 45420.7083 | 45420.5417 | 45420.7083 | 45421.4338 | 45421.4339 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45407.9157 | 45407.556 | 45420.5238 | 45421.4339 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391628 | AL, Montgomery, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45407.6971 | 45427.4167 | 45427.9993 | 45427.4167 | 45427.7535 | 45428.4452 | 45428.4455 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45414.404 | 45413.6129 | 45427.3997 | 45428.4455 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391716 | AL, West Montgomery, Various Sites, NOKIA SAR Software Upgrades | Low | SuccessfulwithIssues | Minor | Planned | MPH | TT | 45407.6494 | 45426.4167 | 45426.9993 | 45426.4167 | 45426.7764 | 45427.4624 | 45427.4629 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45420.4057 | 45413.6158 | 45426.3995 | 45427.4629 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391717 | AL, West Montgomery, Various Sites, NOKIA SAR Software Upgrades (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45407.65 | 45433.4167 | 45433.9993 | 45433.6451 | 45433.9993 | 45434.4206 | 45434.4207 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45419.4806 | 45413.6166 | 45433.3965 | 45434.4208 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391802 | GA, Savannah/Kettle Creek, Replace Fiber Jumpers and Attenuators | Medium | Successful | Moderate | Planned | ADL | TT | 45408.3435 | 45428.3958 | 45428.7083 | 45428.3958 | 45428.4181 | 45429.3696 | 45429.3698 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45425.5891 | 45422.499 | 45428.386 | 45429.3699 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000391900 | GA, Atlanta, GPC HQ, Ciena DWDM Shelf 009 Site Survey | Medium | Successful | Moderate | Planned | ADL | TT | 45408.3332 | 45419.2917 | 45419.9993 | 45419.3826 | 45419.9993 | 45420.3986 | 45420.3994 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45413.3979 | 45408.6484 | 45419.2745 | 45420.3994 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392089 | GA, Atlanta, Reboot/Replace DWDM ADM cards in 3-13 and 5-1 at Virgina Ave (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45411.6049 | 45421.7083 | 45421.875 | 45421.7083 | 45421.875 | 45422.4412 | 45422.4414 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45420.7041 | 45419.4894 | 45421.6906 | 45422.4414 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392098 | MS, Picayune EBTS M8410, Stennis changing from Band 66 to Band 26 LTE | Low | Successful | Minor | Planned | CDL | TT | 45411.6828 | 45425.4583 | 45429.8333 | 45425.4583 | 45429.8333 | 45432.4222 | 45432.4225 | 2024 | 2024-05 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45413.6781 | 45413.618 | 45425.441 | 45432.4225 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392108 | AL, Birmingham, Ross Bridge EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45411.7253 | 45419.4167 | 45419.625 | 45419.4167 | 45419.625 | 45420.3998 | 45420.4 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45413.4868 | 45412.6684 | 45419.3995 | 45420.4 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392209 | GA, Various Sites, Cut Springfield OH WAN and NetGuardian Teamup Ckt. | Low | Successful | Minor | Planned | MPH | TT | 45412.6899 | 45421.7083 | 45421.875 | 45421.7083 | 45421.8097 | 45422.4452 | 45422.4455 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45414.3853 | 45413.6208 | 45421.6906 | 45422.4455 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392231 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 1 NIGHT 1 | Medium | Successful | Moderate | Planned | ADL | TT | 45412.5279 | 45425.7083 | 45425.9993 | 45425.7083 | 45425.9993 | 45426.3894 | 45426.3897 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45419.458 | 45414.674 | 45426.389 | 45426.3897 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392232 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 1 NIGHT 1 (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45412.528 | 45440.7083 | 45440.9993 | 45440.766 | 45440.8653 | 45441.3959 | 45441.3961 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45435.4756 | 45435.4314 | 45440.6889 | 45441.3961 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392235 | GA, Various Locations, Migrate Ciena 6500 customer traffic to (ADM) Ring 1 NIGHT 2 (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45412.5391 | 45441.7083 | 45441.9993 | 45441.7083 | 45441.8319 | 45443.4171 | 45443.4191 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45428.6015 | 45427.4566 | 45443.4167 | 45443.4191 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392271 | AL, Ashland, Added New ADM Modules to Ciena 6500 | Medium | BackedOut | Moderate | Planned | GPB | TT | 45413.6052 | 45421.4583 | 45421.6667 | 45421.4583 | 45421.6667 | 45422.5047 | 45426.39 | 2024 | 2024-05 | Unsuccessful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45419.4574 | 45414.688 | 45421.4405 | 45426.39 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392277 | AL, Webb, ASR903 Software upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45413.6992 | 45422.4583 | 45422.5417 | 45422.4583 | 45422.5417 | 45425.4277 | 45425.4303 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45418.3421 | 45415.4443 | 45422.4407 | 45425.4303 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392280 | AL, Montgomery Area, Install ADMs in Jeff St WDM003/SNWD WDM001/Turnup 100G Links | Medium | Successful | Moderate | Planned | DRB | TT | 45413.7791 | 45427.4167 | 45427.6667 | 45427.4167 | 45427.6667 | 45428.4409 | 45428.4413 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Install | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45427.3983 | 45419.4916 | 45427.3997 | 45428.4413 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392295 | MS, Meridian, ASR903 LTE router software upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45414.44 | 45422.5833 | 45422.625 | 45422.5833 | 45422.625 | 45425.4311 | 45425.4314 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45418.3424 | 45415.4452 | 45422.5657 | 45425.4314 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392296 | GA, Rome, ASR903 Software upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45414.4487 | 45426.9583 | 45427 | 45426.4583 | 45427.0174 | 45427.4635 | 45427.4638 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45418.3588 | 45415.4483 | 45426.9413 | 45427.4638 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392342 | GA, Columbus Area, OTDR/Clean/Scope Fibers on Columbus-Manchester-Jackson DWDM Spans (BACKUP DATE) | Medium | Successful | Moderate | Planned | DRB | TT | 45413.6947 | 45428.7083 | 45428.9583 | 45428.7083 | 45428.759 | 45429.3668 | 45429.367 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Remove/Retire | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45427.4016 | 45415.5581 | 45428.6916 | 45429.3702 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392343 | AL, Pinckard ASR903 Software Upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45413.7035 | 45425.4583 | 45425.5417 | 45425.4583 | 45425.5 | 45425.6546 | 45425.655 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45418.3596 | 45415.446 | 45425.441 | 45425.655 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392344 | AL, Snowdoun ASR903 software upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45413.7074 | 45426.5 | 45426.5833 | 45426.5 | 45426.6896 | 45427.4646 | 45427.4649 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45418.3582 | 45415.4469 | 45426.4829 | 45427.4649 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392370 | GA, Savannah ICON Ring, Clean up unused ethernet circuits | Low | Successful | Minor | Planned | RPY | TT | 45414.5015 | 45425.4167 | 45425.6667 | 45425.4167 | 45425.5833 | 45425.6515 | 45425.6517 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45419.4102 | 45415.5557 | 45425.3993 | 45425.6517 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392379 | MS, Laurel, Migrate Laurel North Sub to NGTAN (from Orbit Radio) | Low | Successful | Minor | Planned | DRB | TT | 45414.5462 | 45441.4167 | 45441.7083 | 45441.4167 | 45441.7826 | 45442.4423 | 45442.4424 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45428.5435 | 45427.4672 | 45441.3974 | 45442.4424 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392474 | GA, ATL CON Ring, ALL NODES on the ATL ICON Ring, Remove unused ethernet circuits | Medium | Successful | Moderate | Planned | RPY | TT | 45418.5058 | 45435.4167 | 45435.6875 | 45435.4167 | 45435.6993 | 45436.4312 | 45436.4316 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45419.6774 | 45419.5882 | 45435.3969 | 45436.4316 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392488 | AL, Plant Farley, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45418.6665 | 45435.3333 | 45435.9993 | 45435.3417 | 45435.5708 | 45436.4249 | 45436.4252 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45419.6763 | 45419.5855 | 45435.3135 | 45436.4252 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392494 | AL, Tuscaloosa , Splice fibers for AFN | Low | Successful | Minor | Planned | DWM | TT | 45418.7849 | 45447 | 45447.25 | 45447 | 45447.1687 | 45447.399 | 45447.3991 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45419.6692 | 45419.5961 | 45446.9887 | 45519.4679 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392495 | AL, Tuscaloosa, Splice fibers for AFN (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45418.7849 | 45453.7917 | 45454.25 | 45453.7917 | 45454.25 | 45455.4203 | 45455.4204 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45449.8003 | 45449.593 | 45453.7811 | 45519.4679 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392512 | GA, N. GA ICON Ring, Replace PLMs with EPLMs | Low | Successful | Minor | Planned | RPY | TT | 45419.4405 | 45432.4167 | 45432.6667 | 45432.4167 | 45432.6667 | 45433.3984 | 45433.3986 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45420.4067 | 45419.5828 | 45432.4002 | 45433.3986 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392547 | AL, HEADLAND CREQ HQ, UPS REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45418.533 | 45433.3333 | 45434.7083 | 45433.3333 | 45434.7083 | 45435.4319 | 45436.4402 | 2024 | 2024-05 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45419.6928 | 45419.5804 | 45433.3131 | 45498.7092 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392561 | AL, Greene Co SP, Various Sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45418.6962 | 45446.3333 | 45446.9993 | 45446.3333 | 45446.6903 | 45446.8707 | 45446.8708 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45420.4075 | 45419.5903 | 45446.3219 | 45446.8708 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392564 | AL, Gorgas, need to move fiber underground | Low | Successful | Minor | Planned | DWM | TT | 45418.7736 | 45448.3333 | 45448.6667 | 45448.3333 | 45448.5208 | 45449.5951 | 45449.5953 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45419.6663 | 45419.5923 | 45448.3222 | 45519.4679 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392581 | GA, Calloway Gardens, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45419.4863 | 45427.375 | 45427.5417 | 45427.375 | 45427.5417 | 45428.4425 | 45428.4427 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45419.6906 | 45419.5764 | 45427.358 | 45428.4427 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392593 | MS, Meridian, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45419.691 | 45447.3333 | 45447.9993 | 45447.3417 | 45447.9451 | 45448.3772 | 45448.3777 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.5475 | 45420.5014 | 45447.322 | 45448.3777 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392595 | AL, Montevallo, Maylene Transport, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45419.6928 | 45426.4167 | 45426.625 | 45426.4167 | 45426.625 | 45427.4843 | 45427.4845 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45420.6049 | 45420.4968 | 45426.3995 | 45427.4845 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392600 | MS, Newton, Various sites, NOKIA SAR Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45419.7104 | 45453.3333 | 45453.9993 | 45453.425 | 45453.8292 | 45454.4052 | 45454.4054 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.545 | 45420.5041 | 45453.3227 | 45454.4054 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392602 | AL, Pine Hill EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45419.7114 | 45426.4583 | 45426.6667 | 45426.4583 | 45426.6667 | 45427.4849 | 45427.485 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45420.6057 | 45420.4977 | 45426.4412 | 45427.4851 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392638 | AL, Anniston to Cheaha, Alcatel MPR9500 M/W dish alignment needed (BACKUP DATE) | Medium | Successful | Moderate | Planned | WJL | TT | 45419.6443 | 45428.3958 | 45428.75 | 45428.3958 | 45428.75 | 45429.3706 | 45429.3708 | 2024 | 2024-05 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45426.3604 | 45420.5001 | 45428.386 | 45429.3708 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392642 | AL, Coffeeville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45419.9664 | 45426.4583 | 45426.6667 | 45426.4583 | 45426.6667 | 45427.4861 | 45427.4863 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45420.6377 | 45420.4984 | 45426.4412 | 45427.4863 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392783 | GA, Moody AFB, Migrate leased circuit to new AT&T ASEoD service. (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45421.6578 | 45441.4167 | 45441.5833 | 45441.4167 | 45441.4368 | 45441.4613 | 45441.4614 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.6797 | 45422.5006 | 45441.3974 | 45441.4614 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392794 | AL, DADEVILLE LOCAL OFFICE, UPS REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45422.3375 | 45444.2917 | 45444.7917 | 45444.3604 | 45444.5257 | 45446.4034 | 45446.4035 | 2024 | 2024-06 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45425.6808 | 45422.5017 | 45444.2801 | 45498.7092 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392832 | AL, Calera, OLT Cabinet, Wiring Second Battery String | Medium | Successful | Moderate | Unplanned | JGL | TT | 45420.6519 | 45427.4479 | 45427.75 | 45427.4479 | 45427.4792 | 45428.4471 | 45428.4474 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45427.4439 | 45427.4401 | 45427.4552 | 45428.4474 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392834 | AL, Octagon EBTS A9196, adding tower strengthening and changing guy wires | Low | Successful | Minor | Planned | CDL | TT | 45420.6579 | 45453.375 | 45471.8333 | 45453.375 | 45467.7083 | 45468.41 | 45468.4101 | 2024 | 2024-06 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45433.5956 | 45433.5672 | 45453.3644 | 45468.4101 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392907 | GA, Offerman, ASR903 LTE router software upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45425.5686 | 45433.5 | 45433.5833 | 45433.5 | 45433.609 | 45434.4158 | 45434.4161 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.7263 | 45425.677 | 45433.4798 | 45434.4161 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392908 | AL, Greene County SP, ASR903 Software Upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45425.577 | 45434.6042 | 45434.6458 | 45434.6042 | 45434.6458 | 45435.4286 | 45435.4289 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45428.3625 | 45427.4804 | 45434.5912 | 45435.4289 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392909 | GA, North Tifton, ASR903 Software Upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45425.5812 | 45435.5208 | 45435.6042 | 45435.5208 | 45435.566 | 45436.4341 | 45436.4344 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45428.3629 | 45427.4816 | 45435.508 | 45436.4344 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392910 | GA, Rome, ASR903 Software upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45425.6018 | 45435.625 | 45435.6667 | 45435.625 | 45435.7479 | 45436.433 | 45436.4333 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45428.3633 | 45427.4824 | 45435.6053 | 45436.4333 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392926 | MS, Gulfport, Seaway Rd Fiber Repair/No MPC Traffic | Low | Successful | Minor | Planned | DRB | TT | 45425.4424 | 45430.375 | 45430.75 | 45430.375 | 45430.75 | 45432.4256 | 45432.4259 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45428.5418 | 45425.6739 | 45430.3584 | 45432.4259 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392940 | GA, Hatch Transport ASR903 Software Upgrades | Medium | Successful | Moderate | Planned | DRI | TT | 45425.573 | 45433.625 | 45433.7083 | 45433.625 | 45433.6701 | 45434.4187 | 45434.419 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.7258 | 45425.6759 | 45433.6049 | 45434.4203 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392941 | AL, Dothan, ASR903 Software Upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45425.5915 | 45434 | 45434.041 | 45433.5 | 45433.5403 | 45434.4196 | 45434.4199 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45425.7254 | 45425.6781 | 45433.9799 | 45434.4199 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392945 | GA, Virginia Avenue, ASR903 Software Upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45425.6106 | 45434.9583 | 45435 | 45434.4583 | 45435 | 45435.4261 | 45435.4269 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45432.3436 | 45429.6469 | 45434.9385 | 45435.4269 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392954 | AL, West Blocton EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45425.8427 | 45433.4167 | 45433.625 | 45433.0417 | 45433.625 | 45434.4211 | 45434.4212 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45427.7145 | 45426.6401 | 45433.3965 | 45434.4213 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000392983 | GA, Sandy Plains EBTS, turning off MW to Sweat Mtn adding MW at Blackwell Sub | Low | Successful | Minor | Planned | CDL | TT | 45426.6263 | 45440.375 | 45443.8333 | 45440.375 | 45443.8333 | 45446.4069 | 45446.407 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45434.3297 | 45433.5571 | 45440.3556 | 45446.407 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000392984 | GA, Sandy Plains EBTS, turning off MW to Sweat Mtn adding MW at Blackwell Sub (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45426.6264 | 45446.375 | 45450.8333 | 45446.375 | 45450.8333 | 45453.4172 | 45453.4173 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45433.561 | 45433.5597 | 45446.3636 | 45453.4173 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393020 | AL, Alexander City, Our Town EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45425.839 | 45435.4167 | 45435.625 | 45435.4167 | 45435.625 | 45436.4412 | 45436.4415 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45427.7183 | 45426.641 | 45435.3969 | 45436.4415 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393039 | AL, Prattville, Autaugaville TS Fiber Hut, power out due to transformer replacement | Low | Successful | Minor | Planned | JEN | TT | 45426.5357 | 45432.3333 | 45435.8333 | 45432.3333 | 45435.8333 | 45436.4397 | 45436.4399 | 2024 | 2024-05 | Successful | Facilities Component | Generator | Repair | Transport | JEN | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45426.7067 | 45426.6355 | 45432.3168 | 45519.4508 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393079 | GA, Macon & Rome, Migrate "Macon-Rome 1GbE MPLS" circuit To New ADM Path | Low | Successful | Minor | Planned | DRB | TT | 45427.6368 | 45433.625 | 45433.75 | 45433.625 | 45433.6618 | 45434.4168 | 45434.417 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45428.5483 | 45428.4709 | 45433.6049 | 45434.417 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393113 | GA, Fort Benning, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45428.6786 | 45436.375 | 45436.5 | 45436.375 | 45436.4083 | 45436.4234 | 45436.4235 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45429.7316 | 45429.6534 | 45436.3553 | 45436.4236 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393125 | AL, Western ICON Ring, Install S Tuscaloosa ICON | Low | Successful | Minor | Planned | RPY | TT | 45427.6805 | 45432.4167 | 45432.6667 | 45432.4167 | 45432.6667 | 45433.3994 | 45433.3996 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45428.5473 | 45428.4681 | 45432.4002 | 45433.3996 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393126 | AL, Western ICON Ring, Install S Tuscaloosa ICON (BACKUP DATE) | Low | Successful | Minor | Planned | RPY | TT | 45427.6806 | 45435.4167 | 45435.6667 | 45435.4167 | 45435.4271 | 45435.4566 | 45435.4568 | 2024 | 2024-05 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45428.5477 | 45428.4689 | 45435.3969 | 45435.4568 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393252 | GA, Lavonia ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45432.4087 | 45440.375 | 45440.5 | 45440.375 | 45440.5 | 45440.6602 | 45440.6604 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45432.4443 | 45432.4339 | 45440.3556 | 45440.6604 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393254 | GA, Terrora ENODEB, DC Plant Upgrade | Low | Successful | Minor | Planned | LPE | TT | 45432.413 | 45440.5 | 45440.6667 | 45440.5 | 45440.6667 | 45441.3949 | 45443.4162 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45432.4446 | 45432.4347 | 45440.4806 | 45443.4162 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393325 | AL, Trussville, Splicing dark fibers for C-Spire | Low | Successful | Minor | Planned | DKG | TT | 45429.5688 | 45434.2917 | 45435.7917 | 45434.341 | 45435.9 | 45436.4407 | 45436.4408 | 2024 | 2024-05 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45429.715 | 45429.643 | 45434.2716 | 45519.4588 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393376 | GA, LaGrange, Transmission ROW, Splice new section of OPGW | Low | Successful | Minor | Planned | JLM | TT | 45432.4698 | 45451.3333 | 45451.7917 | 45451.3438 | 45451.6993 | 45453.4349 | 45453.435 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45433.5945 | 45433.576 | 45451.3226 | 45519.4626 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393387 | AL, North Auburn Transport, Add Ciena 6500 S Chassis Into Network | Medium | Successful | Moderate | Planned | GPB | TT | 45432.5986 | 45454.75 | 45457 | 45454.75 | 45457 | 45460.4387 | 45460.4389 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45443.4668 | 45443.4473 | 45454.7395 | 45460.4389 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393439 | AL, Mobile EBTS A9917 Seven Hills will be turned off, A8917 Dykes Rd turned up | Low | Successful | Minor | Planned | CDL | TT | 45433.4716 | 45441.5 | 45443.8333 | 45441.5 | 45443.8333 | 45446.4074 | 45446.4076 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45433.5083 | 45433.4966 | 45441.4807 | 45446.4076 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393465 | GA, Athens, Various Locations, Migrate EMS Circuits to Ciena ADM | Medium | Successful | Moderate | Planned | ADL | TT | 45434.3424 | 45455.4375 | 45455.6458 | 45455.4375 | 45455.6028 | 45455.6496 | 45455.6499 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45446.4299 | 45446.4023 | 45455.4224 | 45455.6499 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393530 | AL, Ranburne EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45433.4268 | 45440.4167 | 45440.625 | 45440.4167 | 45440.625 | 45440.6607 | 45440.6609 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45433.5091 | 45433.494 | 45440.3972 | 45440.6609 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393532 | AL, West Tuscaloosa, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45433.4313 | 45442.4167 | 45442.625 | 45442.4167 | 45442.625 | 45443.4196 | 45443.4198 | 2024 | 2024-05 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45433.5086 | 45433.4948 | 45442.3976 | 45443.4198 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393576 | AL, Mobile, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45434.7141 | 45461.375 | 45461.9993 | 45461.375 | 45461.775 | 45462.4771 | 45462.4774 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45435.4928 | 45435.482 | 45461.3674 | 45462.4774 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393584 | GA, Monticello, all five STI ILA's Installing power wire & breakers in BDFB's. | Low | Successful | Minor | Planned | SDG | TT | 45435.4123 | 45448.9375 | 45449.25 | 45448.9514 | 45449.1889 | 45449.5968 | 45449.5969 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45435.4465 | 45435.4418 | 45448.9195 | 45449.5969 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393585 | GA, Monticello, all five STI ILA's Installing power wire & breakers in BDFB's. (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45435.4123 | 45449.9375 | 45450.25 | 45449.9375 | 45450.0521 | 45450.435 | 45450.4351 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45435.5529 | 45435.443 | 45449.9197 | 45450.4351 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393600 | MS, Gulfport, Migrate Landon Hub-Long Beach Tower 1G SAR link to UG Fiber | Low | Successful | Minor | Planned | DRB | TT | 45435.6402 | 45446.4583 | 45446.6667 | 45446.4688 | 45446.5146 | 45446.8722 | 45446.8723 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45440.5111 | 45440.506 | 45446.4469 | 45446.8723 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393682 | AL, Carroll Bluff Transport, Generator and ATS Replacement-Upgrade | Low | Successful | Minor | Planned | KNL | TT | 45440.4285 | 45446.75 | 45450.7917 | 45446.75 | 45447.3889 | 45453.4341 | 45453.4341 | 2024 | 2024-06 | Successful | Facilities Component | Propane Tank | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45441.6137 | 45441.6069 | 45446.7386 | 45498.7092 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393683 | AL, South Alabama, Install ADMs at Webb & Farley / Cut DWDM Ckts: Webb-Farley-Dothan | Medium | Successful | Moderate | Planned | DRB | TT | 45440.4328 | 45449.4167 | 45449.75 | 45449.4167 | 45449.6889 | 45449.6993 | 45449.6997 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45440.7041 | 45440.6634 | 45449.4057 | 45449.6997 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393701 | AL, Vernon EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45440.5406 | 45454.4583 | 45454.5833 | 45454.4583 | 45454.5833 | 45455.4223 | 45455.4224 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45440.6692 | 45440.6507 | 45454.4478 | 45455.4224 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393712 | GA, Burton Hydro, Replace the PLM transport cards with EPLMâ€™s. | Low | Successful | Minor | Planned | DAP | TT | 45440.5696 | 45476.4167 | 45476.6667 | 45476.4764 | 45476.5069 | 45476.5106 | 45476.5108 | 2024 | 2024-07 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45455.4169 | 45455.4143 | 45476.3977 | 45476.5108 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000393715 | MS, Buckatunna, Migrate leased circuit to new AT&T ASEoD service. | Low | Successful | Minor | Planned | JHW | TT | 45440.5905 | 45448.5417 | 45448.625 | 45448.5417 | 45448.6028 | 45449.5958 | 45449.5958 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45440.6639 | 45440.6481 | 45448.5306 | 45449.5958 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393724 | AL, Fayette Transport to Phillips Mtn, Nokia M/W 6 - 11 GHz replacement | Low | Successful | Minor | Planned | WJL | TT | 45439.5713 | 45446.3958 | 45450.7708 | 45446.3958 | 45446.7708 | 45446.8748 | 45446.8749 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45443.4312 | 45443.4299 | 45446.3775 | 45447.5038 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393744 | MS, Gulfport, South Lyman EBTS, DC plant modification | Low | Successful | Minor | Planned | RBK | TT | 45440.5463 | 45446.3958 | 45446.4792 | 45446.3958 | 45446.4792 | 45446.6095 | 45446.6096 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45440.6467 | 45440.6453 | 45446.3775 | 45446.6096 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393752 | AL, West Vance EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45440.6162 | 45447.4167 | 45447.625 | 45447.4167 | 45447.625 | 45449.5944 | 45449.5946 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45440.6473 | 45440.6462 | 45447.4054 | 45449.5946 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393755 | AL, Powell Ave, and Parkwest DS, Install SEL ICON Async Modules | Low | Successful | Minor | Planned | DAP | TT | 45440.6252 | 45454.4167 | 45454.6667 | 45454.4271 | 45454.534 | 45454.5376 | 45454.5378 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Install | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45440.6666 | 45440.6522 | 45454.4061 | 45454.5378 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393819 | AL, Roanoke EBTS, rectifier plant replacement. | Low | Successful | Minor | Planned | RBK | TT | 45440.6024 | 45449.4167 | 45449.5833 | 45449.4167 | 45449.5833 | 45449.7029 | 45449.703 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45440.6551 | 45440.647 | 45449.4057 | 45449.703 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393833 | GA, Tallulah Falls, Terrora Substation, Move OPGW to Terrora Commons | Medium | Successful | Moderate | Planned | MAR | TT | 45440.7412 | 45454.3125 | 45454.7292 | 45454.3125 | 45454.7292 | 45455.4212 | 45455.4214 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45441.6616 | 45441.6155 | 45454.295 | 45519.4626 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393834 | GA, Tallulah Falls, Terrora Substation, Move OPGW to Terrora Commons (BACKUP DATE) | Medium | Successful | Moderate | Planned | MAR | TT | 45440.7412 | 45455.3125 | 45455.7292 | 45455.3174 | 45455.8681 | 45456.388 | 45456.3883 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45441.6678 | 45441.6168 | 45455.2973 | 45519.4626 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393862 | Advisory/Oper Event: GA - AUGUSTA - EMERGENCY FIBER TROUBLESHOOTING AND REPAIR NCC-17721 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45441.6637 | 45442 | 45442.25 | 45441.9868 | 45442.1396 | 45442.5322 | 45442.5327 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45441.6774 | 45441.6774 | 45441.9808 | 45442.5327 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393866 | Advisory/Oper Event: GA - AUGUSTA - EMERGENCY FIBER TROUBLESHOOTING AND REPAIR NCC-17721 (BACKUP) | Low | Successful | Std/PreApp | Planned | HHA | HH | 45441.6715 | 45443 | 45443.25 | 45443 | 45443.2139 | 45443.4117 | 45443.4119 | 2024 | 2024-05 | Successful | Transport Device | Other Transport Device | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45441.6771 | 45441.6771 | 45442.9811 | 45443.4119 | 2024-Q2 | 2024-05 | 2024-Q2
CRQ000000393872 | AL, Brewton, Mobile, Various Sites, NOKIA SAR Software Upgrades | Medium | Successful | Moderate | Planned | MPH | TT | 45441.6894 | 45454.375 | 45454.9993 | 45454.3847 | 45454.7757 | 45455.4182 | 45455.4185 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45443.464 | 45443.4502 | 45454.3644 | 45455.4185 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393877 | AL, Plant Barry/McIntosh, Various Sites, NOKIA SAR Software Upgrades (BACKUP DATE) | Medium | Successful | Moderate | Planned | MPH | TT | 45441.7217 | 45463.375 | 45463.9993 | 45463.375 | 45463.7083 | 45463.7113 | 45463.7116 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45443.4732 | 45443.461 | 45463.3677 | 45463.7116 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393902 | GA, Tybee Island, AT&T circuit upgrade | Low | Successful | Minor | Planned | DRI | TT | 45442.566 | 45450.3958 | 45450.4375 | 45450.3958 | 45450.4167 | 45450.4337 | 45450.4338 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45443.464 | 45443.4624 | 45450.3781 | 45450.4338 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393977 | GA, Trenton OH/Burkhalter Gap EBTS, 6GHz to 11GHz MW Radio Upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45446.6384 | 45460.3333 | 45461.7917 | 45460.3333 | 45461.7917 | 45462.4793 | 45462.4795 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45447.606 | 45447.6009 | 45460.3256 | 45519.4736 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393978 | GA, Trenton OH/Burkhalter Gap EBTS, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Medium | Successful | Moderate | Planned | JMN | TT | 45446.6385 | 45462.3333 | 45463.7917 | 45462.3333 | 45463.6667 | 45463.6865 | 45463.6867 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45447.6074 | 45447.6017 | 45462.3259 | 45519.4736 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393984 | GA, Burkhalter Gap EBTS / Durham MW, 6GHz to 11GHz MW Radio Upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45446.6679 | 45461.3333 | 45462.7917 | 45461.3333 | 45462.7917 | 45463.6677 | 45463.6685 | 2024 | 2024-06 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45447.625 | 45447.6033 | 45461.3258 | 45519.4736 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000393985 | GA, Burkhalter Gap EBTS / Durham MW, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Medium | Successful | Moderate | Planned | JMN | TT | 45446.6679 | 45481.3333 | 45482.2917 | 45481.3333 | 45481.7292 | 45481.7851 | 45481.7854 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45475.4154 | 45475.4085 | 45481.3148 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394010 | GA, Norwood, Move DWDM to Spare Fiber between Norwood & Athens due to Severe Degrade | Medium | Successful | Moderate | Planned | DRB | TT | 45447.4802 | 45449.7083 | 45449.8333 | 45449.6896 | 45449.7201 | 45450.4357 | 45450.436 | 2024 | 2024-06 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45447.6049 | 45447.5928 | 45449.6974 | 45450.436 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394147 | GA, Atlanta SEL ICON Ring, cable reroutes needed | Medium | Successful | Moderate | Planned | RPY | TT | 45446.5357 | 45462.375 | 45462.6667 | 45462.375 | 45462.6667 | 45462.7314 | 45462.7316 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45455.3643 | 45453.4166 | 45462.3676 | 45462.7316 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394207 | AL, Rockford EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45447.8699 | 45454.4167 | 45454.625 | 45454.4167 | 45454.625 | 45455.4218 | 45455.4219 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45450.4646 | 45450.4548 | 45454.4061 | 45455.4219 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394208 | AL, Homewood, Wildwood EBTS, rectifier replacement. | Low | Successful | Minor | Planned | RBK | TT | 45447.8732 | 45456.4167 | 45456.625 | 45456.4167 | 45456.625 | 45460.4406 | 45460.4407 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45450.4646 | 45450.4556 | 45456.4086 | 45460.4407 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394348 | GA, Jackson, Lloyd Shoals Sub, Splice lateral cable into backbone cable | Medium | Successful | Moderate | Planned | JLM | TT | 45448.7649 | 45503.7083 | 45504.2083 | 45503.7083 | 45504.2083 | 45504.538 | 45504.5382 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45496.515 | 45496.4842 | 45503.6929 | 45519.4626 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394379 | AL, Auburn, connecting new fibers to Pear Tree COLO | Low | Successful | Minor | Planned | DWM | TT | 45449.5817 | 45474.7917 | 45475.2917 | 45474.8118 | 45475.0465 | 45475.4025 | 45475.4029 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45450.4914 | 45450.4877 | 45474.7725 | 45519.4679 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394384 | GA, Durham MW / Rock Springs EBTS, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45449.6025 | 45481.3333 | 45482.7917 | 45481.3333 | 45482.7917 | 45483.5419 | 45483.5421 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45475.4117 | 45475.4103 | 45481.3148 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394385 | GA, Durham MW / Rock Springs EBTS, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45449.6026 | 45483.3333 | 45484.8333 | 45483.3333 | 45484.8333 | 45485.4539 | 45485.454 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45475.414 | 45475.4132 | 45483.3247 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394392 | GA, Durham MW / Taylor Ridge MW, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45449.6806 | 45482.3333 | 45483.7917 | 45482.3562 | 45483.7917 | 45484.3695 | 45484.3696 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45475.4177 | 45475.4155 | 45482.3245 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394393 | GA, Durham MW / Taylor Ridge MW, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45449.6806 | 45502.3333 | 45503.7917 | 45502.4368 | 45503.5042 | 45503.6386 | 45503.6387 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45491.5673 | 45491.5373 | 45502.3177 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394446 | AL, Birmingham, Shoal Creek EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45453.8805 | 45461.4167 | 45461.5833 | 45461.4167 | 45461.5833 | 45462.4816 | 45462.4817 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45456.3583 | 45455.6716 | 45461.4091 | 45462.4817 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394525 | AL, BALD ROCK TRANSPORT, GENERATOR-ATS UPGRADE | Low | Successful | Minor | Planned | KNL | TT | 45453.5765 | 45467.2917 | 45471.8333 | 45467.2917 | 45471.8333 | 45474.404 | 45474.4042 | 2024 | 2024-07 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45462.2919 | 45461.648 | 45467.271 | 45498.7092 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394535 | AL, South Alex City EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45453.8842 | 45463.4167 | 45463.5833 | 45463.4167 | 45463.5833 | 45463.7156 | 45463.7157 | 2024 | 2024-06 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45456.3583 | 45455.6728 | 45463.4094 | 45463.7157 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394546 | AL, Anniston, Transport/Cabinet, replace end-of-life OLT8 Cards with Combo cards | Low | Successful | Minor | Planned | JGL | TT | 45454.4304 | 45461.375 | 45461.75 | 45461.4396 | 45461.55 | 45462.4803 | 45462.4804 | 2024 | 2024-06 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45456.3576 | 45455.6786 | 45461.3674 | 45462.4804 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394641 | AL, Mobile, ASR903 Software Upgrade | Medium | Successful | Moderate | Planned | DRI | TT | 45455.6021 | 45463 | 45463.041 | 45463 | 45463.041 | 45463.6711 | 45463.6713 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45457.3623 | 45456.4726 | 45462.9927 | 45463.6713 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000394752 | AL, Auburn, splicing 288 LHUG thru Pear Tree COLO Hut | Low | Successful | Minor | Planned | DWM | TT | 45456.4829 | 45503 | 45503.2917 | 45503 | 45503.2917 | 45503.5457 | 45503.5458 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45496.5805 | 45496.5787 | 45502.9845 | 45519.4679 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394753 | AL, Auburn, splicing 288 LHUG thru Pear Tree COLO Hut (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45456.483 | 45504 | 45504.2917 | 45504 | 45504.2917 | 45504.5392 | 45504.5393 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45496.5813 | 45496.5801 | 45503.9846 | 45519.4679 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394761 | GA, Atlanta, GPC HQ, DWDM Shelf 009 Chassis Replacement | Medium | Successful | Moderate | Planned | ADL | TT | 45456.6624 | 45475.375 | 45475.7083 | 45475.375 | 45475.5833 | 45475.5984 | 45475.5988 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45468.3702 | 45468.0203 | 45475.3559 | 45475.5988 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394775 | AL, GA, Various sites, Ciena 6500 Remove OOS Modules | Low | Successful | Minor | Planned | GPB | TT | 45457.4248 | 45474.4167 | 45475.7917 | 45474.4563 | 45475.7896 | 45476.3764 | 45476.3765 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45468.3221 | 45468.0142 | 45474.3975 | 45476.3765 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394861 | AL, Bankhead Dam Transport, replace Alcatel 9500 microwave with Nokia Wavence | Medium | Successful | Moderate | Planned | WJL | TT | 45460.5065 | 45502.3958 | 45506.75 | 45502.3958 | 45506.75 | 45507.4851 | 45507.4854 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45491.5205 | 45491.5141 | 45502.3872 | 45507.4854 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000394949 | GA, Atlanta, Virginia Ave. Replace Ciena ADM Card | Medium | Successful | Moderate | Planned | ADL | TT | 45461.4812 | 45476.375 | 45476.5833 | 45476.375 | 45476.4458 | 45481.3967 | 45481.397 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45468.3706 | 45468.024 | 45476.3561 | 45481.397 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000394969 | GA, Tallulah Falls, Terrora Substation, Moving to new fiber route @ Terrora Commons | Low | Successful | Minor | Planned | MAR | TT | 45461.7142 | 45475.3333 | 45475.5417 | 45475.3333 | 45475.5 | 45476.3773 | 45476.3775 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45474.3621 | 45471.4666 | 45475.3143 | 45519.4626 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395034 | AL, McIntosh, cut dark fibers only into new McIntosh COLO hut | Low | Successful | Minor | Planned | RRR | TT | 45462.5594 | 45483.7917 | 45484.125 | 45483.8083 | 45484 | 45484.3703 | 45484.3705 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45462.8752 | 45462.7585 | 45483.7832 | 45519.4679 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395089 | AL, Birmingham, APC HQ, Linc LTE Data Center Linc MCPTT 3.5.1 Upgrade | Medium | Successful | Moderate | Unplanned | MJR | TT | 45463.7692 | 45467.0833 | 45467.2083 | 45467.0833 | 45467.2083 | 45467.9969 | 45467.9972 | 2024 | 2024-06 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | MJR | COM | PRODUCT DEVELOPMENT & SUPPORT | MSO-EPC OPERATIONS | 45464.545 | 45464.5405 | 45467.0626 | 45467.9972 | 2024-Q2 | 2024-06 | 2024-Q2
CRQ000000395190 | GA, Offerman, Surrency ILA, splicing dark fiber | Low | Successful | Minor | Planned | SDG | TT | 45467.5959 | 45474.9375 | 45475.25 | 45474.9375 | 45475.25 | 45475.4038 | 45475.4039 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | SDG | APC |  | STI | 45474.3622 | 45471.4631 | 45474.9253 | 45475.4039 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395192 | GA, Offerman, Surrency ILA, splicing dark fiber (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45467.5959 | 45475.9375 | 45476.25 | 45475.9715 | 45476.0507 | 45476.3784 | 45476.3786 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | SDG | APC |  | STI | 45474.3623 | 45471.4638 | 45475.9255 | 45476.3786 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395414 | GA, Jekyll Island, Migrate leased circuit to new AT&T ASEoD service. (BACKUP DATE) | Low | Successful | Minor | Planned | JHW | TT | 45471.4606 | 45516.4375 | 45516.5625 | 45516.4375 | 45516.5625 | 45516.6771 | 45516.6772 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Migrate | Transport | JHW | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45509.6606 | 45509.6569 | 45516.4172 | 45516.6772 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395421 | AL, Gorgas, resplice AFN dark fibers | Low | Successful | Minor | Planned | DWM | TT | 45470.6226 | 45517 | 45517.25 | 45517 | 45517.25 | 45517.4063 | 45517.4064 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45513.3572 | 45512.445 | 45516.9868 | 45519.4679 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395458 | AL, Anniston, Eastern Division Office/Warehouse, LTE Path Alignment | Low | Successful | Minor | Planned | MSM | TT | 45474.3819 | 45483.4792 | 45483.6458 | 45483.4792 | 45483.5625 | 45483.5638 | 45483.564 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45476.5005 | 45476.4983 | 45483.4637 | 45519.4508 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395478 | MS, Gulfport, Landon Telecom Hub Fiber Migration (From Old Building) - Phase 1 | Low | Successful | Minor | Planned | DRB | TT | 45474.6759 | 45504.375 | 45504.75 | 45504.3785 | 45504.7333 | 45505.4262 | 45505.4263 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45485.6246 | 45484.6148 | 45504.3597 | 45505.4263 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395482 | MS, Gulfport, Landon Telecom Hub Fiber Migration (From Old Building) - Phase 2 (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45474.683 | 45512.9583 | 45513.3333 | 45513.2632 | 45513.5458 | 45515.4816 | 45515.4822 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45509.529 | 45509.5253 | 45512.9442 | 45515.4822 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395485 | GA, Taylor Ridge MW / Dug Gap EBTS, 6GHz to 11GHz MW Radio Upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45474.715 | 45502.3333 | 45503.7917 | 45502.3333 | 45503.7917 | 45504.5275 | 45504.5277 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45491.5795 | 45491.5605 | 45502.3177 | 45519.4736 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395486 | GA, Taylor Ridge MW / Dug Gap EBTS, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Medium | Successful | Moderate | Planned | JMN | TT | 45474.7151 | 45504.3333 | 45505.7917 | 45505.7931 | 45505.8368 | 45506.315 | 45506.3157 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45491.5773 | 45491.5625 | 45504.318 | 45519.4736 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395487 | GA, Taylor Ridge MW / Summerville MW, 6GHz to 11GHz MW Radio Upgrade | Medium | Successful | Moderate | Planned | JMN | TT | 45474.7406 | 45503.3333 | 45504.7917 | 45503.4215 | 45504.759 | 45505.4275 | 45505.4278 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45491.5778 | 45491.5657 | 45503.3178 | 45519.4736 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395488 | GA, Taylor Ridge MW / Summerville MW, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Medium | Successful | Moderate | Planned | JMN | TT | 45474.7407 | 45505.3333 | 45506.7917 | 45506.4319 | 45506.5285 | 45507.4867 | 45507.487 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45491.5781 | 45491.5723 | 45505.3183 | 45519.4736 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395593 | GA, LaGrange, Transmission ROW, Splice new section of OPGW | Low | Successful | Minor | Planned | JLM | TT | 45475.6486 | 45493.2917 | 45493.75 | 45493.3354 | 45493.4931 | 45494.4446 | 45494.4447 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45476.4536 | 45476.4522 | 45493.2846 | 45519.4626 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395617 | AL, South Alabama Area, Migrate Region 6 DWDM Circuits to New ADMs (BACKUP DATE) | Medium | Successful | Moderate | Unplanned | DRB | TT | 45476.5081 | 45512.4167 | 45512.7083 | 45512.4167 | 45512.5382 | 45512.6066 | 45512.6071 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45511.4581 | 45511.4351 | 45512.4025 | 45512.6071 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395648 | GA, WAYNESBORO, VOGTLE 3 & 4 BLDG 147A, ATS REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45478.4292 | 45503.2917 | 45507.2083 | 45503.2917 | 45507.2083 | 45507.486 | 45507.4861 | 2024 | 2024-08 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45491.5828 | 45491.5215 | 45503.2761 | 45507.4861 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395649 | GA, SKY VALLEY, ALEX MTN TRANSPORT, AC DISCONNECT BREAKER REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45478.4348 | 45489.2917 | 45492.625 | 45489.2917 | 45491.5 | 45491.5115 | 45491.5117 | 2024 | 2024-07 | Successful | Facilities Component | Generator | Repair | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45481.5192 | 45481.5048 | 45489.284 | 45498.7092 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395722 | MS, Heidelberg, Migrate Heidelberg Sub and Heidelberg Denbury Sub to NGTAN | Low | Successful | Minor | Planned | DRB | TT | 45476.5451 | 45532.375 | 45532.75 | 45532.375 | 45532.6875 | 45533.4054 | 45533.4055 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45516.3705 | 45515.4964 | 45532.3616 | 45533.4055 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000395854 | AL, N Auburn Transport, Move Ciena ADM Modules and Upgrade T-Series Path | Medium | Successful | Moderate | Planned | GPB | TT | 45481.6487 | 45502.75 | 45503.9583 | 45502.75 | 45503.9583 | 45504.5353 | 45504.5363 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45491.5788 | 45491.5308 | 45502.7344 | 45504.5363 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000395992 | MS, Meridian, MRDN Telecom Hub-DO 144 Fiber Emergency Repair | Medium | Successful | Moderate | Planned | DRB | TT | 45483.5033 | 45518.3333 | 45518.8333 | 45518.3333 | 45518.7896 | 45519.4926 | 45519.4929 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45509.3479 | 45507.522 | 45518.3203 | 45519.4929 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396057 | AL, Oxford, Splicing ERPS fibers to turn up New GreenBrier OLT | Low | Successful | Minor | Planned | DKG | TT | 45484.4367 | 45490.2917 | 45492.75 | 45490.2917 | 45491.75 | 45492.5458 | 45492.5459 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45485.5494 | 45485.4653 | 45490.2843 | 45519.4588 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396069 | MS, Gulfport, Seaway Rd, Fiber Repair/No MPC Traffic | Low | Successful | Minor | Planned | DRB | TT | 45484.5793 | 45493.375 | 45493.75 | 45493.3847 | 45493.4139 | 45494.4454 | 45494.4455 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45485.61 | 45485.4847 | 45493.368 | 45494.4455 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396071 | GA, Various Locations, Remove Unused Ciena cards. | Low | Successful | Minor | Planned | ADL | TT | 45484.5935 | 45517.375 | 45517.5833 | 45517.375 | 45517.5833 | 45519.5174 | 45519.5175 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45509.4891 | 45509.4878 | 45517.3618 | 45519.5175 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396072 | GA, Various Locations, Remove Unused Ciena cards. | Low | Successful | Minor | Planned | ADL | TT | 45484.5967 | 45505.4167 | 45505.5833 | 45505.4167 | 45505.5833 | 45507.4876 | 45507.4877 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45491.4924 | 45491.4906 | 45505.4017 | 45507.4877 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396078 | MS, Gulfport, Landon Telecom Hub, Circuit Rerouting Due to Upcoming OSP Fiber Work | Low | Successful | Minor | Planned | DRB | TT | 45484.6236 | 45498.375 | 45498.7083 | 45498.375 | 45498.7083 | 45502.4045 | 45502.4045 | 2024 | 2024-07 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45491.4963 | 45491.4881 | 45498.3589 | 45502.4045 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396079 | MS, Gulfport, Landon Telecom Hub, Circuit Rerouting Due to Upcoming OSP Fiber Work (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45484.6237 | 45503.375 | 45503.7083 | 45503.375 | 45503.7083 | 45504.5374 | 45504.5376 | 2024 | 2024-07 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45491.4964 | 45491.4887 | 45503.3595 | 45504.5376 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396108 | GA, BRUNSWICK EBTS, REPLACE ERICSSON MINI-LINK MICROWAVE ANTENNA | Low | Successful | Minor | Planned | WKA | TT | 45485.6209 | 45497.3333 | 45498.6667 | 45497.3333 | 45497.6972 | 45498.4541 | 45498.4542 | 2024 | 2024-07 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45496.3249 | 45495.7144 | 45497.3169 | 45519.4801 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396121 | GA, Atlanta, GPC HQ, Slot and Fiber ADM Cards for Express Route (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45484.4211 | 45498.375 | 45498.5833 | 45498.375 | 45498.5833 | 45502.4038 | 45502.404 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45496.3597 | 45495.7175 | 45498.3589 | 45502.404 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396211 | AL, Autagaville, Various sites, NOKIA IXR SAR In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45489.478 | 45498.375 | 45498.7083 | 45498.375 | 45498.5965 | 45498.6828 | 45498.683 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45491.4963 | 45491.4858 | 45498.3589 | 45498.683 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396317 | MS, Meridian Area, Open JV Splice Enclosure to Test & Isolate Long-haul Fiber Damage | Low | Successful | Minor | Planned | DRB | TT | 45491.5823 | 45497.4167 | 45497.625 | 45497.4167 | 45497.5354 | 45498.4633 | 45498.4635 | 2024 | 2024-07 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45491.6014 | 45491.5984 | 45497.4004 | 45498.4635 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396462 | AL, Plant Barry, hot cut to relocate ADSS to new pole line | Low | Successful | Minor | Planned | RRR | TT | 45490.9299 | 45516.7917 | 45516.9583 | 45516.7944 | 45517.0931 | 45517.4056 | 45517.4059 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45512.4026 | 45512.3932 | 45516.7784 | 45519.4679 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396506 | GA, Sandy Plains EBTS, turning off G9702 Sandy Plains site | Low | Successful | Minor | Planned | CDL | TT | 45492.4961 | 45497.3333 | 45499.8333 | 45497.3333 | 45499.8333 | 45502.4019 | 45502.402 | 2024 | 2024-07 | Successful | Transport Device | Antenna System | Remove/Retire | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45495.6186 | 45495.4473 | 45497.3169 | 45502.402 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396512 | AL, GA, Leaflake-Douglas Hills, NOKIA IXR SAR In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45492.6849 | 45502.375 | 45502.7083 | 45502.375 | 45502.7083 | 45503.5452 | 45503.5453 | 2024 | 2024-07 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45496.49 | 45496.4815 | 45502.3594 | 45503.5453 | 2024-Q3 | 2024-07 | 2024-Q3
CRQ000000396545 | GA, Alto Mtn., Taylor Ridge 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45495.453 | 45516.3333 | 45517.7917 | 45516.3333 | 45517.7917 | 45519.5088 | 45519.5089 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45504.9204 | 45504.5307 | 45516.32 | 45519.5089 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396546 | GA, Alto Mtn., Taylor Ridge 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45495.4531 | 45518.3333 | 45519.7917 | 45518.3333 | 45518.8222 | 45519.5094 | 45519.5095 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45504.9204 | 45504.5333 | 45518.3203 | 45519.5095 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396554 | AL, Webb Transport, Generator and ATS Replacement | Low | Successful | Minor | Planned | KNL | TT | 45495.5496 | 45502.25 | 45870.7917 | 45502.25 | 45505.7917 | 45507.4842 | 45507.4844 | 2024 | 2024-08 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45496.3251 | 45495.7197 | 45502.2343 | 45507.4844 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396651 | GA/AL Various Locations, Ciena 6500 Circuit Migrations Express Route | Medium | Successful | Moderate | Planned | ADL | TT | 45495.701 | 45504.7292 | 45504.9993 | 45504.7292 | 45504.9993 | 45505.6868 | 45505.6871 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45498.5676 | 45498.4687 | 45504.721 | 45505.6871 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396654 | AL, Bald Knob to SDC, 6GHZ to 11GHZ M/W upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | MLC | TT | 45495.7049 | 45516.3958 | 45519.75 | 45516.3958 | 45519.75 | 45520.4313 | 45520.4314 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | MLC | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45503.3217 | 45502.6516 | 45516.3756 | 45520.4314 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396726 | GA, Hamilton Transmission ROW, Splice to new UG COAM route | Medium | Successful | Moderate | Planned | JLM | TT | 45496.3917 | 45517.75 | 45518.0833 | 45517.75 | 45518.0833 | 45519.5195 | 45519.5197 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45512.4222 | 45512.388 | 45517.7369 | 45519.5197 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396727 | GA, Hamilton Transmission ROW, Splice to new UG COAM route (BACKUP DATE) | Medium | Successful | Moderate | Planned | JLM | TT | 45496.3917 | 45518.75 | 45519.0833 | 45518.75 | 45519.0833 | 45519.5201 | 45519.5203 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | JM | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45512.4229 | 45512.3891 | 45518.7371 | 45519.5203 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396873 | AL, Alabaster, Splicing in one Fiber for C-spire location. | Low | Successful | Minor | Planned | DKG | TT | 45498.4213 | 45509.25 | 45511.7917 | 45509.25 | 45511.7917 | 45512.3764 | 45512.3765 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45498.5335 | 45498.4789 | 45509.2354 | 45519.4588 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000396983 | AL/GA Corporate offices, Add new connection to Linc IT Firewalls | Low | Successful | Minor | Planned | DRI | TT | 45498.569 | 45516.4583 | 45516.5417 | 45516.4583 | 45516.5417 | 45516.673 | 45516.6731 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45509.5158 | 45509.5088 | 45516.445 | 45516.6731 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397028 | AL, Autaugaville, Plant Harris, Re-route fiber path between SAR nodes. | Low | Successful | Minor | Planned | MPH | TT | 45499.7238 | 45518.6875 | 45518.7292 | 45518.7326 | 45518.7417 | 45520.4325 | 45520.4326 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45503.3256 | 45502.7023 | 45518.6676 | 45520.4326 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397031 | AL, South Bessemer Colo Hut, Reconfigure Splices to cut in new C-spire equipment | Medium | Successful | Moderate | Planned | RRR | TT | 45501.515 | 45525.041 | 45525.1667 | 45525.041 | 45525.1667 | 45525.4147 | 45525.4148 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45512.4353 | 45512.3995 | 45525.0297 | 45525.4148 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397045 | GA, Aerial LTE A8038, moving the MW dish 50 ft up the tower on the LTE boom | Low | Successful | Minor | Planned | CDL | TT | 45502.5415 | 45516.3333 | 45520.8333 | 45516.3333 | 45520.3958 | 45520.4159 | 45520.416 | 2024 | 2024-08 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45503.3248 | 45502.6996 | 45516.32 | 45520.416 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397057 | AL, Sylacauga EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45502.8812 | 45539.4167 | 45539.625 | 45539.4167 | 45539.625 | 45540.341 | 45540.3411 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45526.6439 | 45526.6408 | 45539.4041 | 45540.3411 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397058 | AL, Coaling EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45502.8848 | 45525.4167 | 45525.5833 | 45525.4167 | 45525.5833 | 45526.4677 | 45526.4678 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45520.4173 | 45520.4127 | 45525.4048 | 45526.4678 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397100 | AL, Waverly, Pear Tree, Add Ciena 6500's Between SDC and N Auburn. (BACKUP DATE) | Medium | Successful | Moderate | Planned | GPB | TT | 45503.8778 | 45512.75 | 45513 | 45512.75 | 45513 | 45516.3792 | 45516.3795 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45506.3391 | 45505.7092 | 45512.7359 | 45516.3795 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397126 | AL, Birmingham, APC HQ, NOKIA SAR SR7 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45499.653 | 45509.75 | 45509.875 | 45509.75 | 45509.8132 | 45510.3852 | 45510.3854 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45503.3236 | 45502.6905 | 45509.7355 | 45510.3854 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397130 | GA, Atlanta, Macon, GPC HQ, Key St, NOKIA SAR SR7 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45499.6827 | 45523.7083 | 45523.9167 | 45523.7083 | 45523.9167 | 45524.3852 | 45524.3853 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45503.3278 | 45502.7038 | 45523.696 | 45524.3853 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397138 | AL, Theodore, Cut new South Mobile Crew HQ fiber into Coastal OPGW route | Medium | Successful | Moderate | Planned | RRR | TT | 45501.5359 | 45524.7917 | 45524.9167 | 45524.3451 | 45524.9556 | 45525.4136 | 45525.4138 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | RRR | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45503.3479 | 45502.7079 | 45524.7796 | 45525.4138 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397157 | GA, Chamblee, 5180 Peachtree Blvd, Relocation Project (Splicing) | Low | Successful | Minor | Planned | SDG | TT | 45502.4537 | 45509.9375 | 45510.25 | 45509.9375 | 45510.25 | 45510.3874 | 45510.3875 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | SDG | APC |  | STI | 45503.3242 | 45502.692 | 45509.9299 | 45510.3875 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397158 | GA, Chamblee, 5180 Peachtree Blvd, Relocation Project (Splicing) (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45502.4537 | 45510.9375 | 45511.25 | 45510.9375 | 45511.25 | 45511.4871 | 45511.4872 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | SDG | APC |  | STI | 45503.3242 | 45502.6924 | 45510.9301 | 45511.4872 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397182 | AL, Birmingham, 600 18th St APC building, Installing new power in fiber room 3. | Low | Successful | Minor | Planned | SDG | TT | 45503.4098 | 45512.875 | 45513.25 | 45512.9271 | 45513.0653 | 45515.48 | 45515.4801 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45511.487 | 45511.4801 | 45512.8609 | 45515.4801 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397309 | AL, Phenix City Transport, generator and ATS replacement | Low | Successful | Minor | Planned | KNL | TT | 45509.4725 | 45516.25 | 45520.8333 | 45516.25 | 45520.8333 | 45523.3912 | 45523.3914 | 2024 | 2024-08 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | KNL | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45510.5717 | 45510.5689 | 45516.2366 | 45523.3914 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397311 | GA, Madison G9247 Bostwick LTE, Temp leased service disconnect for conduit repair. | Low | Successful | Minor | Planned | SPA | TT | 45509.4851 | 45516.375 | 45516.625 | 45516.375 | 45516.625 | 45516.6765 | 45516.6766 | 2024 | 2024-08 | Successful | Facilities Component | Cables, jumpers, and connectors | Repair | Transport | SEP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45510.5743 | 45510.5735 | 45516.3617 | 45516.6766 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397327 | AL, Anniston Crew HQ Transport, changing ONT to different PONS | Low | Unsuccessful | Minor | Planned | ALL | TT | 45504.6215 | 45513.375 | 45513.8333 | 45513.3799 | 45513.4667 | 45515.4838 | 45515.4839 | 2024 | 2024-08 | Unsuccessful | Transport Device | Optical Transport Equipment | Migrate | Transport | AC | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45510.5707 | 45510.5673 | 45513.3609 | 45538.7908 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397328 | AL, Anniston, Crew HQ Transport, changing ONT to different PONS (BACKUP DATE) | Low | Successful | Minor | Planned | ALL | TT | 45504.6216 | 45538.375 | 45538.8333 | 45538.375 | 45538.8333 | 45539.3897 | 45539.3898 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | AC | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45517.5606 | 45517.5563 | 45538.3622 | 45539.3898 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397368 | AL, Mobile/Wilmer, Leased circuit testing | Low | Successful | Minor | Planned | DRI | TT | 45505.6942 | 45517.5417 | 45517.6667 | 45517.5417 | 45517.5806 | 45519.5181 | 45519.5182 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Repair | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45509.6802 | 45509.68 | 45517.5285 | 45519.5182 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397423 | GA, LAKELAND EBTS/STOCKTON (GA) LTE, REALIGN MINI-LINK M/W PATH | Low | Successful | Minor | Planned | WKA | TT | 45509.5738 | 45516.3333 | 45516.7083 | 45516.3542 | 45516.5042 | 45516.8714 | 45516.8715 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | WK | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45510.571 | 45510.57 | 45516.32 | 45519.4801 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397492 | GA, GPC HQ, Reload ATL EPG2 to fix context ID mismatch | Medium | Successful | Moderate | Unplanned | JBS | TT | 45511.6737 | 45523.125 | 45523.2083 | 45523.125 | 45523.2083 | 45523.6866 | 45523.6869 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Repair | Transport | JBS | COM |  | CORE NETWORK ENGINEERING | 45519.5821 | 45519.5642 | 45523.1126 | 45523.6869 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397493 | GA, GPC HQ, Reload ATL EPG2 to fix context ID mismatch (BACKUP DATE) | Medium | Successful | Moderate | Planned | JBS | TT | 45511.6738 | 45524.125 | 45524.2083 | 45524.125 | 45524.2083 | 45525.413 | 45525.4132 | 2024 | 2024-08 | Successful | Transport Device | Other Transport Device | Repair | Transport | JBS | COM |  | CORE NETWORK ENGINEERING | 45519.5804 | 45519.566 | 45524.1127 | 45525.4132 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397520 | GA, LaGrange, Transmission ROW, Splice new section of OPGW | Low | Successful | Minor | Planned | MAR | TT | 45509.7737 | 45528.2917 | 45528.75 | 45528.3528 | 45528.5292 | 45530.4347 | 45530.4348 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45510.5872 | 45510.5841 | 45528.2772 | 45530.4348 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397522 | GA, Gordon ILA, installing new DC Power to Relay Rack | Low | Successful | Minor | Planned | SDG | TT | 45509.9733 | 45517.875 | 45518.25 | 45517.875 | 45518.25 | 45520.4317 | 45520.4318 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45510.5752 | 45510.5743 | 45517.8619 | 45520.4318 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397523 | GA, Gordon ILA, installing new DC Power to Relay Rack (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45509.9733 | 45518.875 | 45519.25 | 45518.9264 | 45519.1333 | 45519.5209 | 45519.521 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | STI | 45510.5752 | 45510.5748 | 45518.8621 | 45519.521 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397556 | AL, Anniston, Eastern Division Warehouse, Power Delivery Pole Replacement | Low | Successful | Minor | Planned | MSM | TT | 45510.6307 | 45513.3542 | 45513.6458 | 45513.3562 | 45513.6792 | 45515.493 | 45515.4931 | 2024 | 2024-08 | Successful | Facilities Component | Transformer | Repair | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45510.655 | 45510.6516 | 45513.347 | 45519.4508 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397669 | GA, Various Locations, NOKIA SAR SRa8 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45513.5432 | 45519.375 | 45519.5833 | 45519.375 | 45519.5312 | 45519.5345 | 45519.5349 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45517.5607 | 45517.5596 | 45519.3622 | 45519.5349 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397673 | AL, Montgomery, Leeds, NOKIA SAR 7750 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45513.5743 | 45526.4167 | 45526.5833 | 45526.4278 | 45526.5458 | 45526.6435 | 45526.6435 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45519.3625 | 45518.5494 | 45526.4051 | 45526.6435 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397707 | AL, Kennedy, Remove and replace LTE hybrid cable | Low | Successful | Minor | Planned | JBT | TT | 45516.5862 | 45532.375 | 45532.75 | 45532.375 | 45532.75 | 45533.4038 | 45533.4044 | 2024 | 2024-08 | Successful | Facilities Component | Cables, jumpers, and connectors | Remove/Retire | Transport | JBT | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45520.3531 | 45519.6184 | 45532.3616 | 45533.4044 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397709 | AL, Auburn, splicing dark fibers for Aubix | Low | Successful | Minor | Planned | DWM | TT | 45516.5935 | 45538.7917 | 45539.125 | 45538.7958 | 45538.9722 | 45539.3905 | 45539.3906 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45519.6102 | 45519.6083 | 45538.779 | 45539.3906 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397710 | AL, Auburn, splicing dark fiber for Aubix (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45516.5935 | 45539.7917 | 45540.125 | 45539.7917 | 45540.125 | 45540.3427 | 45540.3428 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45519.6102 | 45519.6089 | 45539.7792 | 45540.3428 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397753 | AL, Various Sites, NOKIA SAR 7750 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45513.6175 | 45524.4167 | 45524.625 | 45524.4167 | 45524.5417 | 45524.5715 | 45524.5716 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45519.3621 | 45518.5469 | 45524.4045 | 45524.5716 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397812 | GA, Augusta Transport, Replace MDR8000's with Nokia MPR9500 | Medium | Successful | Moderate | Unplanned | JAM | TT | 45517.5247 | 45524.3333 | 45524.75 | 45524.3333 | 45524.7549 | 45525.4123 | 45525.4126 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTN | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45520.4601 | 45520.4253 | 45524.3211 | 45525.4126 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397813 | GA, Augusta Transport, Replace MDR8000's with Nokia MPR9500 (BACKUP DATE) | Medium | Successful | Moderate | Planned | JAM | TT | 45517.5248 | 45525.3333 | 45525.75 | 45525.3333 | 45525.75 | 45526.4657 | 45526.466 | 2024 | 2024-08 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JTN | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45520.4598 | 45520.4261 | 45525.3214 | 45526.466 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000397821 | AL, Hope Hull, splicing fiber around Pintlala TS for AFN upgrade | Low | Successful | Minor | Planned | DHA | TT | 45516.6718 | 45538.7917 | 45539.125 | 45538.825 | 45538.9729 | 45539.3846 | 45539.3847 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45519.6066 | 45519.6065 | 45538.779 | 45539.3847 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397822 | AL, Hope Hull, spicing fiber around Pintlala TS for AFN upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | DHA | TT | 45516.6718 | 45551.7917 | 45552.125 | 45551.7917 | 45552.125 | 45553.4299 | 45553.4301 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45546.6334 | 45546.6239 | 45551.7807 | 45553.4301 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397832 | AL, Pinckard TS and Slocomb TS, splicing new cable into existing OPGW | Low | Successful | Minor | Planned | DHA | TT | 45517.4372 | 45539.7917 | 45540.2917 | 45539.7931 | 45539.9132 | 45540.3417 | 45540.3418 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45519.6103 | 45519.61 | 45539.7792 | 45540.3418 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397926 | MS, Meridian Area, Repair JV Fiber between York IFN and Meridian DO Due to Damage (BACKUP DATE) | Medium | Successful | Moderate | Planned | DRB | TT | 45517.6585 | 45546.3333 | 45546.8333 | 45546.3333 | 45546.7528 | 45547.3794 | 45547.3796 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45526.3662 | 45525.4362 | 45546.3217 | 45547.3796 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397956 | AL, Auburn EBTS, DT Auburn A9107, Adding CBRS to the site | Low | Successful | Minor | Planned | CDL | TT | 45518.639 | 45530.3333 | 45534.8333 | 45530.3333 | 45534.8333 | 45538.3789 | 45538.379 | 2024 | 2024-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45519.5998 | 45519.5984 | 45530.3192 | 45538.379 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397995 | MS, GULFPORT, MPC OPS CENTER, UPS Units A & B PREVENTIVE MAINTENANCE | Low | Successful | Minor | Planned | DRB | TT | 45519.6541 | 45535.375 | 45535.75 | 45535.4118 | 45535.6917 | 45538.3828 | 45538.383 | 2024 | 2024-09 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45520.4413 | 45520.427 | 45535.3621 | 45538.383 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000397996 | MS, GULFPORT, MPC OPS CENTER, UPS Units A & B PREVENTIVE MAINTENANCE (BACKUP DATE) | Low | Successful | Minor | Planned | DRB | TT | 45519.6542 | 45542.375 | 45542.75 | 45542.4313 | 45542.6188 | 45544.3944 | 45544.3945 | 2024 | 2024-09 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45520.4413 | 45520.4275 | 45542.363 | 45544.3945 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398054 | AL, Tallassee LTE, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45523.5476 | 45531.4167 | 45531.5833 | 45531.4167 | 45531.5833 | 45531.6287 | 45531.6288 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45523.6008 | 45523.5961 | 45531.4027 | 45531.6288 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398056 | AL, Eutaw LTE, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45523.5502 | 45533.4167 | 45533.5833 | 45533.4167 | 45533.5833 | 45534.409 | 45534.4091 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45523.6206 | 45523.6176 | 45533.4035 | 45534.4091 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398069 | GA, Atlanta Virginia Transport, Add Ciena Power Connections to DC Plant | Low | Successful | Minor | Planned | ADL | TT | 45523.8706 | 45532.375 | 45532.7083 | 45532.375 | 45532.7083 | 45533.4031 | 45533.4032 | 2024 | 2024-08 | Successful | Facilities Component | DC Backup System | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45525.7762 | 45525.4249 | 45532.3616 | 45533.4032 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398083 | AL, Oxford, splicing fibers to turn device B paths to Greenbrier OLT | Low | Successful | Minor | Planned | DKG | TT | 45524.4006 | 45530.25 | 45534.75 | 45530.25 | 45534.75 | 45538.3778 | 45538.378 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45525.7751 | 45525.4207 | 45530.2358 | 45538.378 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398084 | AL, Oxford, splicing fibers to turn device B paths to Greenbrier OLT (BACKUP DATE) | Low | Successful | Minor | Planned | DKG | TT | 45524.4007 | 45538.25 | 45541.75 | 45538.25 | 45541.75 | 45544.4002 | 45544.4003 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45525.7751 | 45525.4212 | 45538.2372 | 45544.4003 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398089 | AL, Auburn, splicing in new Point Broadband location | Low | Successful | Minor | Planned | DKG | TT | 45524.4302 | 45530.25 | 45532.75 | 45530.4292 | 45532.3597 | 45533.4021 | 45533.4025 | 2024 | 2024-08 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45525.7811 | 45525.4192 | 45530.2358 | 45533.4025 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398148 | GA, Rome OP HQ, Ciena 6500 TID Consolidate | Medium | Successful | Moderate | Planned | GPB | TT | 45523.6069 | 45530.4167 | 45530.5833 | 45530.4167 | 45530.5 | 45530.6705 | 45530.6707 | 2024 | 2024-08 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45526.4834 | 45525.4227 | 45530.4025 | 45530.6707 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398167 | AL, Wetumpka, LH Fiber ROW, Fiber Remediation splice | Low | Successful | Minor | Planned | DHA | TT | 45524.3977 | 45544.7917 | 45545.0417 | 45544.7917 | 45545.0417 | 45545.3937 | 45545.3938 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45525.7767 | 45525.4302 | 45544.7798 | 45545.3938 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398183 | AL, South Alabama Area, Region 6 DWDM Upgrade Project Cleanup Work | Low | Successful | Minor | Planned | DRB | TT | 45524.5768 | 45539.4167 | 45539.7083 | 45539.4167 | 45539.6028 | 45539.6096 | 45539.6098 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45525.7752 | 45525.4264 | 45539.4041 | 45539.6098 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398185 | GA, Athens Transport Hub, test generator with load | Low | Successful | Minor | Planned | PCM | TT | 45524.5891 | 45532.375 | 45532.5 | 45532.375 | 45532.5 | 45532.5612 | 45532.5613 | 2024 | 2024-08 | Successful | Facilities Component | Generator | Repair | Transport | PCM | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45525.7781 | 45525.4235 | 45532.3616 | 45532.5613 | 2024-Q3 | 2024-08 | 2024-Q3
CRQ000000398349 | GA, Marietta EBTS, Blackwell Sub G8702, moving the site from the CAT to the shelter | Low | Successful | Minor | Planned | CDL | TT | 45526.6256 | 45538.4583 | 45541.8333 | 45538.4583 | 45541.8333 | 45544.3927 | 45544.3929 | 2024 | 2024-09 | Successful | Transport Device | Antenna System | Migrate | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45533.413 | 45533.4086 | 45538.4456 | 45544.3929 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398359 | GA, Augusta Transport/ Stevens Creek EBTS, repair M/W hardware | Low | Successful | Minor | Planned | JAM | TT | 45527.3852 | 45538.3333 | 45538.75 | 45538.4194 | 45538.7319 | 45539.3882 | 45539.3883 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | JTN | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45530.6541 | 45530.6527 | 45538.3206 | 45539.3883 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398360 | GA, Augusta Transport/ Stevens Creek EBTS, repair M/W hardware (BACKUP DATE) | Low | Successful | Minor | Planned | JAM | TT | 45527.3853 | 45539.3333 | 45539.75 | 45539.3333 | 45539.5354 | 45540.3405 | 45540.3406 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Repair | Transport | JTN | SCS | INFRASTRUCTURE SERVICES | FO SE OPERATIONS | 45530.6541 | 45530.6534 | 45539.3207 | 45540.3406 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398381 | AL/MS, Various Sites, NOKIA SAR 7750 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45527.6853 | 45540.4167 | 45540.625 | 45540.4167 | 45540.625 | 45540.6367 | 45540.6368 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45530.6607 | 45530.6583 | 45540.4042 | 45540.6368 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398432 | AL/MS, Various Sites, NOKIA SAR 7750 ISSU In Service Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45527.7226 | 45552.375 | 45552.7083 | 45552.3458 | 45552.5264 | 45553.378 | 45553.3782 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45530.6618 | 45530.6613 | 45552.3641 | 45553.3782 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398533 | AL, Western ICON Ring, Reconfigure ports at Alberta City, Holt 1 & 2 ICONs | Medium | Successful | Moderate | Planned | RPY | TT | 45530.5224 | 45553.3958 | 45553.6667 | 45553.4028 | 45553.4867 | 45553.6176 | 45553.618 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45539.4161 | 45538.5451 | 45553.3781 | 45553.618 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398557 | AL, Northport, Tuscaloosa Co HS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45531.3667 | 45538.4167 | 45538.6562 | 45538.4167 | 45538.6562 | 45538.7045 | 45538.7047 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45532.3117 | 45531.6649 | 45538.4039 | 45538.7047 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398558 | AL, Ashland EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45531.3757 | 45540.4167 | 45540.625 | 45540.4167 | 45540.625 | 45544.4024 | 45544.4027 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45532.3117 | 45531.6655 | 45540.4042 | 45544.4027 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398579 | GA, Macon, LTE Core Router Replacement (Phase 1) | Medium | Successful | Moderate | Planned | DRI | TT | 45531.6391 | 45539 | 45539.1667 | 45539 | 45539.0521 | 45539.387 | 45539.3874 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45532.3306 | 45531.7135 | 45538.9873 | 45539.3874 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398580 | GA, Macon, LTE Core Router Replacement (Phase 2) | Medium | Successful | Moderate | Planned | DRI | TT | 45531.6435 | 45540 | 45540.1667 | 45540 | 45540.066 | 45540.3396 | 45540.3399 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45532.3311 | 45531.7139 | 45539.9875 | 45540.3399 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398595 | AL, Malvern ENODEB, Upgrade Defective Generator Transfer Switch | Low | Successful | Minor | Planned | LPE | TT | 45532.3798 | 45540.375 | 45540.5833 | 45540.375 | 45540.5833 | 45544.4017 | 45544.402 | 2024 | 2024-09 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45534.4286 | 45534.4103 | 45540.3626 | 45544.402 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398600 | GA, Ludowici ENODEB, DC Plant Modification | Low | Successful | Minor | Planned | LPE | TT | 45532.4052 | 45544.375 | 45544.3958 | 45544.375 | 45544.3958 | 45544.8664 | 45544.8665 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45534.4265 | 45534.4114 | 45544.3631 | 45544.8665 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398606 | GA, Sea Island ENODEB, DC Plant Modification | Low | Successful | Minor | Planned | LPE | TT | 45532.4359 | 45544.4792 | 45544.5 | 45544.4792 | 45544.5 | 45544.8675 | 45544.8677 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | WLP | COM | PRODUCT DEVELOPMENT & SUPPORT | SE RAN OPS | 45534.4273 | 45534.4128 | 45544.4603 | 45544.8677 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398615 | AL, OAKGROVE LOCAL BUSINESS OFFICE, LIFECYCLE REPLACE COMM ROOM UPS | Low | Successful | Minor | Planned | MVW | TT | 45532.5249 | 45549.2917 | 45549.75 | 45549.3472 | 45549.5674 | 45552.341 | 45552.3415 | 2024 | 2024-09 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45534.4298 | 45534.4136 | 45549.2805 | 45552.3415 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398635 | AL, Montgomery, re-route fiber cables from Martin Dam to Jeff St | Medium | Successful | Moderate | Planned | DWM | TT | 45530.4936 | 45554.7917 | 45555.25 | 45554.8257 | 45554.9556 | 45555.2883 | 45555.2888 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45530.6799 | 45530.6668 | 45554.7812 | 45555.2888 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398783 | GA, Alex Mtn - Rabun Gap, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45534.485 | 45551.3333 | 45552.7917 | 45551.3333 | 45552.7708 | 45553.3701 | 45553.371 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45539.3839 | 45538.6311 | 45551.3223 | 45553.371 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398784 | GA, Alex Mtn - Rabun Gap, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45534.4851 | 45553.3333 | 45554.7917 | 45553.3521 | 45553.5444 | 45555.3236 | 45555.3238 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45539.3839 | 45538.6315 | 45553.3226 | 45555.3238 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398859 | AL, MONTGOMERY SDC, Remove 10-dB Pad from SDC-PEARTREE DWDM Span | Medium | Successful | Moderate | Planned | DRB | TT | 45533.691 | 45552.7917 | 45552.875 | 45552.7771 | 45552.8049 | 45553.3674 | 45553.3679 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45547.5489 | 45547.4524 | 45552.7809 | 45553.3679 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398881 | AL, Octagon EBTS A9196, finish tower strengthening and changing guy wires | Low | Successful | Minor | Planned | CDL | TT | 45534.5447 | 45539.4167 | 45541.8333 | 45539.4167 | 45541.8333 | 45544.4008 | 45544.401 | 2024 | 2024-09 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45534.7088 | 45534.5862 | 45539.4041 | 45544.401 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398895 | AL, ANNISTON, EASTERN DIVISION OFFICE, UPS REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45538.3331 | 45556.2917 | 45556.7083 | 45556.3278 | 45556.6687 | 45558.4471 | 45558.4472 | 2024 | 2024-09 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45539.384 | 45538.6323 | 45556.2814 | 45558.4472 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398938 | MS, Laurel Area, Migrate (4) Laurel/Hattiesburg Substations to NGTAN (2-Day Window) | Medium | Successful | Moderate | Planned | DRB | TT | 45538.5826 | 45552.375 | 45553.75 | 45552.3632 | 45553.6778 | 45554.3363 | 45554.3373 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45540.3787 | 45539.6583 | 45552.3641 | 45554.3373 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398947 | GA, Atlanta Virginia Ave Transport, Insert New Ciena 6500 Nodes | Medium | Successful | Moderate | Unplanned | ADL | TT | 45538.6524 | 45544.375 | 45544.7083 | 45544.375 | 45544.7083 | 45544.8654 | 45544.8657 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45540.4078 | 45540.3795 | 45544.3631 | 45544.8657 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398955 | AL, Snowdoun & Holt COLO, NOKIA SAR 7750 Software Upgrades | Low | Successful | Minor | Planned | MPH | TT | 45538.7336 | 45553.4167 | 45553.75 | 45553.4167 | 45553.6042 | 45553.6121 | 45553.6123 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45539.8495 | 45539.6553 | 45553.4059 | 45553.6123 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398973 | AL, Alexander City EBTS A9623, Alex City adding CBRS to the existing booms | Low | Successful | Minor | Planned | CDL | TT | 45539.4086 | 45558.375 | 45562.875 | 45558.375 | 45560.5417 | 45560.5525 | 45560.5526 | 2024 | 2024-09 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45539.8455 | 45539.6182 | 45558.3649 | 45560.5526 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000398974 | AL, Alexander City EBTS A9623, Alex City adding CBRS to the existing booms (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45539.4086 | 45572.4583 | 45575.8333 | 45572.4583 | 45575.8333 | 45579.4342 | 45579.4343 | 2024 | 2024-10 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45566.3986 | 45566.3972 | 45572.4431 | 45579.4343 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000398977 | AL, Warrior EBTS A9122, Bryant Mtn, adding CBRS to the Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45539.4296 | 45581.4583 | 45583.8333 | 45581.4583 | 45583.8333 | 45586.4471 | 45586.4472 | 2024 | 2024-10 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45580.3472 | 45579.6929 | 45581.4449 | 45586.4472 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000398985 | AL, LANETT, WESTPOINT/LANETT EBTS, REPLACE GENERATOR/ATS | Low | Successful | Minor | Planned | MVW | TT | 45539.4822 | 45551.3333 | 45555.7083 | 45551.3333 | 45555.7083 | 45558.4458 | 45558.4459 | 2024 | 2024-09 | Successful | Facilities Component | Generator | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45540.4237 | 45540.4171 | 45551.3223 | 45558.4459 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399000 | AL, DADEVILLE, MARTIN DAM TRANSPORT, REPLACE GENERATOR/ATS | Low | Successful | Minor | Planned | MVW | TT | 45539.7346 | 45558.3333 | 45562.7083 | 45558.3333 | 45560.5417 | 45561.6298 | 45561.63 | 2024 | 2024-09 | Successful | Facilities Component | Generator | Install | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45540.6381 | 45540.6355 | 45558.3232 | 45561.63 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399047 | AL, GA, MS, All Ericsson microwave migrate to new ENM (Ericsson Network Manager) | Low | Successful | Minor | Planned | WJL | TT | 45538.7652 | 45553.4167 | 45553.6667 | 45553.4167 | 45554.4264 | 45555.3263 | 45555.3264 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Migrate | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45547.5053 | 45547.489 | 45553.4059 | 45555.3264 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399050 | AL, Lineville EBTS, rectifier plant replacement | Low | Successful | Minor | Planned | RBK | TT | 45538.9008 | 45545.4167 | 45545.5833 | 45545.4167 | 45545.5833 | 45545.646 | 45545.6461 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Remove/Retire | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45540.3155 | 45539.6153 | 45545.4049 | 45545.6461 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399096 | AL, Birmingham, APC HQ FR #2, Add Ciena 6500 T-Series DC Feeds | Medium | Successful | Moderate | Planned | GPB | TT | 45540.4468 | 45552.75 | 45552.9583 | 45552.75 | 45552.8799 | 45553.3851 | 45553.3855 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45540.6426 | 45540.6316 | 45552.7392 | 45553.3855 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399109 | AL, Selma, Splicing replaced sections of cable | Low | Successful | Minor | Planned | RCA | TT | 45540.4835 | 45551.7917 | 45556.041 | 45551.7917 | 45556.041 | 45558.4464 | 45558.4466 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45540.643 | 45540.6401 | 45551.7807 | 45558.4466 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399168 | GA, Alex Mtn. / Tallulah Falls, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45541.4914 | 45552.3333 | 45553.7917 | 45552.4778 | 45552.7701 | 45554.341 | 45554.3412 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45544.4137 | 45544.4057 | 45552.3224 | 45554.3412 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399169 | GA, Alex Mtn. / Tallulah Falls, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45541.4915 | 45554.3333 | 45555.7917 | 45554.3333 | 45555.7917 | 45558.4214 | 45558.4215 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45544.4137 | 45544.4062 | 45554.3227 | 45558.4215 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399205 | GA, Currahee Mtn. / Carnesville, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45544.4654 | 45572.3333 | 45573.7917 | 45572.3333 | 45573.7917 | 45573.8178 | 45573.8179 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45561.452 | 45561.4516 | 45572.318 | 45573.8179 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399206 | GA, Currahee Mtn. / Carnesville, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45544.4655 | 45586.3333 | 45587.7917 | 45586.4215 | 45586.7819 | 45588.5495 | 45588.5496 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45580.3468 | 45579.6854 | 45586.3205 | 45588.5496 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399222 | AL, Anniston ICON Ring EMP cables to be installed in place of current cables | Medium | Successful | Moderate | Planned | RPY | TT | 45540.6977 | 45586.4792 | 45586.5833 | 45586.4938 | 45586.5674 | 45586.6533 | 45586.6536 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45579.4721 | 45579.4136 | 45586.4595 | 45586.6536 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399263 | GA, Currahee Mtn. / Tallulah Falls, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45544.4135 | 45558.3333 | 45559.7917 | 45558.3333 | 45559.7917 | 45560.5584 | 45560.5585 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45546.4628 | 45546.4472 | 45558.3232 | 45560.5585 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399300 | GA, Atlanta, Georgia Power Corp HQ, LTE Reload ATL EPG2 to fix context ID mismatch (BACKUP DATE) | Medium | Successful | Moderate | Planned | JBS | TT | 45545.4232 | 45555 | 45555.0417 | 45555 | 45555.1208 | 45555.3174 | 45555.3178 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Repair | Transport | JBS | COM |  | CORE NETWORK ENGINEERING | 45546.4809 | 45546.4439 | 45554.9895 | 45555.3178 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399372 | AL, Anniston Crew HQ Transport, changing ONTs back to primary PONs. | Low | Successful | Minor | Planned | ALL | TT | 45546.4201 | 45558.375 | 45558.9167 | 45558.375 | 45558.9167 | 45559.3947 | 45559.3949 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | AC | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45546.4632 | 45546.4491 | 45558.3649 | 45559.3948 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399400 | AL, Warrior, Bryant Mtn EBTS, DC distribution modification. | Low | Successful | Minor | Planned | RBK | TT | 45546.6564 | 45554.4167 | 45554.5833 | 45554.4167 | 45554.5833 | 45555.371 | 45555.3712 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | NW RAN OPS | 45547.4236 | 45547.4156 | 45554.4061 | 45555.3712 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399458 | GA, Savannah ICON Ring, rebuild circuits due to new path | Medium | Successful | Moderate | Planned | RPY | TT | 45546.6483 | 45595.4167 | 45595.6667 | 45595.4167 | 45595.5417 | 45595.5576 | 45595.5578 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45581.3794 | 45580.6046 | 45595.4051 | 45595.5578 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399487 | AL, Montgomery J Street LTE Core router replacement ALJSTMPCR01 | Medium | Successful | Moderate | Planned | DRI | TT | 45547.4903 | 45554 | 45554.1667 | 45554 | 45554.1535 | 45554.3429 | 45554.3432 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45551.3707 | 45547.6533 | 45553.9893 | 45554.3432 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399488 | AL, Montgomery J Street LTE Core router replacement ALJSTMPCR02 | Medium | Successful | Moderate | Planned | DRI | TT | 45547.4919 | 45555 | 45555.1667 | 45555 | 45555.0236 | 45555.3192 | 45555.3195 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45551.3713 | 45547.6541 | 45554.9895 | 45555.3195 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399531 | AL, Configure OOBM switch and OOBM firewalls in Birmingham | Medium | Successful | Moderate | Planned | NHP | TT | 45547.5889 | 45572.75 | 45572.9583 | 45572.75 | 45572.8403 | 45573.4463 | 45573.4466 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | NHP | COM |  | CORE NETWORK ENGINEERING | 45566.5321 | 45566.4961 | 45572.7348 | 45643.7198 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399568 | AL, Cheaha Mtn Transport to North Auburn Transport, 6-11GHZ Licensed MW upgrades | Low | Successful | Minor | Planned | RAD | TT | 45548.5831 | 45558.375 | 45562.75 | 45558.375 | 45560.5417 | 45561.631 | 45561.6311 | 2024 | 2024-09 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | RAD | SCS | INFRASTRUCTURE SERVICES | FO NW-PROJECTS & GENERATION | 45551.3636 | 45548.7163 | 45558.3649 | 45561.6311 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399591 | AL, Talladega TS, splicing dark fiber | Low | Successful | Minor | Planned | DWM | TT | 45551.4317 | 45588.7917 | 45589 | 45588.7937 | 45588.9153 | 45589.4795 | 45589.4797 | 2024 | 2024-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45581.4635 | 45581.4615 | 45588.7793 | 45589.4797 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399592 | AL, Talladega TS, splicing dark fiber (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45551.4318 | 45573 | 45573.25 | 45573 | 45573.25 | 45573.8184 | 45573.8184 | 2024 | 2024-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45558.4917 | 45558.482 | 45572.9849 | 45573.8184 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399598 | Alabama,Abbeville, New FTD 288 Pair Fiber Splicing to ABBEVILLE DS | Low | Successful | Minor | Planned | DKG | HH | 45551.5241 | 45558.25 | 45562.7917 | 45558.25 | 45559.75 | 45560.3891 | 45560.3892 | 2024 | 2024-09 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45553.5508 | 45553.5506 | 45558.2398 | 45560.3892 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399600 | GA, Macon, DCC, Ciena T-Series Power Upgrades | Low | Successful | Minor | Planned | ADL | HH | 45551.5304 | 45559.4167 | 45559.7083 | 45559.4167 | 45559.7083 | 45559.7791 | 45559.7792 | 2024 | 2024-09 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45553.5597 | 45553.5596 | 45559.4067 | 45559.7792 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399658 | GA, Cornelia OH/Long Mtn., 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45551.6987 | 45593.3333 | 45594.7917 | 45593.3333 | 45594.7917 | 45595.3945 | 45595.3946 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45580.3471 | 45579.6873 | 45593.3214 | 45595.3946 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399660 | GA, Currahee Mtn./Cornelia OH, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45551.7072 | 45582.3333 | 45583.7917 | 45582.3333 | 45583.7917 | 45586.4482 | 45586.4483 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45568.4993 | 45568.4982 | 45582.32 | 45586.4483 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399738 | AL, PLANT BARRY, ADMIN COMM ROOM, MOVE NETGUARDIAN | Low | Successful | Minor | Planned | TRC | HH | 45552.5144 | 45559.375 | 45559.7083 | 45559.375 | 45559.7083 | 45559.778 | 45559.7783 | 2024 | 2024-09 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | TC | SCS | INFRASTRUCTURE SERVICES | FO SW-PROJECTS | 45553.5733 | 45553.5646 | 45559.365 | 45559.7783 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000399757 | AL, Maylene LTE A9180, Guy wire replacement | Low | Successful | Minor | Planned | CLI | TT | 45552.6948 | 45600.2917 | 45602.75 | 45600.2917 | 45602.75 | 45603.4983 | 45603.4984 | 2024 | 2024-11 | Successful | Transport Device | Tower Structure | Upgrade/Modify | Transport | CBS | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45595.4807 | 45595.4595 | 45600.2806 | 45603.4984 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000399848 | AL, Elliotsville, Cabinet, Upgrade Eltek Controller Firmware | Low | Successful | Minor | Planned | JGL | HH | 45554.636 | 45576.375 | 45576.75 | 45576.375 | 45576.75 | 45579.4366 | 45579.4368 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45565.6822 | 45565.6072 | 45576.3605 | 45579.4368 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399867 | GA, Offerman Transport, Migrate LTE Circuit to Single-Mode. | Medium | Successful | Moderate | Planned | ADL | TT | 45555.4661 | 45580.4167 | 45580.7083 | 45580.4167 | 45580.4688 | 45580.5931 | 45580.5934 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45560.4153 | 45559.6239 | 45580.4027 | 45580.5934 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399946 | GA, Various Sites, converting 3 LTE DWDM circuits | Medium | Successful | Moderate | Planned | RLJ | TT | 45555.5238 | 45587.4167 | 45587.75 | 45587.4167 | 45587.4583 | 45587.4595 | 45587.4598 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RLJ | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45560.4131 | 45559.6273 | 45587.404 | 45587.4598 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399977 | GA, Meldrim, Transmission ROW, Little Ogeechee/Meldrim cut in line to New Newton Rd sub (WEEK 1) | Medium | Successful | Moderate | Planned | MAR | TT | 45558.4454 | 45579.3333 | 45586.041 | 45579.3333 | 45586.041 | 45586.4453 | 45586.4456 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45566.6306 | 45566.6231 | 45579.3192 | 45586.4462 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399979 | GA, Meldrim, Transmission ROW, Little Ogeechee/Meldrim cut in line to New Newton Rd Sub (WEEK 2) | Medium | Successful | Moderate | Planned | MAR | TT | 45558.4502 | 45586.3333 | 45593.041 | 45586.3333 | 45593.041 | 45593.4276 | 45593.4281 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45566.6303 | 45566.624 | 45586.3205 | 45593.4281 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000399980 | GA, Meldrim, Transmission ROW, Little Ogeechee/Meldrim cut in line to New Newton Rd sub (WEEK 3) | Medium | Successful | Moderate | Planned | MAR | TT | 45558.4529 | 45593.3333 | 45600.041 | 45593.3333 | 45600.041 | 45600.4041 | 45600.4043 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45566.6677 | 45566.6255 | 45593.3214 | 45600.4043 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400011 | GA, Various Locations, Migrate DWDM Ring 1 to New Underground Fiber Route | Medium | Successful | Moderate | Planned | ADL | TT | 45558.7484 | 45580.75 | 45581 | 45580.75 | 45581 | 45581.3717 | 45581.3719 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45572.5371 | 45572.3915 | 45580.7361 | 45581.3719 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400012 | GA, Various Locations, Migrate DWDM Ring 1 to New Underground Fiber Route (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45558.7486 | 45581.7917 | 45582 | 45581.7917 | 45582 | 45582.4218 | 45582.4226 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45572.5366 | 45572.3939 | 45581.7783 | 45582.4226 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400019 | AL, Birmingham Area, Region 4 DWDM Upgrade Project Phase 1 (S. Bessemer/Holt) | Medium | Successful | Moderate | Planned | DRB | TT | 45558.6621 | 45579.4167 | 45579.75 | 45579.4167 | 45579.8528 | 45580.3768 | 45580.3771 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45565.5831 | 45565.5762 | 45579.4026 | 45580.3771 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400027 | AL, APC HQ/JEFF ST, Region 4 DWDM Upgrade Project Phase 2 (T-Series Tie-In) | Medium | Successful | Moderate | Planned | DRB | TT | 45558.7226 | 45580.5833 | 45580.9167 | 45580.5833 | 45580.6951 | 45581.3701 | 45581.3703 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45565.617 | 45565.5806 | 45580.5694 | 45581.3703 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400031 | AL, Auburn, troubleshoot an issue on the LH route between Peartree and Martin Dam | Medium | Successful | Moderate | Planned | DHA | TT | 45558.8992 | 45579.9583 | 45580.25 | 45579.9917 | 45580.1104 | 45580.3759 | 45580.3762 | 2024 | 2024-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45560.4043 | 45559.6208 | 45579.9443 | 45580.3762 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400069 | AL, Clio EBTS A9458, Adding CBRS to the existing Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45559.9405 | 45593.4167 | 45596.8333 | 45593.4167 | 45596.8333 | 45597.3896 | 45597.3898 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45581.3434 | 45580.5718 | 45593.4048 | 45597.3898 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400070 | AL, Clio EBTS A9458, Adding CBRS to the existing Skymounts (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45559.9406 | 45600.4167 | 45604.8333 | 45600.4167 | 45604.8333 | 45607.4962 | 45607.4963 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45580.3893 | 45580.388 | 45600.4057 | 45607.4963 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400150 | GA, Atlanta 241 GPC HQ, Add Breaker to the DC Plant | Low | Successful | Minor | Unplanned | ADL | TT | 45560.4001 | 45560.4375 | 45560.5 | 45560.4375 | 45560.5 | 45561.5072 | 45561.5073 | 2024 | 2024-09 | Successful | Facilities Component | DC Backup System | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45560.4087 | 45560.4078 | 45560.4207 | 45561.5073 | 2024-Q3 | 2024-09 | 2024-Q3
CRQ000000400154 | AL & GA, Birmingham & Atlanta ATT Ciena 6500 Software Upgrades | Medium | Successful | Moderate | Planned | GPB | TT | 45560.4756 | 45572.75 | 45572.9583 | 45572.75 | 45572.9583 | 45573.4439 | 45573.4442 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45565.4966 | 45565.4937 | 45572.7348 | 45573.4442 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400168 | Moving OOBM Cables from Old Switch Stack to Dell Switches for Birmingham Data Center | Medium | Successful | Moderate | Planned | NHP | TT | 45560.6168 | 45573.375 | 45575.875 | 45573.375 | 45575.875 | 45579.4348 | 45579.435 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | NHP | COM |  | CORE NETWORK ENGINEERING | 45568.6536 | 45568.5486 | 45573.3599 | 45643.7198 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400169 | Moving OOBM Cables from Old Switch Stack to Dell Switches for Birmingham Data Center (BACKUP DATE) | Medium | Successful | Moderate | Planned | NHP | TT | 45560.6168 | 45580.375 | 45582.875 | 45580.375 | 45582.875 | 45583.3508 | 45583.3511 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | NHP | COM |  | CORE NETWORK ENGINEERING | 45568.6544 | 45568.5492 | 45580.361 | 45643.7198 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400267 | AL, Anniston, Replace Failed CIENA 6500 LIM-3-3 in ANTNALX01WDM002 Due to Card Failure | Medium | Successful | Moderate | Planned | DRB | TT | 45566.5799 | 45573.75 | 45573.875 | 45573.75 | 45573.7785 | 45573.8225 | 45573.8229 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45568.5795 | 45568.5632 | 45573.735 | 45573.8229 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400271 | GA, Plt Hatch, Replace CIENA 6500 Fan Unit in Shelf 2 Slot 2 | Medium | Successful | Moderate | Planned | DRB | TT | 45566.6019 | 45576.375 | 45576.4583 | 45576.375 | 45576.3903 | 45576.446 | 45576.4463 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45574.3684 | 45573.8209 | 45576.3605 | 45576.4463 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400279 | AL/MS, Tusc/Meridian Area, R4 DWDM Upgrade Project Phase 3 (4 Days) | Medium | Successful | Moderate | Planned | DRB | TT | 45566.703 | 45581.4167 | 45587.9167 | 45581.4167 | 45586.5625 | 45586.6551 | 45586.6556 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45576.4917 | 45576.4753 | 45581.4032 | 45586.6556 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400405 | GA, Carnesville / Commerce, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45567.5527 | 45587.3333 | 45588.7917 | 45587.3333 | 45588.7917 | 45589.4781 | 45589.4782 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45580.3465 | 45579.6816 | 45587.3206 | 45589.4782 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400406 | GA, Carnesville / Commerce, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | SuccessfulwithIssues | Minor | Planned | JMN | TT | 45567.5527 | 45589.3333 | 45590.7917 | 45589.3333 | 45590.6667 | 45593.4266 | 45593.4267 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45580.3465 | 45579.6836 | 45589.321 | 45593.4267 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400519 | GA, Augusta, Transport Building, TID Consolidate DWDM Shelf 001 and 002 | Medium | Successful | Moderate | Planned | ADL | TT | 45568.4543 | 45581.7083 | 45581.9993 | 45581.7083 | 45581.9993 | 45582.4232 | 45582.4234 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45568.5812 | 45568.5761 | 45581.695 | 45582.4234 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400520 | GA, Savannah, SETH, TID Consolidating DWDM Chassis 001 and 002 | Medium | Successful | Moderate | Planned | ADL | TT | 45568.4578 | 45582.7083 | 45582.9993 | 45582.7083 | 45582.9993 | 45583.3517 | 45583.3519 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45568.5816 | 45568.577 | 45582.6952 | 45583.3519 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400551 | AL, Gadsden, spice dark fibers from Gadsden M/W to Centre SS thru Weiss Dam | Low | Successful | Minor | Planned | DWM | TT | 45569.5372 | 45600.7917 | 45601.25 | 45600.7917 | 45601.25 | 45601.6492 | 45601.6493 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45576.485 | 45576.4833 | 45600.7808 | 45601.6493 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400552 | AL, Gadsden, splice dark fibers from Gadsden M/W to Centre SS thru Weis Dam (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45569.5373 | 45602.7917 | 45603.25 | 45602.7917 | 45603.25 | 45603.5061 | 45603.5064 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45576.485 | 45576.4838 | 45602.781 | 45603.5064 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400669 | GA, GPC HQ, LTE Core Router Replacement GAXGPMPCR01 | Medium | Successful | Moderate | Planned | DRI | TT | 45574.7404 | 45581.9583 | 45582.0833 | 45581.9583 | 45582.2812 | 45582.4209 | 45582.4213 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45580.3658 | 45579.6785 | 45581.945 | 45582.4213 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400670 | GA, GPC HQ, LTE Core Router Replacement GAXGPMPCR02 | Medium | Unsuccessful | Moderate | Planned | DRI | TT | 45574.7422 | 45589.9583 | 45590.125 | 45589.9583 | 45590.0403 | 45590.4135 | 45590.4138 | 2024 | 2024-10 | Unsuccessful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45586.5868 | 45586.4694 | 45589.9462 | 45590.4138 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400708 | AL, Octagon EBTS A9196, installing CBRS at 300 ft | Low | Successful | Minor | Planned | CDL | TT | 45575.8392 | 45586.4583 | 45590.8333 | 45586.4583 | 45590.8333 | 45593.4284 | 45593.4286 | 2024 | 2024-10 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45576.482 | 45576.4815 | 45586.4456 | 45593.4286 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400730 | AL, BILLINGSLEY, Cut Central AL Gen Sta. and Billingsley SS NOKIA SARs to COAM fiber. | Low | Successful | Minor | Planned | MPH | TT | 45573.9877 | 45579.5 | 45579.6667 | 45579.5236 | 45579.6569 | 45579.6899 | 45579.6901 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45576.4827 | 45576.4606 | 45579.4859 | 45579.6901 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400767 | AL, Birmingham, Migrating all TA5000 in-band connections to out-band connections | Low | Successful | Minor | Planned | JGL | TT | 45574.8849 | 45583.4583 | 45583.5417 | 45583.4604 | 45583.5417 | 45586.4497 | 45586.4498 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45576.4824 | 45576.4804 | 45583.4453 | 45586.4498 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400799 | GA, Forest Park HQ T267/G8191, adding LTE to the tower | Low | Successful | Minor | Planned | CDL | TT | 45575.7239 | 45581.3333 | 45583.8333 | 45581.3333 | 45583.8333 | 45586.4461 | 45586.4462 | 2024 | 2024-10 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45579.4251 | 45579.4077 | 45581.3199 | 45586.4462 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400822 | AL, Birmingham, 1925 building, Service Level, Fiber Room 1, HVAC replacement | Low | Successful | Minor | Planned | JTA | TT | 45576.5066 | 45586.2708 | 45589.8125 | 45586.2708 | 45589.8125 | 45590.4145 | 45590.4146 | 2024 | 2024-10 | Successful | Facilities Component | HVAC, Cooling, and Ventilation | Upgrade/Modify | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45581.3433 | 45580.5763 | 45586.2511 | 45590.4146 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400853 | GA, Forest Park EBTS G9147, turning off in prep to move site | Low | Successful | Minor | Planned | CDL | TT | 45579.4837 | 45593.4583 | 45597.8333 | 45593.4583 | 45597.8333 | 45600.4048 | 45600.4049 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45581.3436 | 45580.6171 | 45593.4464 | 45600.4049 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400854 | GA, Forest Park EBTS G9147, turning off in prep to move site (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45579.4838 | 45600.4583 | 45604.8333 | 45600.4583 | 45604.8333 | 45607.4972 | 45607.4973 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45581.3436 | 45580.6179 | 45600.4473 | 45607.4973 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000400869 | GA, Macon Transport, Add Ciena T-Series Modules | Medium | Successful | Moderate | Planned | GPB | TT | 45579.6269 | 45586.375 | 45586.8333 | 45586.375 | 45586.4514 | 45587.3871 | 45587.3876 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45581.3804 | 45580.6113 | 45586.3622 | 45587.3875 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400885 | AL, Smiths Station, Goat Rock Fiber Transport, moving SAR-8 to underground route | Low | Successful | Minor | Planned | MAR | TT | 45580.3892 | 45586.75 | 45587 | 45586.7514 | 45586.9181 | 45587.3884 | 45587.3886 | 2024 | 2024-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45581.3433 | 45580.469 | 45586.7373 | 45587.3886 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400958 | AL/MS, APC/Meridian/Hattiesburg, R4 DWDM Upgrade Project Phase 4 (2 Days) | Medium | Successful | Moderate | Planned | DRB | TT | 45579.6786 | 45587.4167 | 45589.9167 | 45587.3958 | 45589.9167 | 45590.4151 | 45590.4154 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45581.47 | 45581.4182 | 45587.404 | 45590.4154 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400969 | AL and GA, Montgomery to Macon, Ciena T-Series Channel Upgrade from 200G to 300G | Medium | Successful | Moderate | Planned | GPB | TT | 45580.3934 | 45593.75 | 45593.9583 | 45593.75 | 45593.8486 | 45594.3845 | 45594.3847 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45588.5727 | 45588.515 | 45593.7382 | 45594.3847 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400986 | GA, Athens Transport, Insert New Ciena 6500 Nodes into Ring 1 | Medium | Successful | Moderate | Unplanned | ADL | TT | 45580.6122 | 45589.7083 | 45589.9993 | 45589.7083 | 45589.9993 | 45590.416 | 45590.4162 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45588.5722 | 45588.5183 | 45589.6961 | 45590.4162 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000400987 | GA, Athens Transport, Insert New Ciena 6500 Nodes into Ring 1 (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45580.6124 | 45593.7083 | 45593.9993 | 45593.7083 | 45593.9993 | 45594.3837 | 45594.384 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45588.571 | 45588.5192 | 45593.6965 | 45594.384 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401075 | GA, Athens / Commerce, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45582.4132 | 45594.3333 | 45595.7917 | 45594.3333 | 45595.7917 | 45596.4267 | 45596.4268 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45586.7554 | 45586.6714 | 45594.3215 | 45596.4268 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401076 | GA, Athens / Commerce, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45582.4133 | 45596.3333 | 45597.7917 | 45596.3333 | 45597.7917 | 45600.4035 | 45600.4036 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45586.7554 | 45586.6718 | 45596.3219 | 45600.4036 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401116 | AL, Salem, Bartlets Ferry Dam, Move OPGW for GPC Substation | Low | Successful | Minor | Planned | MAR | TT | 45583.8771 | 45592.3333 | 45592.5833 | 45592.3333 | 45592.5833 | 45593.4295 | 45593.4297 | 2024 | 2024-10 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Migrate | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45586.6624 | 45586.6606 | 45592.3214 | 45593.4297 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401176 | AL/MS, West Alabama/MPC Area, R4 DWDM Upgrade Project Phase 5 (3 Days) | Medium | Successful | Moderate | Unplanned | DRB | TT | 45582.6686 | 45589.4167 | 45594.9167 | 45589.4167 | 45594.9167 | 45595.3919 | 45595.3921 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45588.6769 | 45588.4997 | 45589.4044 | 45595.3921 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401178 | AL, BIRMINGHAM, Parkwest Sub, relocate fiber | Low | Successful | Minor | Planned | DWM | TT | 45582.6806 | 45595.7917 | 45596.0417 | 45595.7917 | 45596.0417 | 45597.3907 | 45597.3949 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45588.5741 | 45588.5612 | 45595.7802 | 45597.3949 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401219 | GA, Augusta, Cut Augusta 15th St Trans Duke-Oconee Serial Tie Line Ckt Testing. | Low | Successful | Minor | Planned | MPH | TT | 45584.7348 | 45593.375 | 45593.7083 | 45593.375 | 45593.7083 | 45594.3828 | 45594.3829 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45586.7572 | 45586.6656 | 45593.3631 | 45594.3829 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401220 | GA, Augusta, Cut Augusta 15th St Trans Duke-Oconee Serial Tie Line Ckt Testing. (BACKUP DATE) | Low | Successful | Minor | Planned | MPH | TT | 45584.7348 | 45594.375 | 45594.7083 | 45594.375 | 45594.7083 | 45595.4009 | 45595.4009 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45586.7572 | 45586.6669 | 45594.3632 | 45595.4009 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401281 | AL, Gadsden, Splicing dark fibers around Gadsden TS to Weiss Dam | Low | Successful | Minor | Planned | DWM | TT | 45587.6374 | 45602.7917 | 45603.0208 | 45602.7917 | 45603.0208 | 45603.5047 | 45603.5048 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.6458 | 45593.6434 | 45602.781 | 45603.5048 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401282 | AL, Gadsden, Splicing dark fibers around Gadsden TS to Weiss Dam (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45587.6375 | 45603.7917 | 45604.0208 | 45603.7917 | 45604.0208 | 45604.434 | 45604.4361 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.6459 | 45593.6443 | 45603.7812 | 45604.4361 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401283 | AL, Gadsden, repairing broken fibers on route between Gadsden TS to Sand Mtn sub | Low | Successful | Minor | Planned | DWM | TT | 45587.6618 | 45615 | 45615.2917 | 45615 | 45615.2917 | 45615.4097 | 45615.4098 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.5833 | 45593.5826 | 45614.9926 | 45615.4098 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401284 | AL, Gadsden, repairing broken fibers on route between Gadsden TS to Sand Mtn sub (BACKUP DATE) | Low | Successful | Minor | Planned | DWM | TT | 45587.6618 | 45616.0208 | 45616.2917 | 45616.0208 | 45616.2917 | 45617.3935 | 45617.3936 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.5858 | 45593.5837 | 45616.0066 | 45617.3936 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401369 | AL, Octagon, Hwy 43, moving transmission lines for ALDOT | Medium | Successful | Moderate | Planned | DHA | TT | 45587.7389 | 45612.3333 | 45612.7917 | 45612.3333 | 45612.7917 | 45614.4305 | 45614.4307 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.6042 | 45593.5804 | 45612.3256 | 45614.4307 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401372 | GA. Atlanta, GPC HQ, Ciena T-Series Power Upgrades | Medium | Successful | Moderate | Planned | ADL | TT | 45587.9001 | 45594.3333 | 45594.7083 | 45594.3333 | 45594.7083 | 45595.4003 | 45595.4004 | 2024 | 2024-10 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45588.6778 | 45588.5577 | 45594.3215 | 45595.4004 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401397 | AL, Trussville, Adding new piece of 288 because of city road widening project. | Low | Successful | Minor | Planned | DKG | TT | 45588.4649 | 45595.9583 | 45596.9583 | 45595.9583 | 45596.9583 | 45597.396 | 45597.3961 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45590.4144 | 45588.5602 | 45595.9469 | 45597.3961 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401424 | AL, Silver Hill TS, move OPGW reroutes | Low | Successful | Minor | Planned | DHA | TT | 45588.8578 | 45608 | 45608.25 | 45608 | 45608.25 | 45608.3893 | 45608.3894 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DGH | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45593.5858 | 45593.5784 | 45607.9903 | 45608.3894 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401447 | GA, Carnesville / Commerce, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Unplanned | JMN | TT | 45589.5937 | 45593.3333 | 45594.7917 | 45593.3333 | 45594.7917 | 45595.3935 | 45595.3937 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45593.3633 | 45589.6938 | 45593.377 | 45595.3937 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401448 | GA, Carnesville / Commerce, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45589.5938 | 45595.3333 | 45596.7917 | 45595.3333 | 45595.7604 | 45596.4259 | 45596.4261 | 2024 | 2024-10 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45593.3633 | 45589.6951 | 45595.3217 | 45596.4261 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401452 | GA, Nichols EBTS G9827, cutting the site from the temp COW to the big COW | Low | Successful | Minor | Planned | CDL | TT | 45589.7029 | 45595.4583 | 45597.7917 | 45595.4583 | 45597.7917 | 45600.4058 | 45600.4058 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45593.3636 | 45590.4302 | 45595.4468 | 45600.4058 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401453 | GA, Nichols EBTS G9827, cutting the site from the temp COW to the big COW (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45589.703 | 45600.4583 | 45604.7917 | 45600.4583 | 45604.7917 | 45607.4967 | 45607.4968 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45593.3636 | 45590.431 | 45600.4473 | 45607.4968 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401472 | AL, Camden Transport Tower, replumb and re-tension guy wires on tower | Low | Successful | Minor | Planned | CLI | TT | 45590.5031 | 45602.375 | 45602.75 | 45602.375 | 45602.75 | 45603.5024 | 45603.5027 | 2024 | 2024-11 | Successful | Transport Device | Tower Structure | Repair | Transport | CBS | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45596.4478 | 45596.4461 | 45602.3643 | 45603.5027 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401473 | AL, Camden Transport Tower, replumb and re-tension guy wires on tower (BACKUP DATE) | Low | Successful | Minor | Planned | CLI | TT | 45590.5031 | 45609.375 | 45609.75 | 45609.375 | 45609.75 | 45610.4374 | 45610.4376 | 2024 | 2024-11 | Successful | Transport Device | Tower Structure | Repair | Transport | CBS | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45596.4478 | 45596.447 | 45609.3667 | 45610.4376 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401508 | AL, Moores Bridge, Phillips Mtn Transport, tower plumb and tension | Low | Successful | Minor | Planned | CLI | TT | 45593.505 | 45603.375 | 45603.7917 | 45603.375 | 45603.7917 | 45604.4314 | 45604.4315 | 2024 | 2024-11 | Successful | Transport Device | Tower Structure | Repair | Transport | CBS | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45600.4182 | 45600.4082 | 45603.3644 | 45604.4315 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401545 | AL, APC Corp HQ, replace generator and power control system | Low | Successful | Minor | Planned | JTA | TT | 45589.6483 | 45596.2917 | 45610.6458 | 45596.2917 | 45610.6458 | 45611.3818 | 45611.3819 | 2024 | 2024-11 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45593.4318 | 45593.4313 | 45596.2802 | 45611.3819 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401563 | AL, Southern ICON Ring, P&C circuits to be built between Barry 1 & Ellicott 1 | Medium | Successful | Moderate | Planned | RPY | TT | 45590.5713 | 45596.3958 | 45596.5417 | 45596.3958 | 45596.5417 | 45597.3966 | 45597.3969 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45593.461 | 45593.4213 | 45596.3775 | 45597.3969 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401565 | AL, Birmingham, ICON Ring, turn up circuits between Northwest, Powell Ave, & Parkwest | Medium | Successful | Moderate | Unplanned | RPY | TT | 45590.5831 | 45595.3958 | 45595.5417 | 45595.3958 | 45595.5417 | 45595.5563 | 45595.5566 | 2024 | 2024-10 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45593.4592 | 45593.4197 | 45595.3773 | 45595.5565 | 2024-Q4 | 2024-10 | 2024-Q4
CRQ000000401569 | GA, Sawnee Mtn. / Gainesville EBTS, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45590.6209 | 45600.3333 | 45601.7917 | 45600.3333 | 45601.7917 | 45602.4538 | 45602.4539 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45593.5764 | 45593.5748 | 45600.3223 | 45602.4539 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401570 | GA, Sawnee Mtn. / Gainesville EBTS, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45590.621 | 45602.3333 | 45603.7917 | 45602.3333 | 45603.7917 | 45604.425 | 45604.4254 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45593.5765 | 45593.5754 | 45602.3226 | 45604.4254 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401573 | GA, Gainesville OH / Gainesville EBTS, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45590.663 | 45601.3333 | 45602.7917 | 45601.3333 | 45602.7917 | 45603.5002 | 45603.5004 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45593.5809 | 45593.5765 | 45601.3225 | 45603.5004 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401574 | GA, Gainesville OH / Gainesville EBTS, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45590.6631 | 45609.3333 | 45610.7917 | 45609.3333 | 45610.7917 | 45611.3833 | 45611.3837 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45603.5513 | 45602.6025 | 45609.325 | 45611.3837 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401578 | GA, Fortson Transport, upgrade radio path | Low | Successful | Minor | Planned | TAJ | TT | 45593.4064 | 45609.3333 | 45609.7708 | 45609.3333 | 45609.7708 | 45610.4354 | 45610.4355 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | TAJ | SCS | INFRASTRUCTURE SERVICES | FO SE-PROJECTS & NATIONAL | 45593.6558 | 45593.6491 | 45609.325 | 45610.4355 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401586 | AL, Gadsden, repair dark fibers on route between Gadsden SP TS to Sand Mountain sub | Low | Successful | Minor | Planned | DWM | TT | 45593.4411 | 45617.0174 | 45617.2917 | 45617.0174 | 45617.2917 | 45617.3953 | 45617.3954 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | DWM | SCS | INFRASTRUCTURE SERVICES | FO AL LONG HAUL FIBER | 45610.4911 | 45610.4618 | 45617.0068 | 45617.3954 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401588 | AL, Clanton, Lay Dam LTE A8423, Tower plumb and tensioning | Low | Successful | Minor | Planned | CLI | TT | 45593.4444 | 45601.4583 | 45601.7917 | 45601.4583 | 45601.7917 | 45602.4542 | 45602.4543 | 2024 | 2024-11 | Successful | Transport Device | Tower Structure | Repair | Transport | CBS | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45596.4435 | 45596.4417 | 45601.4475 | 45602.4543 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401606 | AL, Auburn, Building/Cabinet, Adding XGSPON card with coexist module and move jumpers | Low | Successful | Minor | Planned | JGL | TT | 45593.6787 | 45602.4583 | 45602.75 | 45602.4583 | 45602.75 | 45603.5036 | 45603.5038 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JGL | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45594.5555 | 45594.5512 | 45602.4476 | 45603.5038 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401615 | AL, Auburn LTE A8107, SE Auburn, Adding CBRS to the Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45593.9343 | 45601.4167 | 45604.7917 | 45601.4167 | 45604.7917 | 45607.4977 | 45607.4978 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45594.5544 | 45594.5493 | 45601.4058 | 45607.4978 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401633 | AL, MONTGOMERY, SDC BLDG A, REPLACE DC RECTIFIER SYSTEM AND BATTERIES | Low | Successful | Minor | Planned | MVW | TT | 45593.8197 | 45607.3125 | 45611.7917 | 45607.3125 | 45611.7917 | 45614.4285 | 45614.4286 | 2024 | 2024-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45594.5557 | 45594.5528 | 45607.2957 | 45614.4286 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401635 | AL, Auburn LTE A8107, SE Auburn installing CBRS controllers in the cabinet | Low | Successful | Minor | Planned | CDL | TT | 45593.8877 | 45600.4583 | 45602.7917 | 45600.4583 | 45602.7917 | 45603.4993 | 45603.4994 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45594.5543 | 45594.5475 | 45600.4474 | 45603.4994 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401642 | AL/MS, West Alabama/MPC Area, R4 DWDM Upgrade Project: Cleanup Phase | Medium | Successful | Moderate | Planned | DRB | TT | 45594.3204 | 45600.4167 | 45600.75 | 45600.4167 | 45600.5722 | 45600.6053 | 45600.6055 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45594.5857 | 45594.5454 | 45600.4057 | 45600.6055 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401707 | AL, Bham, APC HQ, Migrate all APC/MPC Static devices from BHM to ATL. (BACKUP DATE) | Medium | Successful | Moderate | Planned | RAS | TT | 45595.5295 | 45609.7917 | 45609.9167 | 45609.7917 | 45609.9167 | 45610.4386 | 45610.4388 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Migrate | Transport | RAS | COM |  | CORE ENGINEERING | 45596.5142 | 45596.506 | 45609.7835 | 45610.4388 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401739 | AL, ANNISTON CREW HQ TRANSPORT, REPLACE INVERTER BATTERIES | Low | Successful | Minor | Planned | MVW | TT | 45594.5959 | 45603.3333 | 45603.75 | 45603.3333 | 45603.75 | 45604.4263 | 45604.4306 | 2024 | 2024-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45595.6427 | 45595.5832 | 45603.3227 | 45604.4306 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401791 | GA, Athens Transport, Insert New Ciena 6500 Nodes into Ring 1 Phase 2 | Medium | Successful | Moderate | Planned | ADL | TT | 45595.4737 | 45602.4167 | 45602.9167 | 45602.4167 | 45602.5958 | 45602.6005 | 45602.6007 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45600.3457 | 45597.4811 | 45602.4059 | 45602.6007 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401817 | GA, Georgia MISC, Phase One ADM Upgrades | Medium | Successful | Moderate | Planned | ADL | TT | 45596.4822 | 45607.3333 | 45607.9993 | 45607.3333 | 45607.9993 | 45608.3885 | 45608.3888 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45602.5104 | 45602.4479 | 45607.3235 | 45608.3888 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401818 | GA, Athens / Bostwick EBTS, 6GHz to 11GHz MW Radio Upgrade | Low | Successful | Minor | Planned | JMN | TT | 45596.4903 | 45607.3333 | 45608.7917 | 45607.3333 | 45608.7917 | 45609.4303 | 45609.4304 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45602.5115 | 45602.5092 | 45607.3235 | 45609.4304 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401850 | GA, Various Location, GA Misc, Phase 2 Circuit Migrations | Medium | Successful | Moderate | Planned | ADL | TT | 45596.6433 | 45609.3333 | 45609.9993 | 45609.3333 | 45609.9993 | 45610.4367 | 45610.437 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45602.3617 | 45601.7082 | 45609.325 | 45610.437 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401851 | GA, North Tifton EBTS Transport, TID Consolidate DWDM Nodes | Medium | Successful | Moderate | Planned | ADL | TT | 45596.6495 | 45609.7083 | 45609.9993 | 45609.7083 | 45609.9993 | 45610.438 | 45610.4382 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45602.5086 | 45602.4902 | 45609.7001 | 45610.4382 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401855 | GA, Atlanta, GPC HQ, Phase 3 GA Misc Circuit Migrations | Medium | Successful | Moderate | Planned | ADL | TT | 45596.6579 | 45610.3333 | 45610.9993 | 45610.3333 | 45610.9993 | 45611.3841 | 45611.3843 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45602.594 | 45602.5678 | 45610.3253 | 45611.3843 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401857 | AL and GA, Montgomery to Macon, Ciena T-Series Channel Upgrade from 200G to 300G | Medium | Successful | Moderate | Planned | GPB | TT | 45596.6647 | 45603.75 | 45603.9583 | 45603.75 | 45603.9583 | 45604.4331 | 45604.4334 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45600.3442 | 45597.6784 | 45603.7395 | 45604.4334 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401868 | GA, Various Locations, Phase 4 GA Misc Circuit Migrations | Medium | Successful | Moderate | Planned | ADL | TT | 45597.3699 | 45614.3333 | 45614.9993 | 45614.3611 | 45614.9993 | 45615.4042 | 45615.4045 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45603.5697 | 45603.4854 | 45614.3257 | 45615.4045 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401869 | GA, North Tifton EBTS Transport, TID Consolidate DWDM Nodes (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45597.374 | 45614.7083 | 45614.9993 | 45614.7083 | 45614.9993 | 45615.4091 | 45615.4093 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45602.5081 | 45602.4909 | 45614.7009 | 45615.4093 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401913 | AL, Birmingham APC HQ, PCC, and GSC Ciena 6500 Circuit Moves to ADM Phase 3 | Medium | Successful | Moderate | Planned | GPB | TT | 45600.4741 | 45616.4167 | 45617.9167 | 45616.4167 | 45617.9167 | 45618.4958 | 45618.4964 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45603.5703 | 45603.4904 | 45616.4095 | 45618.4964 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401920 | GA/AL, Various Locations, Phase One (Day 2), Ciena ADM Upgrades | Medium | Successful | Moderate | Planned | ADL | TT | 45596.5128 | 45608.3333 | 45608.9993 | 45608.3333 | 45608.9993 | 45609.4319 | 45609.4322 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45601.5705 | 45601.5096 | 45608.3249 | 45609.4322 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401941 | GA, GPC HQ, LTE Core Router Replacement GAXGPMPCR02 | Medium | Successful | Moderate | Planned | DRI | TT | 45596.7057 | 45602.9583 | 45603.125 | 45602.9583 | 45603.2104 | 45603.4941 | 45603.4944 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45600.3462 | 45597.4833 | 45602.9477 | 45603.4944 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401952 | AL, Birmingham, APC HQ, Add Modules to Ciena T-Series | Medium | Successful | Moderate | Planned | GPB | TT | 45597.4183 | 45608.4167 | 45608.9167 | 45608.4167 | 45608.9167 | 45609.4326 | 45609.4328 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45601.6156 | 45601.6026 | 45608.4082 | 45609.4328 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401992 | AL, Birmingham APC HQ and AT&T Ciena 6500 Circuit Moves to ADM Phase 2 | Medium | Successful | Moderate | Planned | GPB | TT | 45600.4496 | 45615.4167 | 45615.9167 | 45615.4431 | 45615.6104 | 45617.3928 | 45617.393 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45603.5706 | 45603.4883 | 45615.4093 | 45617.393 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000401995 | GA, Atlanta ICON ring, NW Sub ICON to be removed | Medium | Successful | Moderate | Planned | RPY | TT | 45600.4903 | 45616.4583 | 45616.7083 | 45616.4583 | 45616.7083 | 45617.394 | 45617.3942 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45602.3544 | 45601.6211 | 45616.4511 | 45617.3942 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402011 | GA, Nichols EBTS G9827, cutting the site from the temp COW to the big COW | Low | Successful | Minor | Planned | CDL | TT | 45600.7458 | 45607.3542 | 45611.75 | 45607.3542 | 45611.75 | 45614.4295 | 45614.4296 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45602.3333 | 45601.6153 | 45607.3374 | 45614.4296 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402021 | GA, DAVIS ST SUB, Activate SWAN circuit for New CGR | Medium | Successful | Moderate | Planned | DAP | TT | 45600.5277 | 45607.4167 | 45607.5833 | 45607.4167 | 45607.5833 | 45607.6579 | 45607.6583 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45602.3509 | 45601.6181 | 45607.4069 | 45607.6583 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402023 | GA, Savannah ICON Ring, insert SFP in Rice Hope C and configure | Medium | Successful | Moderate | Planned | RPY | TT | 45600.5468 | 45614.5 | 45614.7083 | 45614.5 | 45614.5729 | 45615.4066 | 45615.4069 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45602.3607 | 45601.6197 | 45614.4925 | 45615.4069 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402046 | GA, Lakemont, ROW, replace damaged sections of fiber | Medium | Successful | Moderate | Planned | MAR | TT | 45600.8621 | 45607.2917 | 45610.7083 | 45607.2917 | 45610.6486 | 45611.3824 | 45611.3827 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | MAB | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45602.3623 | 45601.6086 | 45607.2818 | 45611.3827 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402106 | AL, ANNISTON CREQ HQ TRANSPORT, REPLACE DC BATTERIES | Low | Successful | Minor | Planned | MVW | TT | 45602.4083 | 45617.3333 | 45618.75 | 45617.3333 | 45618.75 | 45622.3447 | 45622.3449 | 2024 | 2024-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45603.5855 | 45603.575 | 45617.3262 | 45622.3449 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402138 | AL, APC HQ, LTE/MPLS Core Router Replacement ALXAPMPCR01 | Medium | SuccessfulwithIssues | Moderate | Planned | DRI | TT | 45601.5378 | 45618 | 45618.1667 | 45618 | 45618.1667 | 45618.4724 | 45618.4725 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45609.3658 | 45608.5923 | 45617.9793 | 45618.4725 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402139 | AL, APC HQ, LTE/MPLS Core Router Replacement ALXAPMPCR02 | Medium | Successful | Moderate | Planned | DRI | TT | 45601.54 | 45611 | 45611.1667 | 45611 | 45611.1521 | 45611.3794 | 45611.3798 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45603.5974 | 45603.5736 | 45610.9921 | 45611.3798 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402149 | AL, Trussville, Adding new piece of 288 because of city road widening project. | Low | Successful | Minor | Planned | DKG | TT | 45601.677 | 45609.7917 | 45611.0417 | 45609.7917 | 45611.0417 | 45611.3857 | 45611.3858 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45602.338 | 45601.7031 | 45609.7835 | 45611.3858 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402189 | AL, ANNISTON CREQ HQ TRANSPORT, MODIFY AC PANEL WIRING | Low | Successful | Minor | Planned | MVW | TT | 45602.756 | 45617.3333 | 45618.75 | 45617.3333 | 45617.6111 | 45617.6332 | 45617.6334 | 2024 | 2024-11 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45603.5855 | 45603.5744 | 45617.3262 | 45617.6334 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402264 | AL, Mobile, Migrate Mobile DCC circuits / Turn up new "Mobile-SDC DSCADA 1G" DWDM Ckt | Medium | Successful | Moderate | Planned | DRB | TT | 45603.5315 | 45610.4167 | 45610.75 | 45610.4167 | 45610.5799 | 45611.3774 | 45611.3778 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45603.6637 | 45603.6583 | 45610.4086 | 45611.3778 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402274 | AL, Gorgas EBTS A9155, installing CBRS at 294 ft not on Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45603.6531 | 45614.4583 | 45618.8333 | 45614.4583 | 45618.8333 | 45621.6348 | 45621.6349 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45604.4076 | 45603.6696 | 45614.4508 | 45621.6349 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402276 | AL, Gorgas EBTS A9155, installing CBRS at 294 ft not on Skymounts (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45603.6531 | 45628.4583 | 45632.7917 | 45628.4583 | 45632.7917 | 45635.4115 | 45635.4118 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45604.4077 | 45603.6705 | 45628.4431 | 45635.4118 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402320 | AL, APCO HQ, 1925 building Service Level, Fiber Room 1, replace generator and power controls | Low | Successful | Minor | Planned | JTA | TT | 45603.5118 | 45611.2708 | 45626.8125 | 45611.2708 | 45626.8125 | 45628.6886 | 45628.689 | 2024 | 2024-12 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45603.5967 | 45603.5775 | 45611.256 | 45628.689 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402394 | AL, GORGAS SP TRANSPORT, BATTERY REPLACEMENT | Low | Successful | Minor | Planned | MSM | TT | 45607.3842 | 45630.375 | 45632.7083 | 45630.375 | 45632.7083 | 45632.7131 | 45632.7131 | 2024 | 2024-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45614.4744 | 45614.472 | 45630.36 | 45632.7131 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402412 | MS, Hattiesburg Hub Station Service Power Interruption | Low | Successful | Minor | Planned | DRB | TT | 45607.5284 | 45610.375 | 45610.75 | 45610.375 | 45610.7361 | 45611.3848 | 45611.3849 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45608.4498 | 45607.6544 | 45610.367 | 45611.3849 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402441 | GA, Bostwick EBTS / Madison Transport, 6GHz to 11GHz MW Radio Upgrade (BACKUP DATE) | Low | Successful | Minor | Planned | JMN | TT | 45607.3769 | 45632.3333 | 45632.7917 | 45632.3333 | 45632.7917 | 45635.4102 | 45635.4104 | 2024 | 2024-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | JMN | SCS | INFRASTRUCTURE SERVICES | FO NE-PROJECTS | 45621.8026 | 45621.6351 | 45632.3186 | 45635.4104 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402468 | GA, Various Sites, Add 10G MDA modules for North GA Hydro SAR COAM Ring. | Low | Successful | Minor | Planned | MPH | TT | 45607.6071 | 45614.375 | 45614.7083 | 45614.375 | 45614.625 | 45615.4019 | 45615.402 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45608.4496 | 45607.6557 | 45614.3674 | 45615.402 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402483 | AL, Brookwood LTE, Adding LTE electronics to the cabinet | Low | Successful | Minor | Planned | CDL | TT | 45607.8703 | 45615.4167 | 45617.7917 | 45615.4167 | 45617.7917 | 45618.4887 | 45618.4908 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45609.3571 | 45608.6214 | 45615.4093 | 45618.4908 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402504 | GA, Waynesboro EBTS, adding MW path to Wrens GA | Low | Successful | Minor | Planned | CDL | TT | 45608.5666 | 45614.4583 | 45618.7917 | 45614.4583 | 45618.7917 | 45621.6336 | 45621.6337 | 2024 | 2024-11 | Successful | Transport Device | Microwave TX/RX (Licensed) | Install | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45609.357 | 45608.6187 | 45614.4508 | 45621.6337 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402517 | GA, Wrens EBTS G9309, cutting site from COW to temp ATC site | Low | Successful | Minor | Planned | CDL | TT | 45608.6632 | 45616.4583 | 45618.7917 | 45616.4583 | 45618.7917 | 45621.6358 | 45621.636 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Migrate | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45610.4912 | 45610.4584 | 45616.4511 | 45621.636 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402518 | GA, Wrens EBTS G9309, cutting site from COW to temp ATC site (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45608.6633 | 45628.4167 | 45632.7917 | 45628.4167 | 45632.7917 | 45635.4109 | 45635.4111 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Migrate | Transport | CDL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45610.4912 | 45610.4592 | 45628.4014 | 45635.4111 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402524 | GA, DAVIS STREET SUBSTATION, Activate a new subtended ring | Medium | Successful | Moderate | Planned | DAP | TT | 45607.6407 | 45637.3958 | 45637.6875 | 45637.3958 | 45637.6875 | 45638.4509 | 45638.4512 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45630.4114 | 45629.5767 | 45637.3887 | 45638.4512 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402525 | GA, DAVIS STREET SUBSTATION, Activate a new subtended ring (BACKUP DATE) | Medium | Successful | Moderate | Unplanned | DAP | TT | 45607.6407 | 45645.3958 | 45645.6875 | 45645.4042 | 45645.4785 | 45645.4865 | 45645.4868 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | DAP | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45644.4186 | 45643.6614 | 45645.3881 | 45645.4868 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402585 | AL, BALD ROCK TRANSPORT, BATTERY REPLACEMENT | Low | Successful | Minor | Planned | MSM | TT | 45609.3746 | 45628.375 | 45630.7083 | 45628.375 | 45630.7083 | 45631.4596 | 45631.4597 | 2024 | 2024-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MSM | SCS | INFRASTRUCTURE SERVICES | FO AL OPERATIONS | 45614.4719 | 45614.4704 | 45628.355 | 45631.4597 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402715 | AL/GA, APC HQ, Reseat/Replace Ciena DWDM OTN FLEX MOTR Card/Migrate ADMS circuit | Medium | Successful | Moderate | Planned | DRB | TT | 45610.6882 | 45617.7083 | 45617.7917 | 45617.7083 | 45617.7604 | 45618.4676 | 45618.4679 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45611.6006 | 45611.4157 | 45617.6875 | 45618.4679 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402751 | AL, Dadeville, changing out card 11 at Red Ridge and West Dadeville OLT's | Low | Successful | Minor | Planned | DKG | TT | 45610.634 | 45617.2917 | 45617.7917 | 45617.4153 | 45617.4903 | 45618.4973 | 45618.4974 | 2024 | 2024-11 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Upgrade/Modify | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45611.5916 | 45611.4144 | 45617.2846 | 45618.4974 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402831 | GA, Atlanta Area, Miscellaneous DWDM Upgrade Project Cleanup Phase | Medium | Successful | Moderate | Planned | DRB | TT | 45611.5502 | 45617.375 | 45617.7083 | 45617.375 | 45617.4944 | 45618.4988 | 45618.499 | 2024 | 2024-11 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45614.5529 | 45614.5312 | 45617.368 | 45618.499 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402838 | GPC & APC, LTE core router new LTE interfaces | Medium | Successful | Moderate | Planned | DRI | TT | 45611.6402 | 45617.75 | 45617.8333 | 45617.75 | 45617.8021 | 45618.4711 | 45618.4713 | 2024 | 2024-11 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45614.6065 | 45614.5397 | 45617.7292 | 45618.4713 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402917 | *ADVISORY* GA, Douglas Hills (DHA), GPC Performing test of backup power systems | Low | Successful | Minor | Planned | JTC | TT | 45615.5436 | 45618.4167 | 45618.5625 | 45618.4167 | 45618.7312 | 45621.3214 | 45621.3216 | 2024 | 2024-11 | Successful | Facilities Component | Generator | Upgrade/Modify | Transport | JTC | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45615.5924 | 45615.5821 | 45618.3961 | 45621.3216 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000402946 | GA, Region 7, Ciena 6500 ADM Upgrades/Circuit Migrations | Medium | Successful | Moderate | Planned | ADL | TT | 45614.9119 | 45630.3333 | 45630.9993 | 45630.3333 | 45630.9993 | 45631.4603 | 45631.4606 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45619.4947 | 45618.6899 | 45630.3183 | 45631.4606 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402947 | GA, Region 7, Ciena 6500 ADM Circuit Migrations | Medium | Successful | Moderate | Planned | ADL | TT | 45614.9189 | 45631.3333 | 45631.9993 | 45631.3333 | 45631.9993 | 45632.4694 | 45632.4697 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Migrate | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45619.4944 | 45618.6908 | 45631.3185 | 45632.4697 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000402948 | GA, GPC HQ/Macon, adding T-Series equipment | Medium | Successful | Moderate | Planned | ADL | TT | 45614.9405 | 45628.3333 | 45629.9993 | 45628.3333 | 45629.9993 | 45630.4052 | 45630.4055 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45617.4839 | 45617.4018 | 45628.3133 | 45630.4055 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403015 | AL, Alabaster, Splicing dark fiber for C-Spire handoff. | Low | Successful | Minor | Planned | RCA | TT | 45616.4912 | 45635.3333 | 45636.7917 | 45635.3333 | 45636.7917 | 45637.4009 | 45637.401 | 2024 | 2024-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | RC | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45617.6182 | 45617.6154 | 45635.3189 | 45637.401 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403059 | AL, Birmingham, Building 2 fibers from 12th Street Crew to APC Corporate | Low | Successful | Minor | Planned | DKG | TT | 45616.608 | 45629.2917 | 45632.7917 | 45629.2917 | 45632.7917 | 45635.4123 | 45635.4124 | 2024 | 2024-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Install | Transport | DKG | SCS | INFRASTRUCTURE SERVICES | FO AL FIBER TO DISTRIBUTION | 45617.6139 | 45617.6125 | 45629.2765 | 45636.404 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403089 | AL, Gorgas EBTS A9155, installing CBRS at 294 ft not on Skymounts | Low | Successful | Minor | Planned | CDL | TT | 45617.5677 | 45619.375 | 45619.8333 | 45619.375 | 45619.8333 | 45622.3432 | 45622.3434 | 2024 | 2024-11 | Successful | Transport Device | Antenna System | Install | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45617.6136 | 45617.6076 | 45619.3545 | 45622.3434 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000403093 | GA, Atlanta ICON ring, NW Sub ICON to be removed | Medium | Successful | Moderate | Planned | RPY | TT | 45617.6179 | 45629.4167 | 45629.6667 | 45629.4271 | 45629.4986 | 45629.5294 | 45629.5301 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Remove/Retire | Transport | RY | SCS | INFRASTRUCTURE SERVICES | TELECOM EDGE SERVICES | 45618.3138 | 45617.6671 | 45629.4015 | 45629.5301 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403121 | GA, AUGUSTA 15TH ST AUGUSTA TRANSPORT, DC RECTIFIER LIFECYCLE REPLACEMENT | Low | Successful | Minor | Planned | MVW | TT | 45616.5922 | 45628.3333 | 45632.7083 | 45628.3333 | 45632.7083 | 45632.7125 | 45632.7126 | 2024 | 2024-12 | Successful | Facilities Component | DC Backup System | Upgrade/Modify | Transport | MVW | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45617.6136 | 45617.6084 | 45628.3133 | 45632.7126 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403127 | AL, Mobile LTE A8575, Royal St, adding CBRS to the existing boom mounts | Low | Successful | Minor | Planned | CDL | TT | 45616.6367 | 45635.4167 | 45639.7917 | 45635.4167 | 45639.7917 | 45642.4406 | 45642.4408 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Install | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45617.6185 | 45617.6164 | 45635.4023 | 45642.4408 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403130 | AL, Dadeville EBTS A9136, moving the LTE up the tower and adding CBRS | Low | Successful | Minor | Planned | CDL | TT | 45616.668 | 45635.4583 | 45639.7917 | 45635.4583 | 45639.7917 | 45642.4418 | 45642.442 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Install | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45617.7459 | 45617.6256 | 45635.444 | 45642.442 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403131 | AL, Dadeville EBTS A9136, moving the LTE up the tower and adding CBRS (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45616.668 | 45642.4583 | 45645.7917 | 45642.4583 | 45645.7917 | 45646.7298 | 45646.7299 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Install | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45617.746 | 45617.6267 | 45642.4433 | 45646.7299 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403136 | AL, Parrish, Gorgas LTE, Move LTE equipment further up the rack | Low | Successful | Minor | Planned | RBK | TT | 45616.9601 | 45629.375 | 45629.6667 | 45629.375 | 45629.6667 | 45630.406 | 45630.4061 | 2024 | 2024-12 | Successful | Facilities Component | Cabinet / Rack | Upgrade/Modify | Transport | RBK | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN SUPERVISOR NW REGION | 45617.6246 | 45617.6135 | 45629.3599 | 45630.4061 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403153 | GA, Tifton EBTS Ciena 6500 Module adds, and OTS move | Medium | Successful | Moderate | Planned | GPB | TT | 45617.3997 | 45628.625 | 45628.9583 | 45628.625 | 45628.9583 | 45629.3949 | 45629.3952 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45617.6201 | 45617.6095 | 45628.6098 | 45629.3952 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403160 | AL, Montgomery, J St, Ciena 6500 T-Series DC Power Upgrades & Module Additions | Medium | Successful | Moderate | Planned | GPB | TT | 45617.4355 | 45635.5833 | 45635.9583 | 45635.6444 | 45635.7847 | 45636.6212 | 45636.6215 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | GPB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45618.3147 | 45617.665 | 45635.569 | 45636.6215 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403232 | AL, Haleyville, Upgrade Haleyville Ofc and Crew WAN from 18M to 100M. | Low | Successful | Minor | Planned | MPH | HH | 45621.3294 | 45636.75 | 45636.9583 | 45636.75 | 45636.9583 | 45637.4014 | 45637.4016 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | JMP | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45622.4157 | 45622.4131 | 45636.7358 | 45637.4016 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403241 | Alabama Montgomery 1810 William Dickerson Dr Building "C" | Low | Successful | Minor | Planned | JTA | HH | 45621.4369 | 45628.4167 | 45628.5833 | 45628.4167 | 45628.5833 | 45628.6701 | 45628.6702 | 2024 | 2024-12 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45622.3973 | 45622.3878 | 45628.4015 | 45628.6702 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403271 | Al, Brookwood, LTE, A8398 Searles adding CBRS to the existing Skymounts | Low | Successful | Minor | Planned | CDL | HH | 45622.3579 | 45628.5 | 45632.7917 | 45628.5 | 45632.7917 | 45635.3814 | 45635.3816 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Install | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45622.4008 | 45622.3976 | 45628.4848 | 45635.3816 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403304 | GPC/APC new LTE links to the Linc EPC Core | Medium | Successful | Moderate | Planned | DRI | TT | 45623.6581 | 45630.4792 | 45630.541 | 45630.4792 | 45630.5417 | 45630.575 | 45630.5753 | 2024 | 2024-12 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | DR | SCS | INFRASTRUCTURE SERVICES | TELECOM AGGREGATE SERVICES | 45628.4654 | 45628.4409 | 45630.4711 | 45630.5753 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403317 | GA, Atlanta, 270 Peachtree, Installing new DC Power for Robinson Electric | Low | Successful | Minor | Planned | SDG | TT | 45628.4135 | 45635.875 | 45636.25 | 45636.0479 | 45636.1285 | 45636.622 | 45636.6221 | 2024 | 2024-12 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | CONNECTIVITY AND STRATEGIC INNOVATION | 45630.377 | 45628.6557 | 45635.8607 | 45636.6221 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403318 | GA, Atlanta, 270 Peachtree, Installing new DC Power for Robinson Electric. (BACKUP DATE) | Low | Successful | Minor | Planned | SDG | TT | 45628.4136 | 45636.875 | 45637.25 | 45636.875 | 45637.25 | 45637.402 | 45637.4021 | 2024 | 2024-12 | Successful | Facilities Component | DC Backup System | Install | Transport | SDG | APC |  | CONNECTIVITY AND STRATEGIC INNOVATION | 45630.377 | 45628.6561 | 45636.8608 | 45637.4021 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403354 | Advisory - Southern Linc BRM Application Patch | Low | Successful | Minor | Unplanned | JNB | HH | 45622.4352 | 45622.5833 | 45622.625 | 45622.5833 | 45622.625 | 45622.6356 | 45623.3827 | 2024 | 2024-11 | Successful | Facilities Component | Cabinet / Rack | Upgrade/Modify | Transport | JNB | COM |  | IS PORTFOLIO | 45622.455 | 45622.4545 | 45622.563 | 45623.3827 | 2024-Q4 | 2024-11 | 2024-Q4
CRQ000000403366 | GA, Buckhead Primary, splice new Lateral into new Verizon route. | Medium | Successful | Moderate | Planned | RFU | TT | 45622.6708 | 45640.3333 | 45640.75 | 45640.3333 | 45640.75 | 45642.4451 | 45642.4455 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Upgrade/Modify | Transport | RWF | SCS | INFRASTRUCTURE SERVICES | FO GA LONG HAUL FIBER | 45628.4659 | 45628.4467 | 45640.32 | 45642.4455 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403384 | GA, Forest Park LTE G8191, cutting from COM shelter to Linc shelter | Low | Successful | Minor | Planned | CDL | TT | 45623.6133 | 45636.375 | 45639.7917 | 45636.375 | 45639.7917 | 45642.4427 | 45642.4428 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Migrate | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45630.3902 | 45629.4036 | 45636.3607 | 45642.4428 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403385 | GA, Forest Park LTE G8191, cutting from COM shelter to Linc shelter (BACKUP DATE) | Low | Successful | Minor | Planned | CDL | TT | 45623.6133 | 45642.4167 | 45645.75 | 45642.4167 | 45645.75 | 45646.7293 | 45646.7294 | 2024 | 2024-12 | Successful | Transport Device | Antenna System | Migrate | Transport | CL | COM | PRODUCT DEVELOPMENT & SUPPORT | RAN OPERATIONS | 45628.4511 | 45628.4431 | 45642.4016 | 45646.7294 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403393 | GA, Various Locations, Insert Shoals Crossing into DWDM Ring 1 | Medium | Successful | Moderate | Planned | ADL | TT | 45624.7358 | 45642.3333 | 45643.0833 | 45642.3333 | 45643.0833 | 45643.3968 | 45643.3974 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45630.4039 | 45628.6441 | 45642.3182 | 45643.3974 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403394 | GA, Various Locations, Insert Shoals Crossing into DWDM Ring 1 (BACKUP DATE) | Medium | Successful | Moderate | Planned | ADL | TT | 45624.7358 | 45643.3333 | 45644.0833 | 45643.3333 | 45644.0833 | 45644.4984 | 45644.4986 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45630.4007 | 45628.6456 | 45643.3184 | 45644.4986 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403414 | GA, **ADVISORY** CHAMBLEE PEACHTREE DEKALB AIRPORT, Building Services planned power outage | Low | Successful | Minor | Planned | WWA | TT | 45628.4485 | 45647.2917 | 45647.4583 | 45647.2917 | 45647.4583 | 45649.4154 | 45649.4156 | 2024 | 2024-12 | Successful | Facilities Component | Transformer | Repair | Transport | WCW | SCS | INFRASTRUCTURE SERVICES | FO NE OPERATIONS | 45637.3587 | 45631.462 | 45647.2773 | 45649.4156 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403474 | AL, Jasper Transport, Alcatel 9500 6GHz to 11GHz replacement. | Low | Successful | Minor | Planned | WJL | TT | 45629.6247 | 45636.375 | 45638.75 | 45636.375 | 45638.75 | 45639.411 | 45639.4112 | 2024 | 2024-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM WIRELESS | 45630.4334 | 45630.4326 | 45636.3607 | 45639.4112 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403523 | GA, DWDM Ring 1, Install New Cards in T-Series and Test Links to Genesis Data Center. | Medium | Successful | Moderate | Planned | ADL | TT | 45628.6185 | 45635.3333 | 45639.9993 | 45635.3333 | 45639.9993 | 45642.4391 | 45642.4394 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Install | Transport | ADL | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45630.4097 | 45629.3983 | 45635.3189 | 45642.4394 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403778 | GA/AL, Southern Linc Atlanta/Birmingham Data Centers DNS changes (BACKUP DATE) | Low | Successful | Minor | Planned | GEB | TT | 45632.7004 | 45637.8333 | 45637.9167 | 45637.8333 | 45637.9167 | 45638.4526 | 45638.4527 | 2024 | 2024-12 | Successful | Transport Device | Other Transport Device | Upgrade/Modify | Transport | GEB | COM |  | NETWORKING | 45632.7263 | 45632.7144 | 45637.8194 | 45638.4527 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403973 | AL, Jasper Transport, Alcatel 9500 6GHz to 11GHz replacement. | Low | Successful | Minor | Planned | WJL | TT | 45636.4868 | 45639.375 | 45640.75 | 45639.375 | 45640.75 | 45642.4436 | 45642.4437 | 2024 | 2024-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM WIRELESS | 45636.6375 | 45636.6282 | 45639.3615 | 45642.4437 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403974 | AL, Jasper Transport, Alcatel 9500 6GHz to 11GHz replacement. (BACKUP DATE) | Low | Successful | Minor | Planned | WJL | TT | 45636.4869 | 45642.375 | 45643.75 | 45642.375 | 45643.75 | 45644.4977 | 45644.498 | 2024 | 2024-12 | Successful | Transport Device | Microwave TX/RX (Licensed) | Upgrade/Modify | Transport | WJL | SCS | INFRASTRUCTURE SERVICES | TELECOM WIRELESS | 45636.6375 | 45636.6287 | 45642.3599 | 45644.498 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000403976 | AL, Tuscaloosa, Western Division Office, building electrical infrastructure renovation | Low | Successful | Minor | Planned | JTA | TT | 45636.5023 | 45640.2917 | 45641.75 | 45640.2917 | 45641.75 | 45642.4445 | 45642.4446 | 2024 | 2024-12 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Upgrade/Modify | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45636.6401 | 45636.6273 | 45640.2783 | 45642.4446 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000404080 | GA, Offerman, DWDM High Received Span Loss Issue, Clean/Roll Fibers to Spare Pair | Medium | Successful | Moderate | Planned | DRB | TT | 45639.6509 | 45645.7083 | 45645.875 | 45645.7083 | 45645.875 | 45646.727 | 45646.7283 | 2024 | 2024-12 | Successful | Transport Device | Optical Transport Equipment | Repair | Transport | DRB | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45642.3345 | 45639.7396 | 45645.6938 | 45646.7283 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000404133 | Advisory/Oper Event: GA - ATLANTA - FIBER RELOCATION - UNITI NCC-19136 | Low | Successful | Std/PreApp | Planned | HHA | HH | 45638.4063 | 45638.9167 | 45639.2083 | 45638.9167 | 45639.2083 | 45639.7417 | 45639.7418 | 2024 | 2024-12 | Successful | Transport Device | FIBER OPTIC TRANSPORT - FDP / OSP | Repair | Transport | HMH | SCS | INFRASTRUCTURE SERVICES | TELECOM CORE SERVICES | 45638.4261 | 45638.4261 | 45638.903 | 45639.7418 | 2024-Q4 | 2024-12 | 2024-Q4
CRQ000000404164 | AL, Montgomery, 1810 William Dickerson Dr Building C, PM power distribution equipment | Low | Successful | Minor | Planned | JTA | TT | 45639.6355 | 45645.4167 | 45645.7083 | 45645.4167 | 45645.7083 | 45646.7302 | 45646.7303 | 2024 | 2024-12 | Successful | Facilities Component | Uninterruptable Power Supply (UPS) | Repair | Transport | JT | SCS | INFRASTRUCTURE SERVICES | TECH INFRASTRUCTURE ENGRG | 45639.7505 | 45639.7387 | 45645.402 | 45646.7303 | 2024-Q4 | 2024-12 | 2024-Q4

## Glossary
Verbiage | Meaning
CRQ | Change Request Query
Change ID | Numberic ID used to identify CRQ
Summary | A brief summary of the work scheduled to be performed
Priority | Used to rank which cases would take precident over others if needed
Status Reason | Description of work status
Change Plannning | ???? Not Needed
Impact | Risk Impact to the Telecommunications Infrastructure. Lowest risk work is set to Minor. Medium risk work is set to Moderate and Highest risk is set to Major.
Submitter | Name of person that is submitting the Change Request.
Coordinator | Person responsible for processing the change request and ensuring the communication to all business partners
SubmitDateTime | Time the Change request submitted
SchStartDateTime | Time when the change work is scheduled to begin (Pending approval from appropriate Operation Centers)
SchEndDateTime | Time when work is schedule to be completed
ActualStartDateTime | Time the change work actually began
ActualEndDateTime | Time the change work was completed
CompletedYear | I hope no one needs this one explained
CompletedDateTime | Time that Change ticket was marked completed
ClosedDateTime | Time that change ticket was closed
CompletedMonth | I hope no one needs this one explained
ChangeSuccess | Status of case upon being worked
ProdCat2 | Product Category 2 is the area of technology in which the work was performed
SchHoursWorked | Amount of hours the work is scheduled to last
ProdCat3 | Product Category is the type of Telecommunications equipment that will be worked on
OpCat1 | Operation Category is the type of operation to be performed.
Customer | Initials of person the work is being performed by (Typically the same as submitter)
CustomerOpCo | Operating Company that the customer reports to (Eg: Georgia Power, Alabama Power, Southern Company Services, Southern Nuclear, etc)
CustomerGroup | Organization in which the customer reports to (Which Vice President the customer reports to)
CustomerDept | Southern Company Organization that the submitter works in